## Sprint Comparison
Sprint Comparison — FILTER (FILTER + PTGM + FDSE) — 8 sprints across 4 months
Anchor Month | Sprint | Window | Working Days | Holidays | Effective WD | Active Team | Available (h) | Net Available (h) | Completed (h) | Completed Tickets | Spillover (OE h) | Spillover Tickets | Removed (OE h) | Sprint Completion (tickets) | Sprint Completion (planned hrs) | Mid-sprint Adds (core) | P1 Escalations (open / total)
Jan 2026 | sprint-Arthur | 06 Jan → 19 Jan 2026 | 10 | 0 | 10 | 17 | 1152 | 921.6 | 546.1 | 98 | 0.5 | 13 | 163 | 88.29% | 99.91% | 21 | 0 / 9
Jan 2026 | sprint-Bertha | 20 Jan → 02 Feb 2026 | 10 | 1 | 9 | 17 | 1008 | 806.4 | 1043.84 | 145 | 0.5 | 12 | 136 | 92.36% | 99.95% | 14 | 1 / 13
Jan 2026 TOTAL | 2 sprint(s) |  | 20 | 1 | 19 |  | 2160 | 1728 | 1589.94 | 243 | 1 | 25 | 299 | 90.32% | 99.93% | 35 | 1 / 22
Feb 2026 | sprint-Cristobal | 03 Feb → 16 Feb 2026 | 10 | 1 | 9 | 17 | 1051.2 | 840.96 | 724 | 119 | 0 | 1 | 58 | 99.17% | 100% | 13 | 1 / 6
Feb 2026 | sprint-Dolly | 17 Feb → 02 Mar 2026 | 10 | 0 | 10 | 18 | 1152 | 921.6 | 568 | 50 | 16 | 2 | 151 | 96.15% | 96.99% | 15 | 1 / 5
Feb 2026 TOTAL | 2 sprint(s) |  | 20 | 1 | 19 |  | 2203.2 | 1762.56 | 1292 | 169 | 16 | 3 | 209 | 97.66% | 98.5% | 28 | 2 / 11
Mar 2026 | sprint-Edouard | 03 Mar → 16 Mar 2026 | 10 | 1 | 9 | 17 | 1051.2 | 840.96 | 1508 | 192 | 128 | 28 | 92 | 87.27% | 91.72% | 18 | 2 / 11
Mar 2026 | sprint-Fay | 17 Mar → 30 Mar 2026 | 10 | 1 | 9 | 17 | 1008 | 806.4 | 955 | 138 | 30 | 11 | 38 | 92.62% | 96.62% | 27 | 2 / 7
Mar 2026 TOTAL | 2 sprint(s) |  | 20 | 2 | 18 |  | 2059.2 | 1647.36 | 2463 | 330 | 158 | 39 | 130 | 89.95% | 94.17% | 45 | 4 / 18
Apr 2026 | sprint-Gonzalo | 31 Mar → 13 Apr 2026 | 10 | 0 | 10 | 17 | 1180.8 | 944.64 | 1173.18 | 184 | 189 | 36 | 2 | 83.64% | 84.93% | 10 | 4 / 9
Apr 2026 | sprint-Hanna | 14 Apr → 27 Apr 2026 | 10 | 0 | 10 | 17 | 1166.4 | 933.12 | 1005.36 | 240 | 211 | 62 | 48 | 79.47% | 82.66% | 23 | 5 / 9
Apr 2026 TOTAL | 2 sprint(s) |  | 20 | 0 | 20 |  | 2347.2 | 1877.76 | 2178.54 | 424 | 400 | 98 | 50 | 81.55% | 83.8% | 33 | 9 / 18
Actual Delivery per Sprint
Ideal Capacity = effective working days × 8 × focus factor × active FTE. Delivered = sum of in-sprint Time Spent on the Completed bucket. Engaged = Delivered + Time Spent on the Spillover bucket (work in progress). Gap = Ideal − Delivered (positive ⇒ under-delivered, negative ⇒ over-delivered).
Sprint | Ideal Capacity (hrs) | Delivered — Completed (hrs) | Engaged — Completed + NC (hrs) | Delivery vs Ideal | Engagement vs Ideal | Gap (Ideal − Delivered) | Rating | Notes
sprint-Arthur | 1224 | 546.1 | 554.1 | 44.62% | 45.27% | 677.9 | Significantly Below | Inactive: Amol Mithari · 21 mid-sprint adds
sprint-Bertha | 1101.6 | 1043.84 | 1043.84 | 94.76% | 94.76% | 57.76 | On Target | Inactive: Amol Mithari · 1 company holiday(s) in window · 14 mid-sprint adds
Jan 2026 subtotal | 2325.6 | 1589.94 | 1597.94 | 68.37% | 68.71% | 735.66 | Significantly Below | 2 sprint(s)
sprint-Cristobal | 1101.6 | 724 | 732 | 65.72% | 66.45% | 377.6 | Significantly Below | Inactive: Amol Mithari · 1 company holiday(s) in window · 13 mid-sprint adds
sprint-Dolly | 1296 | 568 | 568 | 43.83% | 43.83% | 728 | Significantly Below | 15 mid-sprint adds
Feb 2026 subtotal | 2397.6 | 1292 | 1300 | 53.89% | 54.22% | 1105.6 | Significantly Below | 2 sprint(s)
sprint-Edouard | 1101.6 | 1508 | 1556 | 136.9% | 141.2% | -406.4 | On Target | Inactive: Rachit Mishra · 1 company holiday(s) in window · 18 mid-sprint adds
sprint-Fay | 1101.6 | 955 | 979 | 86.69% | 88.87% | 146.6 | On Target | Inactive: Rachit Mishra · 1 company holiday(s) in window · 27 mid-sprint adds
Mar 2026 subtotal | 2203.2 | 2463 | 2535 | 111.8% | 115.1% | -259.8 | On Target | 2 sprint(s)
sprint-Gonzalo | 1224 | 1173.18 | 1217.18 | 95.85% | 99.44% | 50.82 | On Target | Inactive: Rachit Mishra · 10 mid-sprint adds
sprint-Hanna | 1224 | 1005.36 | 1092.86 | 82.14% | 89.29% | 218.64 | Below Target | Inactive: Rachit Mishra · 23 mid-sprint adds
Apr 2026 subtotal | 2448 | 2178.54 | 2310.04 | 88.99% | 94.36% | 269.46 | On Target | 2 sprint(s)
Total | 9374.4 | 7523.48 | 7742.98 | 80.26% | 82.6% | 1850.92 | Below Target | 8 sprint(s) across 4 month(s)

## Monthly Rollup
Monthly Rollup — capacity & delivery
Aggregated across the sprints anchored in each calendar month. Completion % values are averaged across the sprints in the month (equal-weighted, not capacity-weighted).
Month | Sprints | Working Days | Holidays | Available (h) | Net Available (h) | Completed (h) | Spillover (OE h) | Removed (OE h) | Avg Completion (tickets) | Avg Completion (planned hrs) | Mid-sprint Adds
Jan 2026 | 2 | 20 | 1 | 2160 | 1728 | 1589.94 | 1 | 299 | 90.32% | 99.93% | 35
Feb 2026 | 2 | 20 | 1 | 2203.2 | 1762.56 | 1292 | 16 | 209 | 97.66% | 98.5% | 28
Mar 2026 | 2 | 20 | 2 | 2059.2 | 1647.36 | 2463 | 158 | 130 | 89.95% | 94.17% | 45
Apr 2026 | 2 | 20 | 0 | 2347.2 | 1877.76 | 2178.54 | 400 | 50 | 81.55% | 83.8% | 33
Month-over-month delta
From → To | Δ Sprints | Δ Working Days | Δ Holidays | Δ Available (h) | Δ Net Avail (h) | Δ Completed (h) | Δ Spillover (h) | Δ Removed (h) | Δ Avg Compl. (tickets) | Δ Avg Compl. (hrs) | Δ Mid-sprint Adds
Jan 2026 → Feb 2026 | 0 | 0 | 0 | 43.2 | 34.56 | -297.94 | 15 | -90 | 7.34% | -1.44% | -7
Feb 2026 → Mar 2026 | 0 | 0 | 1 | -144 | -115.2 | 1171 | 142 | -79 | -7.72% | -4.33% | 17
Mar 2026 → Apr 2026 | 0 | 0 | -2 | 288 | 230.4 | -284.46 | 242 | -80 | -8.39% | -10.37% | -12

## Priority Trends
Priority Trends — Completed by Priority across sprints
Tickets (parents) — subtasks rolled up to their parent. Hours include parents + every subtask (matches per-person Completed total). Ticket key lists at the bottom show the actual parent keys for reference.
Anchor Month | Sprint | Window | Bucket | P0 (parents) | P1 (parents) | P2 (parents) | P3 (parents) | P4 (parents) | Total Parents
Jan 2026 | sprint-Arthur | 06 Jan → 19 Jan | Tickets (parents) | 0 | 12 | 10 | 24 | 0 | 46
Jan 2026 | sprint-Bertha | 20 Jan → 02 Feb | Tickets (parents) | 3 | 13 | 6 | 31 | 0 | 53
Feb 2026 | sprint-Cristobal | 03 Feb → 16 Feb | Tickets (parents) | 0 | 12 | 20 | 29 | 0 | 61
Feb 2026 | sprint-Dolly | 17 Feb → 02 Mar | Tickets (parents) | 1 | 1 | 4 | 27 | 0 | 33
Mar 2026 | sprint-Edouard | 03 Mar → 16 Mar | Tickets (parents) | 1 | 16 | 20 | 40 | 4 | 81
Mar 2026 | sprint-Fay | 17 Mar → 30 Mar | Tickets (parents) | 1 | 8 | 13 | 35 | 0 | 57
Apr 2026 | sprint-Gonzalo | 31 Mar → 13 Apr | Tickets (parents) | 9 | 20 | 23 | 27 | 1 | 80
Apr 2026 | sprint-Hanna | 14 Apr → 27 Apr | Tickets (parents) | 4 | 37 | 28 | 26 | 1 | 96
Hours (incl. subtasks)
Anchor Month | Sprint | Window | Bucket | P0 (hrs) | P1 (hrs) | P2 (hrs) | P3 (hrs) | P4 (hrs) | Total Hrs
Jan 2026 | sprint-Arthur | 06 Jan → 19 Jan | Hours (incl. subtasks) | 0 | 87.15 | 133.8 | 325.15 | 0 | 546.1
Jan 2026 | sprint-Bertha | 20 Jan → 02 Feb | Hours (incl. subtasks) | 26.5 | 146.02 | 91 | 780.32 | 0 | 1043.84
Feb 2026 | sprint-Cristobal | 03 Feb → 16 Feb | Hours (incl. subtasks) | 0 | 122 | 208.5 | 393.5 | 0 | 724
Feb 2026 | sprint-Dolly | 17 Feb → 02 Mar | Hours (incl. subtasks) | 8 | 24 | 51.5 | 484.5 | 0 | 568
Mar 2026 | sprint-Edouard | 03 Mar → 16 Mar | Hours (incl. subtasks) | 13 | 167 | 378.5 | 902.5 | 47 | 1508
Mar 2026 | sprint-Fay | 17 Mar → 30 Mar | Hours (incl. subtasks) | 24 | 53 | 245.5 | 632.5 | 0 | 955
Apr 2026 | sprint-Gonzalo | 31 Mar → 13 Apr | Hours (incl. subtasks) | 59 | 164.5 | 394.68 | 530 | 25 | 1173.18
Apr 2026 | sprint-Hanna | 14 Apr → 27 Apr | Hours (incl. subtasks) | 28.72 | 271.24 | 308.74 | 371.66 | 25 | 1005.36
Reference — Completed parent ticket keys (Jira)
Anchor Month | Sprint | Priority | Parent Tickets (semicolon-separated)
Jan 2026 | sprint-Arthur | P1 | FILTER-6563; FILTER-11620; FILTER-11608; FILTER-11478; FILTER-10247; FILTER-5170; FILTER-8475; FILTER-11071; FILTER-1621; FILTER-3211; FILTER-11407; FILTER-10237
Jan 2026 | sprint-Arthur | P2 | FILTER-11646; FILTER-11626; FILTER-11293; FILTER-9255; FILTER-11449; FILTER-7172; FILTER-10738; FILTER-10740; FILTER-11340; FILTER-10116
Jan 2026 | sprint-Arthur | P3 | FILTER-11725; FILTER-11701; FILTER-11619; FILTER-11615; FILTER-11614; FILTER-11621; FILTER-11604; FILTER-11605; FILTER-11589; FILTER-11588; FILTER-11563; FILTER-9128; FILTER-9069; FILTER-11458; FILTER-11347; FILTER-10741; FILTER-11013; FILTER-8088; FDSE-143; FDSE-121; FDSE-115; FDSE-110; FDSE-108; FDSE-103
Jan 2026 | sprint-Bertha | P0 | FILTER-11783; FILTER-11707; FILTER-11678
Jan 2026 | sprint-Bertha | P1 | FILTER-11325; FILTER-11685; FILTER-11690; FILTER-11689; FILTER-11680; FILTER-11644; FILTER-7871; FILTER-11557; FILTER-11478; FILTER-11047; FILTER-10842; FILTER-10237; FILTER-8535
Jan 2026 | sprint-Bertha | P2 | FILTER-11471; FILTER-11592; FILTER-11590; FILTER-11312; FILTER-10743; FILTER-10491
Jan 2026 | sprint-Bertha | P3 | FILTER-11787; FILTER-11822; FILTER-11743; FILTER-11770; FILTER-11758; FILTER-11753; FILTER-11747; FILTER-11727; FILTER-11714; FILTER-11716; FILTER-11698; FILTER-11696; FILTER-11695; FILTER-11638; FILTER-10624; FILTER-11584; FILTER-10069; FILTER-11465; FILTER-10745; FILTER-10744; FILTER-11098; FILTER-11087; FILTER-11074; FILTER-10878; FILTER-10871; FILTER-10835; FDSE-148; FDSE-147; FDSE-141; FDSE-140; FDSE-137
Feb 2026 | sprint-Cristobal | P1 | FILTER-10034; FILTER-12016; FILTER-11998; FILTER-11962; FILTER-11958; FILTER-11942; FILTER-11926; FILTER-11910; FILTER-11826; FILTER-9605; FILTER-11443; FILTER-10392
Feb 2026 | sprint-Cristobal | P2 | FILTER-11709; FILTER-11965; FILTER-11921; FILTER-11909; FILTER-11789; FILTER-11825; FILTER-11768; FILTER-10346; FILTER-11711; FILTER-11712; FILTER-11571; FILTER-10375; FILTER-9275; FILTER-10760; FILTER-4843; FILTER-7127; FILTER-9846; FILTER-9912; FILTER-10714; FILTER-10713
Feb 2026 | sprint-Cristobal | P3 | FILTER-12049; FILTER-11988; FILTER-11987; FILTER-11813; FILTER-11740; FILTER-11922; FILTER-10521; FILTER-11919; FILTER-11577; FILTER-11899; FILTER-11898; FILTER-10476; FILTER-11649; FILTER-11715; FILTER-11717; FILTER-10900; FILTER-10925; FILTER-10643; FILTER-11581; FILTER-10630; FILTER-4362; FILTER-7286; FILTER-10489; FILTER-11114; FILTER-9908; FDSE-142; FDSE-126; FDSE-123; FDSE-112
Feb 2026 | sprint-Dolly | P0 | FILTER-12065
Feb 2026 | sprint-Dolly | P1 | FILTER-12016
Feb 2026 | sprint-Dolly | P2 | FILTER-12259; FILTER-6994; FILTER-11982; FILTER-10227
Feb 2026 | sprint-Dolly | P3 | PTGM-665; FILTER-12375; FILTER-12321; FILTER-12318; FILTER-12313; FILTER-12309; FILTER-12303; FILTER-12302; FILTER-12250; FILTER-12146; FILTER-12135; FILTER-12131; FILTER-12130; FILTER-12129; FILTER-12111; FILTER-11819; FILTER-12069; FILTER-12072; FILTER-12070; FILTER-12051; FILTER-12050; FILTER-12043; FILTER-11979; FILTER-11713; FILTER-6620; FDSE-162; FDSE-161
Mar 2026 | sprint-Edouard | P0 | FILTER-12389
Mar 2026 | sprint-Edouard | P1 | FILTER-12393; FILTER-10034; FILTER-12369; FILTER-11913; FILTER-12284; FILTER-12278; FILTER-12272; FILTER-12269; FILTER-12228; FILTER-12079; FILTER-12093; FILTER-12153; FILTER-12136; FILTER-12055; FILTER-12012; FILTER-11985
Mar 2026 | sprint-Edouard | P2 | PTGM-666; FILTER-12200; FILTER-12199; FILTER-11637; FILTER-4949; FILTER-12300; FILTER-11974; FILTER-12265; FILTER-12259; FILTER-12045; FILTER-11893; FILTER-11688; FILTER-11731; FILTER-11732; FILTER-11734; FILTER-11789; FILTER-11033; FILTER-11687; FILTER-10558; FILTER-10631
Mar 2026 | sprint-Edouard | P3 | FILTER-11631; FILTER-11827; FILTER-12532; FILTER-12311; FILTER-12307; FILTER-12305; FILTER-12293; FILTER-12499; FILTER-8230; FILTER-12486; FILTER-12402; FILTER-12017; FILTER-12375; FILTER-12372; FILTER-12365; FILTER-5679; FILTER-5401; FILTER-12332; FILTER-12333; FILTER-12334; FILTER-11776; FILTER-12292; FILTER-12291; FILTER-12003; FILTER-12048; FILTER-12143; FILTER-12132; FILTER-12117; FILTER-12100; FILTER-12086; FILTER-11812; FILTER-11742; FILTER-12071; FILTER-10728; FILTER-11532; FILTER-11895; FILTER-10347; FILTER-11767; FILTER-11482; FILTER-10458
Mar 2026 | sprint-Edouard | P4 | FILTER-11778; FILTER-11782; FILTER-11802; FILTER-11806
Mar 2026 | sprint-Fay | P0 | FILTER-12573
Mar 2026 | sprint-Fay | P1 | FILTER-12644; FILTER-12572; FILTER-12366; FILTER-12278; FILTER-12272; FILTER-12247; FILTER-12228; FILTER-12093
Mar 2026 | sprint-Fay | P2 | PTGM-666; FILTER-12606; FILTER-12602; FILTER-12481; FILTER-12455; FILTER-12342; FILTER-12300; FILTER-11974; FILTER-12265; FILTER-12004; FILTER-11687; FILTER-11539; FILTER-8474
Mar 2026 | sprint-Fay | P3 | PTGM-684; FILTER-11631; FILTER-13024; FILTER-12972; FILTER-12971; FILTER-12970; FILTER-12796; FILTER-12697; FILTER-12693; FILTER-12681; FILTER-12677; FILTER-12472; FILTER-12543; FILTER-12311; FILTER-12307; FILTER-12305; FILTER-12293; FILTER-12474; FILTER-12467; FILTER-12435; FILTER-12431; FILTER-5679; FILTER-5401; FILTER-12332; FILTER-12334; FILTER-12304; FILTER-11776; FILTER-12003; FILTER-12139; FILTER-12100; FILTER-12071; FILTER-12018; FILTER-11976; FILTER-11895; FILTER-10777
Apr 2026 | sprint-Gonzalo | P0 | FILTER-13470; FILTER-13434; FILTER-13286; FILTER-13423; FILTER-13419; FILTER-13360; FILTER-13099; FILTER-13009; FILTER-12657
Apr 2026 | sprint-Gonzalo | P1 | FILTER-13450; FILTER-13381; FILTER-13373; FILTER-13326; FILTER-13129; FILTER-13105; FILTER-12912; FILTER-12868; FILTER-12864; FILTER-12788; FILTER-12780; FILTER-12685; FILTER-12563; FILTER-12476; FILTER-12396; FILTER-12284; FILTER-12272; FILTER-12228; FILTER-12119; FILTER-12093
Apr 2026 | sprint-Gonzalo | P2 | PTGM-666; FILTER-13502; FILTER-13494; FILTER-13415; FILTER-13339; FILTER-13090; FILTER-12200; FILTER-13039; FILTER-8230; FILTER-12973; FILTER-12900; FILTER-12896; FILTER-12892; FILTER-12820; FILTER-12199; FILTER-11637; FILTER-12275; FILTER-11974; FILTER-12265; FILTER-11688; FILTER-11033; FILTER-11687; FILTER-11181
Apr 2026 | sprint-Gonzalo | P3 | PTGM-687; PTGM-686; FILTER-13785; FILTER-13782; FILTER-13318; FILTER-13080; FILTER-11631; FILTER-13031; FILTER-13023; FILTER-13022; FILTER-8230; FILTER-12848; FILTER-12472; FILTER-12311; FILTER-12307; FILTER-12305; FILTER-12293; FILTER-12474; FILTER-12467; FILTER-12447; FILTER-12405; FILTER-12343; FILTER-12333; FILTER-11776; FILTER-12241; FILTER-12156; FILTER-11895
Apr 2026 | sprint-Gonzalo | P4 | FILTER-12323
Apr 2026 | sprint-Hanna | P0 | FILTER-13743; FILTER-13739; FILTER-13542; FILTER-12997
Apr 2026 | sprint-Hanna | P1 | FILTER-13526; FILTER-13759; FILTER-13562; FILTER-13645; FILTER-13635; FILTER-13601; FILTER-13556; FILTER-13550; FILTER-13507; FILTER-13503; FILTER-13490; FILTER-13482; FILTER-13442; FILTER-13399; FILTER-13352; FILTER-13344; FILTER-13335; FILTER-13310; FILTER-13298; FILTER-13105; FILTER-12936; FILTER-12932; FILTER-12908; FILTER-12888; FILTER-12868; FILTER-12864; FILTER-12792; FILTER-12768; FILTER-12393; FILTER-12476; FILTER-12512; FILTER-12384; FILTER-7666; FILTER-12228; FILTER-12119; FILTER-12010; FILTER-11654
Apr 2026 | sprint-Hanna | P2 | FILTER-13801; FILTER-13587; FILTER-13730; FILTER-13620; FILTER-13621; FILTER-13581; FILTER-13518; FILTER-12904; FILTER-13486; FILTER-13462; FILTER-13377; FILTER-13288; FILTER-13095; FILTER-12200; FILTER-13048; FILTER-12900; FILTER-12896; FILTER-12892; FILTER-12856; FILTER-12820; FILTER-12716; FILTER-12199; FILTER-12455; FILTER-11688; FILTER-11687; FILTER-11181; FILTER-10558; FDSE-173
Apr 2026 | sprint-Hanna | P3 | PTGM-687; PTGM-686; FILTER-13785; FILTER-13782; FILTER-13715; FILTER-13711; FILTER-10462; FILTER-13458; FILTER-13454; FILTER-11631; FILTER-13031; FILTER-12884; FILTER-12872; FILTER-12848; FILTER-12796; FILTER-12776; FILTER-12772; FILTER-12702; FILTER-12447; FILTER-11776; FILTER-12244; FILTER-12241; FILTER-12048; FILTER-12143; FILTER-11532; FDSE-156
Apr 2026 | sprint-Hanna | P4 | FILTER-12323

## P1 & Mid-Sprint
P1 Escalations & Mid-sprint additions — sprint snapshot
Anchor Month | Sprint | Window | P1 Escalations (total) | P1 Escalations (open) | Mid-sprint Adds (core) | Spillover Tickets | Removed Tickets
Jan 2026 | sprint-Arthur | 06 Jan → 19 Jan | 9 | 0 | 21 | 13 | 13
Jan 2026 | sprint-Bertha | 20 Jan → 02 Feb | 13 | 1 | 14 | 12 | 12
Feb 2026 | sprint-Cristobal | 03 Feb → 16 Feb | 6 | 1 | 13 | 1 | 5
Feb 2026 | sprint-Dolly | 17 Feb → 02 Mar | 5 | 1 | 15 | 2 | 7
Mar 2026 | sprint-Edouard | 03 Mar → 16 Mar | 11 | 2 | 18 | 28 | 9
Mar 2026 | sprint-Fay | 17 Mar → 30 Mar | 7 | 2 | 27 | 11 | 8
Apr 2026 | sprint-Gonzalo | 31 Mar → 13 Apr | 9 | 4 | 10 | 36 | 6
Apr 2026 | sprint-Hanna | 14 Apr → 27 Apr | 9 | 5 | 23 | 62 | 11
Reference — Jira ticket keys per metric
Anchor Month | Sprint | Category | Tickets (semicolon-separated)
Jan 2026 | sprint-Arthur | P1 Escalation — total | FILTER-10237; FILTER-10392; FILTER-11047; FILTER-11365; FILTER-11443; FILTER-11557; FILTER-11680; FILTER-6563; FILTER-7871
Jan 2026 | sprint-Arthur | Mid-sprint additions (core) | FDSE-123; FDSE-126; FDSE-137; FDSE-140; FDSE-143; FILTER-11293; FILTER-11588; FILTER-11589; FILTER-11592; FILTER-11604; FILTER-11605; FILTER-11608; FILTER-11614; FILTER-11615; FILTER-11619; FILTER-11620; FILTER-11621; FILTER-11646; FILTER-11701; FILTER-11725; FILTER-7871
Jan 2026 | sprint-Arthur | Spillover (Not Completed) | FILTER-10635; FILTER-11063; FILTER-11064; FILTER-11301; FILTER-11303; FILTER-11310; FILTER-11311; FILTER-11327; FILTER-11372; FILTER-11404; FILTER-11405; FILTER-11406; FILTER-11427
Jan 2026 | sprint-Arthur | Removed | FDSE-112; FDSE-123; FDSE-126; FDSE-137; FDSE-138; FDSE-140; FDSE-142; FDSE-148; FILTER-10743; FILTER-10900; FILTER-11581; FILTER-11592; FILTER-7871
Jan 2026 | sprint-Bertha | P1 Escalation — open | FILTER-11610
Jan 2026 | sprint-Bertha | P1 Escalation — total | FILTER-10034; FILTER-10237; FILTER-10392; FILTER-11047; FILTER-11443; FILTER-11557; FILTER-11610; FILTER-11644; FILTER-11654; FILTER-11680; FILTER-11777; FILTER-7871; FILTER-8535
Jan 2026 | sprint-Bertha | Mid-sprint additions (core) | FDSE-141; FDSE-145; FDSE-147; FILTER-11590; FILTER-11695; FILTER-11696; FILTER-11697; FILTER-11698; FILTER-11743; FILTER-11747; FILTER-11770; FILTER-11787; FILTER-7871; FILTER-8535
Jan 2026 | sprint-Bertha | Spillover (Not Completed) | FILTER-11063; FILTER-11064; FILTER-11301; FILTER-11303; FILTER-11310; FILTER-11311; FILTER-11327; FILTER-11372; FILTER-11404; FILTER-11405; FILTER-11406; FILTER-11427
Jan 2026 | sprint-Bertha | Removed | FDSE-112; FDSE-123; FDSE-126; FDSE-142; FDSE-145; FILTER-10900; FILTER-11581; FILTER-11697; FILTER-11711; FILTER-11713; FILTER-9275; FILTER-9299
Feb 2026 | sprint-Cristobal | P1 Escalation — open | FILTER-11610
Feb 2026 | sprint-Cristobal | P1 Escalation — total | FILTER-10034; FILTER-10392; FILTER-11443; FILTER-11610; FILTER-11654; FILTER-11985
Feb 2026 | sprint-Cristobal | Mid-sprint additions (core) | FILTER-10521; FILTER-10604; FILTER-11740; FILTER-11898; FILTER-11899; FILTER-11909; FILTER-11919; FILTER-11922; FILTER-11962; FILTER-11987; FILTER-11988; FILTER-12016; FILTER-12049
Feb 2026 | sprint-Cristobal | Spillover (Not Completed) | FILTER-10635
Feb 2026 | sprint-Cristobal | Removed | FILTER-10604; FILTER-11697; FILTER-11713; FILTER-6852; FILTER-9853
Feb 2026 | sprint-Dolly | P1 Escalation — open | FILTER-11610
Feb 2026 | sprint-Dolly | P1 Escalation — total | FILTER-11610; FILTER-11964; FILTER-11985; FILTER-12010; FILTER-12012
Feb 2026 | sprint-Dolly | Mid-sprint additions (core) | FDSE-155; FDSE-161; FDSE-164; FILTER-12016; FILTER-12070; FILTER-12129; FILTER-12130; FILTER-12131; FILTER-12135; FILTER-12146; FILTER-12250; FILTER-12302; FILTER-12303; FILTER-12309; FILTER-12318
Feb 2026 | sprint-Dolly | Spillover (Not Completed) | FILTER-12052; FILTER-12240
Feb 2026 | sprint-Dolly | Removed | FDSE-155; FDSE-164; FILTER-10604; FILTER-11697; FILTER-11974; FILTER-12010; FILTER-9853
Mar 2026 | sprint-Edouard | P1 Escalation — open | FILTER-11610; FILTER-12119
Mar 2026 | sprint-Edouard | P1 Escalation — total | FILTER-10034; FILTER-11610; FILTER-11913; FILTER-11985; FILTER-12010; FILTER-12012; FILTER-12093; FILTER-12119; FILTER-12247; FILTER-12369; FILTER-7666
Mar 2026 | sprint-Edouard | Mid-sprint additions (core) | FILTER-12079; FILTER-12150; FILTER-12153; FILTER-12200; FILTER-12293; FILTER-12304; FILTER-12305; FILTER-12311; FILTER-12342; FILTER-12365; FILTER-12372; FILTER-12375; FILTER-12389; FILTER-12402; FILTER-12486; FILTER-12490; FILTER-12499; FILTER-12532
Mar 2026 | sprint-Edouard | Spillover (Not Completed) | FILTER-11147; FILTER-11354; FILTER-11483; FILTER-11485; FILTER-11499; FILTER-11843; FILTER-11844; FILTER-11872; FILTER-11873; FILTER-11880; FILTER-11881; FILTER-11882; FILTER-12153; FILTER-12155; FILTER-12197; FILTER-12198; FILTER-12217; FILTER-12218; FILTER-12223; FILTER-12224; FILTER-12226; FILTER-12227; FILTER-12232; FILTER-12233; FILTER-12282; FILTER-12283; FILTER-12395; PTGM-663
Mar 2026 | sprint-Edouard | Removed | FDSE-155; FDSE-164; FILTER-10604; FILTER-11697; FILTER-12010; FILTER-12150; FILTER-12304; FILTER-12342; FILTER-9853
Mar 2026 | sprint-Fay | P1 Escalation — open | FILTER-11610; FILTER-12476
Mar 2026 | sprint-Fay | P1 Escalation — total | FILTER-11610; FILTER-12010; FILTER-12093; FILTER-12247; FILTER-12476; FILTER-12644; FILTER-7666
Mar 2026 | sprint-Fay | Mid-sprint additions (core) | FILTER-10777; FILTER-12010; FILTER-12150; FILTER-12153; FILTER-12293; FILTER-12305; FILTER-12311; FILTER-12332; FILTER-12333; FILTER-12334; FILTER-12342; FILTER-12400; FILTER-12467; FILTER-12472; FILTER-12473; FILTER-12474; FILTER-12543; FILTER-12677; FILTER-12681; FILTER-12693; FILTER-12697; FILTER-12796; FILTER-12970; FILTER-12971; FILTER-12972; FILTER-13024; FILTER-9853
Mar 2026 | sprint-Fay | Spillover (Not Completed) | FILTER-11483; FILTER-11485; FILTER-11843; FILTER-11844; FILTER-12420; FILTER-12423; FILTER-12428; FILTER-12429; FILTER-12473; FILTER-7955; PTGM-663
Mar 2026 | sprint-Fay | Removed | FILTER-10604; FILTER-11697; FILTER-12010; FILTER-12150; FILTER-12153; FILTER-12333; FILTER-12400; FILTER-9853
Apr 2026 | sprint-Gonzalo | P1 Escalation — open | FILTER-11610; FILTER-12119; FILTER-12476; FILTER-12619
Apr 2026 | sprint-Gonzalo | P1 Escalation — total | FILTER-11610; FILTER-11654; FILTER-12010; FILTER-12093; FILTER-12119; FILTER-12476; FILTER-12619; FILTER-13105; FILTER-13129
Apr 2026 | sprint-Gonzalo | Mid-sprint additions (core) | FILTER-11974; FILTER-12150; FILTER-13022; FILTER-13023; FILTER-13047; FILTER-13080; FILTER-13090; FILTER-13339; FILTER-13360; FILTER-13502
Apr 2026 | sprint-Gonzalo | Spillover (Not Completed) | FDSE-155; FDSE-163; FDSE-164; FILTER-10604; FILTER-11697; FILTER-11843; FILTER-11844; FILTER-11872; FILTER-11873; FILTER-12104; FILTER-12105; FILTER-12178; FILTER-12179; FILTER-12345; FILTER-12449; FILTER-12473; FILTER-12492; FILTER-12493; FILTER-12494; FILTER-12526; FILTER-12541; FILTER-12542; FILTER-12620; FILTER-12621; FILTER-12622; FILTER-12823; FILTER-12982; FILTER-12984; FILTER-13040; FILTER-13047; FILTER-13319; FILTER-13320; FILTER-13784; FILTER-13787; FILTER-13826; PTGM-663
Apr 2026 | sprint-Gonzalo | Removed | FILTER-10780; FILTER-12010; FILTER-12150; FILTER-12400; FILTER-12796; FILTER-7955
Apr 2026 | sprint-Hanna | P1 Escalation — open | FILTER-10053; FILTER-12119; FILTER-12476; FILTER-12619; FILTER-13117
Apr 2026 | sprint-Hanna | P1 Escalation — total | FILTER-10053; FILTER-11654; FILTER-12010; FILTER-12119; FILTER-12476; FILTER-12619; FILTER-13105; FILTER-13117; FILTER-7666
Apr 2026 | sprint-Hanna | Mid-sprint additions (core) | FDSE-155; FDSE-156; FDSE-164; FDSE-173; FILTER-10604; FILTER-11697; FILTER-12010; FILTER-12200; FILTER-12244; FILTER-12473; FILTER-12796; FILTER-13047; FILTER-13080; FILTER-13553; FILTER-13554; FILTER-13610; FILTER-13620; FILTER-13621; FILTER-13743; FILTER-13801; FILTER-7955; PTGM-686; PTGM-687
Apr 2026 | sprint-Hanna | Spillover (Not Completed) | FDSE-155; FDSE-163; FDSE-164; FILTER-11483; FILTER-11485; FILTER-11843; FILTER-11844; FILTER-11872; FILTER-11873; FILTER-12178; FILTER-12179; FILTER-12282; FILTER-12283; FILTER-12395; FILTER-12428; FILTER-12429; FILTER-12449; FILTER-12514; FILTER-12515; FILTER-12516; FILTER-12517; FILTER-12518; FILTER-12519; FILTER-12520; FILTER-12521; FILTER-12522; FILTER-12523; FILTER-12524; FILTER-12525; FILTER-12541; FILTER-12542; FILTER-12620; FILTER-12621; FILTER-12622; FILTER-12823; FILTER-12906; FILTER-13098; FILTER-13118; FILTER-13119; FILTER-13120; FILTER-13337; FILTER-13338; FILTER-13479; FILTER-13480; FILTER-13481; FILTER-13553; FILTER-13554; FILTER-13643; FILTER-13644; FILTER-13658; FILTER-13660; FILTER-13663; FILTER-13665; FILTER-13713; FILTER-13714; FILTER-13717; FILTER-13718; FILTER-13784; FILTER-13787; FILTER-13826; PTGM-700; PTGM-701
Apr 2026 | sprint-Hanna | Removed | FILTER-10604; FILTER-10780; FILTER-11697; FILTER-12010; FILTER-12400; FILTER-12473; FILTER-13047; FILTER-13080; FILTER-13290; FILTER-13610; FILTER-7955