## Capacity vs Delivery
Capacity vs Delivery — FILTER · sprint-Arthur (Tue 06 Jan → Mon 19 Jan 2026)
Team Composition (per Securly-PjM-Skills.md Part 2 — Filter India roster). Inactive members for this sprint window are shaded grey with a roster note.
Name | Role | Function / Split | Allocation (FTE) | Seniority | Employment | Notes
Shashank Tiwari | Project Manager | PM / Delivery | 0 | Lead | FTE | Not counted in delivery capacity
Harsh Verma | FE | FrontEnd Architect (Angular) | 1 | Senior | FTE
Arun Thakur | FE + Ext | Angular / Extension | 1 | Medium | FTE
Harshada Kude | FE | Angular | 1 | Junior | FTE
Shailendra Singh | FE | Angular | 1 | Medium | FTE
Swaroop Chavhan | FE + Ext | Angular / Extension | 1 | Medium | FTE
Ashish Modak | BE Architect | Extension / Go / PHP | 1 | Senior | FTE
Prateek Fotedar | BE (www) | Go / PHP | 1 | Senior | FTE
Sagar Satpute | BE (www) | Go / PHP | 1 | Medium | FTE
Vaibhav Kumbhar | BE | Go / PHP | 1 | Medium | FTE
Ashish Temurnikar | BE | DNS / SPAC / Squid / Rust | 1 | Senior | FTE
Ravi Raj | BE | DNS / SPAC / Squid / Rust | 1 | Medium | FTE
Pratik Tiwari | BE + Ext | Extension / Go / Rust | 1 | Senior | FTE
Altamash Heroli | QA | Pri. Manual QA | 1 | Senior | FTE
Surabhi Choudhary | QA | Sr. Manual QA | 1 | Senior | FTE
Ayesha Kamde | QA | Manual QA | 1 | Junior | FTE
Amol Mithari | Auto QA Lead | Team Lead — Auto QA / SDET | 0 | Lead | FTE | Joined team on 20-Feb-2026 — not part of this sprint
Amit Shete | Auto QA | Pri. SDET | 1 | Senior | FTE
Rachit Mishra | Auto QA | SDET | 1 | Junior | FTE
Total FILTER allocation |  |  |  | FTE-equivalent heads available to FILTER
Capacity Parameters (yellow cells are inputs — re-run the script after edits)
Parameter | Value | Description
Sprint length (working days) | 10 | FILTER 15-day sprint Tue → Mon. sprint-Arthur = 2026-01-06 → 2026-01-19.
Company holidays in sprint | 0 | India calendar 2026 — none in window
Effective working days (sprint − company holidays) |  | Used as the per-person calendar for availability
Hours per working day (nominal) | 8 | Standard working day
Focus factor (productive fraction) | 0.9 | 90% — what SLT expects (sprint-analysis default)
Misc buffer (meetings, scrums, code review, …) | 20% | 20% blanket reservation deducted from Available to get Net Available
Effective hours per FTE per sprint
Allocated FTE on FILTER (active this sprint) | 17 | Headcount actually working this sprint (excludes joiners/leavers outside window)
Ideal capacity for the sprint (hrs)
Issue scope (Jira projects) | FILTER, PTGM, FDSE | Tickets pulled with `project in (FILTER, PTGM, FDSE) AND sprint = …` — FDSE: 14 · FILTER: 218 · PTGM: 22
Capacity vs Actual Delivery — sprint-Arthur
Metric | Hours | % of Ideal | Rating | Notes
Actual Availability |  |  |  | Sum of per-person availability (Ideal − leaves)
Misc Buffer (20%) |  |  |  | Reserved for meetings, scrums, code reviews
Net Available (Available − Misc Buffer) |  |  |  | Realistic delivery capacity — used as the denominator for Completed %
Completed |  |  |  | Sum of in-sprint timeSpent (Completed bucket)
Not Completed (Spillover) |  |  |  | Original estimate for spillover (carried into next sprint)
Removed |  |  |  | Original estimate for issues removed mid-sprint
Completed by Priority
Tickets (parents) = unique parent items (Story / Task / Defect / Escape Defect) — subtasks roll up to their parent so 1 parent + 3 subtasks = 1 ticket. Tickets (incl. subtasks) = raw record count incl. every Dev / QA / Automation / Review / Test Case Creation / Debug subtask. Hours = sum across parents and subtasks; matches the core-team Completed hours on the Per-person Delivery sheet.
Priority | Tickets (parents) | Tickets (incl. subtasks) | Hours (incl. subtasks) | % of Completed Hrs | % of Tickets (parents) | Notes
P1 | 12 | 23 | 87.15 |  |  | P1 — high priority (see P1 Escalation tab for escalations)
P2 | 10 | 30 | 133.8 |  |  | Major
P3 | 24 | 45 | 325.15 |  |  | Standard
TOTAL | 46 | 98 | 546.1 | 100% | 100% | Sum of Completed bucket (core roster)
Sprint Completion (spillover = Not Completed)
Metric | Tickets | Planned Hrs (OE) | % by Tickets | % by Hrs | Notes
Completed (closed in sprint) | 98 | 587.08 |  |  | In-sprint deliverables
Spillover (not completed → carry-over) | 13 | 0.5 |  |  | Original estimate carried to next sprint
Removed (mid-sprint scope cut) | 13 | 163 | — | — | Excluded from completion ratio (out of scope)
Mid-sprint additions (core) | 21 |  | — | — | Late-arriving work (Jira issueKeysAddedDuringSprint)
Sprint completion rate (tickets) | 88.29% | On Target | Completed ÷ (Completed + Spillover)
Sprint completion rate (planned hrs) | 99.91% | On Target | Σ OE Completed ÷ Σ OE (Completed + Spillover)
Planned completion rate (tickets, excludes mid-sprint adds) | 86.46% | On Target | Originally-committed tickets only
Planned completion rate (planned hrs, excludes mid-sprint adds) | 99.9% | On Target | Originally-committed planned hours only
P1 Escalation snapshot
9 ticket(s) in sprint-Arthur match 'P1 Escalation' in the title — 9 closed, 0 still open. See the 'P1 Escalation' tab.
Mid-sprint additions snapshot
21 ticket(s) were added to sprint-Arthur after it started (issueKeysAddedDuringSprint) — Completed 15, Spillover 0, Removed 6. Highlighted in amber on every detail sheet (Added Mid-Sprint = YES).
Assumptions & caveats
• Sprint window from Jira (/rest/agile/1.0/sprint/4666): 2026-01-06 → 2026-01-19 (10 Mon–Fri working days). Refresh with fetch_filter_sprint_meta.py + fetch_filter_sprint_issues.py.
• Issues pulled from FILTER + PTGM + FDSE (project-scope expanded for the India scrum team's split across the three products).
• Date-aware roster: Amol Mithari joined 20-Feb-2026; Rachit Mishra's last day was 20-Feb-2026. Inactive members for this sprint window are shaded grey in the Team Composition table and excluded from per-person availability + delivery.
• Available (hrs) = (effective working days − leave days) × 8 × focus factor, where effective working days = sprint working days − company holidays falling inside the sprint − days outside the person's employment window. Per-person Delivery shows leave days in Column G to explain the delta from a full sprint.
• Net Available = Available − 20% Misc Buffer for meetings, scrums, code review, etc. Completed/Not Completed/Removed % of capacity use Net Available as the denominator.
• Time Spent on Completed sheet uses the in-sprint hybrid worklog rule (sprint-analysis.md): single-sprint = timespent; multi-sprint = SUM of worklogs whose started ∈ [sprintStart, sprintEnd].
• Not Completed and Removed totals use Original Estimate.
• Removed list comes from the Sprint Report puntedIssues (greenhopper API).
• Core roster only: assignees outside Securly-PjM-Skills.md Part 2 are dropped from per-person + detail sheets.
• P1 Escalation tab is filtered to Issue Type = Escape Defect AND Priority = P1 AND title contains 'P1 Escalation'.
• Completed by Priority — Tickets (parents) rolls subtasks up to their parent (each work item counted once at its parent priority); Tickets (incl. subtasks) shows the raw record count for comparison. The Hours column sums every record (parent + subtasks) and matches the core-team Completed total.
• Spillover = Not Completed bucket (tickets carried into the next sprint).
• Sprint completion rate uses Completed ÷ (Completed + Spillover); Removed tickets are excluded (treated as scope cut). 'Planned' rate also excludes mid-sprint additions.
• All detail sheets (Completed, Not Completed, Removed) highlight tickets added after sprint start (Jira sprint-report issueKeysAddedDuringSprint) in amber, with an 'Added Mid-Sprint = YES' tag column.
• Ratings: ≥85% On Target (green), 70–85% Below Target (amber), <70% Significantly Below (red).

## Per-person Delivery
Assignee | Completed (hrs) | Not Completed (hrs) | Removed (hrs) | Efficiency | Available (hrs) | Leave Days (sprint) | Misc Buffer 20% (hrs) | Net Available (hrs)
Harsh Verma | 61 | 0 | 8 |  | 72 | 0
Arun Thakur | 5 | 0.5 | 0 |  | 64.8 | 1
Harshada Kude | 52 | 0 | 32 |  | 72 | 0
Shailendra Singh | 50 | 0 | 60 |  | 64.8 | 1
Swaroop Chavhan | 0 | 0 | 52 |  | 64.8 | 1
Ashish Modak | 6 | 0 | 0 |  | 43.2 | 4
Prateek Fotedar | 45 | 0 | 0 |  | 72 | 0
Sagar Satpute | 18 | 0 | 0 |  | 72 | 0
Vaibhav Kumbhar | 39 | 0 | 0 |  | 72 | 0
Ashish Temurnikar | 41 | 0 | 0 |  | 72 | 0
Ravi Raj | 90 | 0 | 1 |  | 72 | 0
Pratik Tiwari | 28 | 0 | 10 |  | 72 | 0
Altamash Heroli | 23.5 | 0 | 0 |  | 72 | 0
Surabhi Choudhary | 27.5 | 0 | 0 |  | 72 | 0
Ayesha Kamde | 25.1 | 0 | 0 |  | 64.8 | 1
Amit Shete | 18.5 | 0 | 0 |  | 64.8 | 1
Rachit Mishra | 16.5 | 0 | 0 |  | 64.8 | 1
TOTAL

## Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Debug | FILTER-11621 | Debug and analyse latest config.json for uk.pinterest.com |  |  | Arun Thakur | Closed | Fixed | P3 | 2026-01-12 | 2026-01-12 | 2026-02-01 | sprint-Arthur | 5 | 6 | FILTER | unplanned-sprint |  | YES
Task | FILTER-11608 | Squid coredump issue on Ohio |  |  | Ashish Temurnikar | RELEASED TO PROD |  | P1 | 2026-01-08 |  | 2026-02-09 | sprint-Arthur | 6 | 1 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-11646 | Initial debugging for FILTER-11644 |  |  | Ashish Temurnikar | Closed |  | P2 | 2026-01-15 |  | 2026-01-19 | sprint-Arthur | 10 | 8 | FILTER | unplanned-sprint |  | YES
Task | FDSE-143 | Improved packaging system to accommodate SDK and Dev kit for re-usability and easy consumption |  |  | Harsh Verma | Closed | Done | P3 | 2026-01-05 | 2026-01-07 | 2026-02-01 | sprint-Arthur | 16 | 24 | FDSE | product-filter |  | YES
Task | FILTER-11588 | Helping classroom team for PR review and Technical discussions |  |  | Harsh Verma | Closed |  | P3 | 2026-01-05 |  | 2026-02-01 | sprint-Arthur | 5 | 4 | FILTER | unplanned-sprint |  | YES
Task | FILTER-11589 | Helping Home Team for the overall architecture of Parent Portal design Revamp and and AI Chat for their dashobard requirement |  |  | Harsh Verma | Closed |  | P3 | 2026-01-05 |  | 2026-02-01 | sprint-Arthur | 24 | 24 | FILTER | unplanned-sprint |  | YES
Task | FILTER-11605 | Create a plan to improve the performance of Angular applications |  |  | Harsh Verma | Closed |  | P3 | 2026-01-08 |  | 2026-02-01 | sprint-Arthur | 16 | 24 | FILTER | unplanned-sprint |  | YES
Defect | FILTER-11604 | Issue in the custom list link API | FILTER-3618 | Epic | Prateek Fotedar | RELEASED TO PROD |  | P3 | 2026-01-08 |  | 2026-02-09 | sprint-Arthur | 6 | 0 | FILTER | Capitalized-Feature, unplanned-sprint |  | YES
Defect | FILTER-11614 | [Filter API] PUT /api/custom-list/resource returns HTTP 500 when updating resource to same value | FILTER-3618 | Epic | Prateek Fotedar | RELEASED TO PROD |  | P3 | 2026-01-10 |  | 2026-02-09 | sprint-Arthur | 2 | 2 | FILTER | Capitalized-Feature, unplanned-sprint |  | YES
Defect | FILTER-11615 | [Filter API] PUT /api/custom-list/resource returns HTTP 500 instead of 4xx when resourceId belongs to different custom list | FILTER-3618 | Epic | Prateek Fotedar | RELEASED TO PROD |  | P3 | 2026-01-10 |  | 2026-02-09 | sprint-Arthur | 1 | 1 | FILTER | Capitalized-Feature, unplanned-sprint |  | YES
Defect | FILTER-11619 | GET /api/custom-list returns HTTP 500 for invalid input parameters and malformed tokens instead of proper error codes | FILTER-3618 | Epic | Prateek Fotedar | RELEASED TO PROD |  | P3 | 2026-01-12 |  | 2026-02-09 | sprint-Arthur | 1.5 | 1.5 | FILTER | Capitalized-Feature, unplanned-sprint |  | YES
Defect | FILTER-11620 | Security Issue: Cross-Account Policy Linking Authorization Bug | FILTER-3618 | Epic | Prateek Fotedar | Closed without action |  | P1 | 2026-01-12 |  | 2026-01-21 | sprint-Arthur | 0 | 0 | FILTER | Capitalized-Feature, unplanned-sprint |  | YES
Task | FILTER-11701 | [sprox] Redis connection for wrapper & redis config separation | FILTER-8230 | Epic | Ravi Raj | Closed |  | P3 | 2026-01-19 |  | 2026-02-01 | sprint-Arthur | 8 | 0.08 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-11725 | [sprox] Function translation to sprox - Part 3 |  |  | Ravi Raj | Closed |  | P3 | 2026-01-19 |  | 2026-02-01 | sprint-Arthur | 10 | 10 | FILTER | unplanned-sprint |  | YES
Escape Defect | FILTER-11293 | Uncategorised block logic ignores domain's basegen when primary domain is not categorized and sub domain categorizarion is disabled |  |  | Vaibhav Kumbhar | Done | Fixed | P2 | 2025-12-04 | 2025-12-15 | 2026-03-09 | sprint-Arthur | 5 | 0 | FILTER | Reverified-2026, unplanned-sprint |  | YES
Task | FILTER-11013 | Pkg-35 Regression testing |  |  | Altamash Heroli | Closed without action |  | P3 | 2025-11-25 |  | 2026-01-22 | sprint-Arthur | 13.5 | 15 | FILTER | unplanned-sprint
QA | FILTER-11014 | pkg-35 Regression Testing | FILTER-11013 | Task | Altamash Heroli | Closed without action |  | P3 | 2025-11-25 |  | 2026-01-07 | sprint-Arthur | 10 | 15 | FILTER
QA | FILTER-11131 | C++ securly init connection function calling | FILTER-10740 | Task | Altamash Heroli | Closed without action |  | P3 | 2025-12-02 |  | 2025-12-08 | sprint-Arthur | 0 | 0 | FILTER
QA | FILTER-11211 | QA - [sprox] main.rs module separation part-1 | FILTER-10738 | Task | Altamash Heroli | Closed without action |  | P3 | 2025-12-03 |  | 2025-12-08 | sprint-Arthur | 0 | 0 | FILTER
QA | FILTER-11278 | QA - [sprox] Securly supporting files compilation | FILTER-10741 | Task | Altamash Heroli | Closed without action |  | P3 | 2025-12-04 |  | 2025-12-08 | sprint-Arthur | 0 | 0 | FILTER
QA | FILTER-11452 | QA task | FILTER-11449 | Task | Altamash Heroli | Closed without action |  | P2 | 2025-12-15 |  | 2026-01-18 | sprint-Arthur | 0 | 0 | FILTER
Automation | FILTER-11170 | Fix Custom Group Creation Button State and Default Date Errors | FILTER-9128 | Escape Defect | Amit Shete | Done |  | P3 | 2025-12-02 |  | 2026-01-20 | sprint-Arthur | 3.5 | 4 | FILTER
Automation | FILTER-11342 | Automated E2E Regression Test: Validate SourceIP Integrity and Logging on PHP Block | FILTER-11340 | Escape Defect | Amit Shete | Done |  | P3 | 2025-12-08 |  | 2026-01-20 | sprint-Arthur | 4.5 | 4 | FILTER
Automation | FILTER-11349 | Automated E2E Regression Test: Validate Tab Rebrokering Post-Idle on Windows/macOS | FILTER-11347 | Task | Amit Shete | Done |  | P3 | 2025-12-08 |  | 2026-01-20 | sprint-Arthur | 5 | 5 | FILTER
Automation | FILTER-11367 | Automated E2E Regression Test: Fix Custom Group Creation Requirement for Duration | FILTER-9069 | Escape Defect | Amit Shete | Closed without action |  | P3 | 2025-12-09 |  | 2026-01-15 | sprint-Arthur | 0 | 0 | FILTER
Automation | FILTER-11528 | Automated UI Regression: Validate Audit Log Sort Persistence on Search Interaction | FILTER-10247 | Defect | Amit Shete | Done |  | P3 | 2025-12-19 |  | 2026-01-20 | sprint-Arthur | 5.5 | 6 | FILTER
Escape Defect | FILTER-10237 | P1 escalation-Crextn-specific Bypass using upgraded credentials |  |  | Ashish Modak | Release in Progress | Fixed | P1 | 2025-09-26 | 2025-11-20 | 2026-02-03 | sprint-Arthur | 6 | 6 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_escalated, jira_in_progress, p1escalation, unplanned-sprint
Dev | FILTER-11276 | [sprox] Securly supporting files compilation | FILTER-10741 | Task | Ashish Temurnikar | Closed without action |  | P3 | 2025-12-04 |  | 2026-01-19 | sprint-Arthur | 12 | 12 | FILTER
Dev | FILTER-11496 | Fix Google Maps Menu Failure: Unblock googleusercontent.com/maps.google.com/1 in SmartPAC/DNS | FILTER-1621 | Bug (OLD - use Defect instead) | Ashish Temurnikar | Closed without action |  | P1 | 2025-12-19 |  | 2026-01-11 | sprint-Arthur | 6 | 6 | FILTER
Dev | FILTER-11501 | Resolve Google "Unusual Traffic" Blocks for admin.google.com on US-West Egress IPs | FILTER-9255 | Escape Defect | Ashish Temurnikar | Closed without action |  | P3 | 2025-12-19 |  | 2026-01-11 | sprint-Arthur | 7 | 6 | FILTER
Dev | FILTER-11609 | Squid coredump issue on Ohio | FILTER-11608 | Task | Ashish Temurnikar | Done |  | P1 | 2026-01-08 |  | 2026-01-22 | sprint-Arthur | 0 | 6 | FILTER
QA | FILTER-10702 | QA Testing: proxy signature to fingerprinting ruleset | FILTER-8088 | Task | Ayesha Kamde | Closed without action |  | P3 | 2025-11-07 |  | 2026-01-12 | sprint-Arthur | 0 | 4 | FILTER
QA | FILTER-11016 | pkg-35 Regression Testing | FILTER-11013 | Task | Ayesha Kamde | Closed without action |  | P3 | 2025-11-25 |  | 2026-01-07 | sprint-Arthur | 0 | 10 | FILTER
QA | FILTER-11021 | Manual QA Validation for Dual Logging (Blocked + Flagged) on all Search Engines | FILTER-10116 | Defect | Ayesha Kamde | Closed without action |  | P3 | 2025-11-25 |  | 2026-01-16 | sprint-Arthur | 0.15 | 8 | FILTER
QA | FILTER-11027 | Manual QA Validation for Flagged Icon and Status in Double Logging Scenarios | FILTER-7172 | Bug (OLD - use Defect instead) | Ayesha Kamde | Done |  | P2 | 2025-11-25 |  | 2026-01-16 | sprint-Arthur | 1 | 6 | FILTER
QA | FILTER-11171 | Manual QA Validation for Custom Group Creation UI/Date Logic | FILTER-9128 | Escape Defect | Ayesha Kamde | Done |  | P3 | 2025-12-02 |  | 2026-01-14 | sprint-Arthur | 2.5 | 1 | FILTER
QA | FILTER-11250 | Manual QA Validation for Activities UI Overflow and Column State Persistence | FILTER-6563 | Escape Defect | Ayesha Kamde | Done |  | P3 | 2025-12-03 |  | 2026-01-28 | sprint-Arthur | 3 | 0 | FILTER | OOB, QAed-during-pkg-35-2025
Test Case Creation | FILTER-11366 | Testcases creation for Filter- 7172 | FILTER-7172 | Bug (OLD - use Defect instead) | Ayesha Kamde | Done |  | P3 | 2025-12-09 |  | 2026-01-20 | sprint-Arthur | 0.15 | 0 | FILTER
QA | FILTER-11368 | Manual QA Validation for Custom Group Creation Duration Requirement | FILTER-9069 | Escape Defect | Ayesha Kamde | Done |  | P3 | 2025-12-09 |  | 2026-01-14 | sprint-Arthur | 0.15 | 1 | FILTER
QA | FILTER-11417 | QA - Fix the Math.fun Signatures | FILTER-11407 | Task | Ayesha Kamde | Done |  | P1 | 2025-12-11 |  | 2026-01-11 | sprint-Arthur | 5 | 3 | FILTER
QA | FILTER-11503 | Manual QA Validation: admin.google.com Accessibility (US-West SmartPAC) | FILTER-9255 | Escape Defect | Ayesha Kamde | Closed without action |  | P3 | 2025-12-19 |  | 2026-01-11 | sprint-Arthur | 0 | 2 | FILTER
QA | FILTER-11506 | Manual QA Validation: UK Cluster Activity Log Availability and Backfill Verification | FILTER-11071 | Task | Ayesha Kamde | Closed without action |  | P1 | 2025-12-19 |  | 2026-01-19 | sprint-Arthur | 0.15 | 6 | FILTER
QA | FILTER-11529 | Manual QA Validation: Audit Log Row Stability (RTQA4 & USwest) | FILTER-10247 | Defect | Ayesha Kamde | Done |  | P3 | 2025-12-19 |  | 2026-01-16 | sprint-Arthur | 2 | 1 | FILTER
QA | FILTER-11551 | Manual QA Validation: "Uncategorized" Block vs. Academic Subdomains | FILTER-11293 | Escape Defect | Ayesha Kamde | Done |  | P2 | 2025-12-21 |  | 2026-01-06 | sprint-Arthur | 5 | 0 | FILTER
QA | FILTER-11576 | Manual QA Validation: Broker Stability Audit & Log Monitoring | FILTER-11478 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2026-01-05 |  | 2026-01-09 | sprint-Arthur | 4 | 4 | FILTER
QA | FILTER-11820 | Post release validation | FILTER-6563 | Escape Defect | Ayesha Kamde | Closed without action |  | P3 | 2026-01-29 |  | 2026-01-29 | sprint-Arthur | 2 | 2 | FILTER
Task | FDSE-108 | Implementation of Modal as per the design | FDSE-107 | Epic | Harshada Kude | Closed | Fixed | P3 | 2025-11-20 | 2025-12-22 | 2026-02-01 | sprint-Arthur | 24 | 12 | FDSE | product-filter
Task | FDSE-110 | Implementation of Side drawer as per the design | FDSE-109 | Epic | Harshada Kude | Closed | Fixed | P3 | 2025-11-20 | 2026-01-19 | 2026-02-01 | sprint-Arthur | 28 | 24 | FDSE | product-filter
Dev | FILTER-11450 | Dev Task | FILTER-11449 | Task | Prateek Fotedar | Done |  | P2 | 2025-12-15 |  | 2026-01-16 | sprint-Arthur | 13 | 13 | FILTER
Dev | FILTER-11523 | Implement Automated Email Alerts for On-Call Status Deactivation | FILTER-5170 | Task | Prateek Fotedar | Done |  | P1 | 2025-12-19 |  | 2026-01-12 | sprint-Arthur | 7 | 7 | FILTER
Task | FILTER-11563 | case when securlyCustomListId is invalid | FILTER-3618 | Epic | Prateek Fotedar | Closed |  | P3 | 2026-01-02 |  | 2026-01-28 | sprint-Arthur | 2.5 | 0 | FILTER | Capitalized-Feature
Dev | FILTER-11570 | Dev Task | FILTER-11563 | Task | Prateek Fotedar | Done |  | P3 | 2026-01-02 |  | 2026-01-21 | sprint-Arthur | 2.5 | 2.5 | FILTER | Capitalized-Feature
Dev | FILTER-11616 | Issue in the custom list API | FILTER-11604 | Defect | Prateek Fotedar | Done |  | P3 | 2026-01-11 |  | 2026-01-21 | sprint-Arthur | 5 | 5 | FILTER | Capitalized-Feature
Dev | FILTER-11623 | Fix PUT /api/custom-list/resource HTTP 500 Error on Idempotent Updates | FILTER-11614 | Defect | Prateek Fotedar | Done |  | P3 | 2026-01-12 |  | 2026-01-21 | sprint-Arthur | 2 | 2 | FILTER | Capitalized-Feature
Dev | FILTER-11624 | Update API validation to check resourceId ownership in PUT /api/custom-list/resource | FILTER-11615 | Defect | Prateek Fotedar | Done |  | P3 | 2026-01-13 |  | 2026-01-21 | sprint-Arthur | 1 | 1 | FILTER | Capitalized-Feature
Dev | FILTER-11625 | Implement input validation for 'page' and 'limit' query parameters in GET /api/custom-list | FILTER-11619 | Defect | Prateek Fotedar | Done |  | P3 | 2026-01-13 |  | 2026-01-21 | sprint-Arthur | 1.5 | 1.5 | FILTER | Capitalized-Feature
Task | FILTER-10738 | [sprox] main.rs module separation - Part 1 | FILTER-8230 | Epic | Pratik Tiwari | Closed | Fixed | P2 | 2025-11-10 | 2026-01-11 | 2026-02-01 | sprint-Arthur | 8 | 8 | FILTER
Dev | FILTER-11353 | [sprox] main.rs module separation - Part 1 | FILTER-10738 | Task | Pratik Tiwari | Closed without action |  | P3 | 2025-12-08 |  | 2026-01-15 | sprint-Arthur | 0 | 10 | FILTER
Dev | FILTER-11415 | Fix the Math.fun Signatures | FILTER-11407 | Task | Pratik Tiwari | Done |  | P1 | 2025-12-11 |  | 2026-01-11 | sprint-Arthur | 0 | 8 | FILTER
Dev | FILTER-11627 | clever.com | FILTER-11626 | Task | Pratik Tiwari | Done |  | P2 | 2026-01-13 |  | 2026-01-15 | sprint-Arthur | 8 | 8 | FILTER
Dev | FILTER-11628 | Crextn marked S3 site as proxy | FILTER-11626 | Task | Pratik Tiwari | Closed without action |  | P2 | 2026-01-13 |  | 2026-01-16 | sprint-Arthur | 0 | 0 | FILTER
Dev | FILTER-11629 | S3 and CDN miscategorized as Malware | FILTER-11626 | Task | Pratik Tiwari | Closed without action |  | P2 | 2026-01-13 |  | 2026-01-16 | sprint-Arthur | 0 | 0 | FILTER
Task | FILTER-8088 | proxy signature to fingerprinting ruleset |  |  | Pratik Tiwari | Resolved | Fixed | P3 | 2025-04-30 | 2025-09-29 | 2026-02-02 | sprint-Arthur | 12 | 12 | FILTER
Automation | FILTER-11018 | pkg-35 Regression Testing | FILTER-11013 | Task | Rachit Mishra | Done |  | P3 | 2025-11-25 |  | 2025-12-09 | sprint-Arthur | 3.5 | 4 | FILTER
Automation | FILTER-11020 | Automated E2E Regression Test for Blocked + Flagged Activity Log Creation | FILTER-10116 | Defect | Rachit Mishra | Done |  | P3 | 2025-11-25 |  | 2026-01-20 | sprint-Arthur | 5.5 | 4.5 | FILTER
Automation | FILTER-11026 | Automated E2E Regression Test for Double Logging: Validate Flag Icon and Status | FILTER-7172 | Bug (OLD - use Defect instead) | Rachit Mishra | Done |  | P2 | 2025-11-25 |  | 2026-01-20 | sprint-Arthur | 5.5 | 5 | FILTER
Automation | FILTER-11451 | Automation Task | FILTER-11449 | Task | Rachit Mishra | Done |  | P2 | 2025-12-15 |  | 2026-01-19 | sprint-Arthur | 2 | 2 | FILTER
Task | FILTER-10740 | [sprox] C++ securly init connection function calling | FILTER-8230 | Epic | Ravi Raj | Closed |  | P2 | 2025-11-10 |  | 2026-02-01 | sprint-Arthur | 16 | 0 | FILTER | unplanned-sprint
Dev | FILTER-11352 | [sprox] C++ securly init connection function calling | FILTER-10740 | Task | Ravi Raj | Done |  | P3 | 2025-12-08 |  | 2026-01-15 | sprint-Arthur | 16 | 10 | FILTER
Task | FILTER-11458 | [sprox] Function translation to sprox - Part 2 | FILTER-8230 | Epic | Ravi Raj | Closed |  | P3 | 2025-12-17 |  | 2026-02-01 | sprint-Arthur | 16 | 8 | FILTER | unplanned-sprint
Dev | FILTER-11516 | [sprox] Function translation to sprox - Part 2 | FILTER-11458 | Task | Ravi Raj | Done |  | P3 | 2025-12-19 |  | 2026-01-19 | sprint-Arthur | 16 | 16 | FILTER
Dev | FILTER-11702 | Redis connection for wrapper & redis config separation | FILTER-11701 | Task | Ravi Raj | Done |  | P3 | 2026-01-19 |  | 2026-01-19 | sprint-Arthur | 8 | 8 | FILTER
Dev | FILTER-11491 | Fix Policy Request Email Template to Include Applied OU and Security Group Criteria | FILTER-3211 | Bug (OLD - use Defect instead) | Sagar Satpute | Done |  | P1 | 2025-12-19 |  | 2026-02-09 | sprint-Arthur | 10 | 13 | FILTER
Dev | FILTER-11512 | Fix Automatic Admin Group Creation Failure Following Premium Feature Enablement | FILTER-8475 | Defect | Sagar Satpute | Done |  | P1 | 2025-12-19 |  | 2026-01-12 | sprint-Arthur | 8 | 8 | FILTER
Dev | FILTER-11546 | Reopened -Dev Task - Custom Groups require duration to be created ¦ securly@knochsd.org | FILTER-9069 | Escape Defect | Sagar Satpute | Closed without action |  | P3 | 2025-12-21 |  | 2026-01-14 | sprint-Arthur | 0 | 5 | FILTER
Task | FDSE-115 | New changes in Checkbox as per the updated design | FDSE-54 | Epic | Shailendra Singh | Closed |  | P3 | 2025-11-20 |  | 2026-02-01 | sprint-Arthur | 8 | 16 | FDSE | product-filter
Task | FDSE-121 | Implementation of Info component | FDSE-120 | Epic | Shailendra Singh | Closed | Fixed | P3 | 2025-12-04 | 2026-01-10 | 2026-02-01 | sprint-Arthur | 24 | 16 | FDSE | product-filter
Dev | FILTER-11019 | Fix Filter/TAS Failure to Log Both Blocked and Flagged Records | FILTER-10116 | Defect | Shailendra Singh | Closed without action |  | P3 | 2025-11-25 |  | 2026-01-14 | sprint-Arthur | 0 | 4 | FILTER
Dev | FILTER-11025 | Fix Flagged Activity Status Mismatch and Missing Icon in Double Logging Cases | FILTER-7172 | Bug (OLD - use Defect instead) | Shailendra Singh | Closed without action |  | P2 | 2025-11-25 |  | 2026-01-14 | sprint-Arthur | 0 | 6 | FILTER
Dev | FILTER-11527 | Fix Audit Log Row Rearrangement when Pressing Enter in Search Field | FILTER-10247 | Defect | Shailendra Singh | Done |  | P3 | 2025-12-19 |  | 2026-01-12 | sprint-Arthur | 6 | 6 | FILTER
Dev | FILTER-11552 | Custom groups creation issue | FILTER-9128 | Escape Defect | Shailendra Singh | Done |  | P3 | 2025-12-22 |  | 2026-01-14 | sprint-Arthur | 0 | 0 | FILTER
Escape Defect | FILTER-9128 | Custom Group creation is not working |  |  | Shailendra Singh | Done | Fixed | P3 | 2025-07-10 | 2026-01-07 | 2026-03-18 | sprint-Arthur | 12 | 8 | FILTER | jira_added, jira_backlog, jira_done, jira_escalated, jira_p3, jira_qa_verified, zendesk_enterprise
QA | FILTER-11015 | pkg-35 Regression Testing | FILTER-11013 | Task | Surabhi Choudhary | Closed without action |  | P3 | 2025-11-25 |  | 2026-01-07 | sprint-Arthur | 0 | 0 | FILTER
QA | FILTER-11343 | Manual QA Validation for Invalid SourceIP Logging in PHP Broker | FILTER-11340 | Escape Defect | Surabhi Choudhary | Done |  | P3 | 2025-12-08 |  | 2026-01-09 | sprint-Arthur | 3 | 3 | FILTER
QA | FILTER-11350 | Manual QA Validation for CRXTN Tab Rebrokering Post-Idle on Windows/macOS/Linux | FILTER-11347 | Task | Surabhi Choudhary | Done |  | P3 | 2025-12-08 |  | 2026-01-09 | sprint-Arthur | 8 | 0 | FILTER
QA | FILTER-11495 | Manual QA Validation: Policy Priority Email Notifications (OU & Security Groups) | FILTER-3211 | Bug (OLD - use Defect instead) | Surabhi Choudhary | Done |  | P1 | 2025-12-19 |  | 2026-01-16 | sprint-Arthur | 5 | 4 | FILTER
QA | FILTER-11498 | Manual QA Validation: Google Maps Menu Interaction on UK Cluster | FILTER-1621 | Bug (OLD - use Defect instead) | Surabhi Choudhary | Closed without action |  | P1 | 2025-12-19 |  | 2026-01-11 | sprint-Arthur | 0.5 | 4 | FILTER
QA | FILTER-11514 | Manual QA Validation: Admin Group Creation and Toggle Logic for Premium Accounts | FILTER-8475 | Defect | Surabhi Choudhary | Done |  | P1 | 2025-12-19 |  | 2026-01-14 | sprint-Arthur | 5 | 5 | FILTER
QA | FILTER-11611 | Verify SPAC/DNS working with Automation suite. Regression testing. | FILTER-11608 | Task | Surabhi Choudhary | Done |  | P1 | 2026-01-08 |  | 2026-01-09 | sprint-Arthur | 6 | 6 | FILTER
Task | FDSE-103 | Implement Datepicker Single Date and Date Range only | FDSE-102 | Epic | Swaroop Chavhan | Closed |  | P3 | 2025-11-20 |  | 2026-02-01 | sprint-Arthur | 0 | 32 | FDSE | product-filter
Dev | FILTER-11248 | Fix Activities UI Overflow on Ultrawide Monitors & Persist Column Resizing | FILTER-6563 | Escape Defect | Swaroop Chavhan | Done |  | P3 | 2025-12-03 |  | 2026-01-11 | sprint-Arthur | 0 | 1 | FILTER
Dev | FILTER-11504 | Investigate and Restore UK Cluster Activity Logging (Data Stalled Since 30/11/2025) | FILTER-11071 | Task | Swaroop Chavhan | Closed without action |  | P1 | 2025-12-19 |  | 2026-01-12 | sprint-Arthur | 0 | 2 | FILTER
Dev | FILTER-11299 | PHP: Uncategorised block logic ignores domain's basegen when primary domain is not categorized and sub domain categorizarion is disabled | FILTER-11293 | Escape Defect | Vaibhav Kumbhar | Done |  | P2 | 2025-12-04 |  | 2025-12-21 | sprint-Arthur | 8 | 8 | FILTER
Dev | FILTER-11300 | GO: Uncategorised block logic ignores domain's basegen when primary domain is not categorized and sub domain categorizarion is disabled | FILTER-11293 | Escape Defect | Vaibhav Kumbhar | Done |  | P2 | 2025-12-04 |  | 2025-12-21 | sprint-Arthur | 6 | 8 | FILTER
Dev | FILTER-11341 | Fix PHP Broker Logging Invalid SourceIP Causing OS Ingestion Failure | FILTER-11340 | Escape Defect | Vaibhav Kumbhar | Done |  | P3 | 2025-12-08 |  | 2026-02-09 | sprint-Arthur | 6 | 0 | FILTER
Task | FILTER-11347 | Rebroker open tabs for Windows |  |  | Vaibhav Kumbhar | RELEASED TO PROD | Done | P3 | 2025-11-13 | 2025-12-19 | 2026-02-09 | sprint-Arthur | 0 | 10 | FILTER | jira_added, jira_backlog, jira_escalated, jira_in_progress, jira_resolved
Dev | FILTER-11348 | Fix CRXTN crextn_reload_tab_fids Failure to Rebroker Open Tabs on Windows OS | FILTER-11347 | Task | Vaibhav Kumbhar | Done |  | P3 | 2025-12-08 |  | 2025-12-19 | sprint-Arthur | 10 | 12 | FILTER
Dev | FILTER-11453 | Write script to fetch top 2000 uncategorized domains to categorize them | FILTER-11293 | Escape Defect | Vaibhav Kumbhar | Closed without action |  | P2 | 2025-12-16 |  | 2025-12-21 | sprint-Arthur | 4 | 0 | FILTER

## Not Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Code Review | FILTER-11311 | Review PR for the REL : REL-10348 |  |  | Arun Thakur | Backlog |  | P3 | 2025-12-04 |  | 2026-02-03 | sprint-Arthur | 0 | 0.25 | FILTER
Code Review | FILTER-11327 | Review PR for the REL : REL-10355 |  |  | Arun Thakur | Backlog |  | P3 | 2025-12-05 |  | 2026-02-03 | sprint-Arthur | 0 | 0.25 | FILTER
Code Review | FILTER-11406 | Review PR for the REL : REL-10361 |  |  | Arun Thakur | Backlog |  | P3 | 2025-12-10 |  | 2026-02-03 | sprint-Arthur | 0 | 0 | FILTER
Epic | FILTER-10635 | Force PR to get blocked if PR checks are failing |  |  | Harsh Verma | Development In Progress |  | P2 | 2025-11-06 |  | 2026-03-03 | sprint-Arthur | 8 | 0 | FILTER | unplanned-sprint
Code Review | FILTER-11063 | Review PR for the REL : REL-10254 |  |  | Harsh Verma | Backlog |  | P3 | 2025-11-28 |  | 2026-02-03 | sprint-Arthur | 0 | 0 | FILTER
Code Review | FILTER-11427 | Review PR for the REL : REL-10316 |  |  | Harsh Verma | Backlog |  | P3 | 2025-12-11 |  | 2026-02-03 | sprint-Arthur | 0 | 0 | FILTER
Code Review | FILTER-11303 | Review PR for the REL : REL-10345 |  |  | Pratik Tiwari | Backlog |  | P3 | 2025-12-04 |  | 2026-02-03 | sprint-Arthur | 0 | 0 | FILTER
Code Review | FILTER-11310 | Review PR for the REL : REL-10321 |  |  | Pratik Tiwari | Backlog |  | P3 | 2025-12-04 |  | 2026-02-03 | sprint-Arthur | 0 | 0 | FILTER
Code Review | FILTER-11404 | Review PR for the REL : REL-10361 |  |  | Pratik Tiwari | Backlog |  | P3 | 2025-12-10 |  | 2026-02-03 | sprint-Arthur | 0 | 0 | FILTER
Code Review | FILTER-11064 | Review PR for the REL : REL-10254 |  |  | Swaroop Chavhan | Backlog |  | P3 | 2025-11-28 |  | 2026-02-03 | sprint-Arthur | 0 | 0 | FILTER
Code Review | FILTER-11301 | Review PR for the REL : REL-10345 |  |  | Swaroop Chavhan | Backlog |  | P3 | 2025-12-04 |  | 2026-02-03 | sprint-Arthur | 0 | 0 | FILTER
Code Review | FILTER-11372 | Review PR for the REL : REL-10198 |  |  | Swaroop Chavhan | Backlog |  | P3 | 2025-12-09 |  | 2026-02-03 | sprint-Arthur | 0 | 0 | FILTER
Code Review | FILTER-11405 | Review PR for the REL : REL-10361 |  |  | Swaroop Chavhan | Backlog |  | P3 | 2025-12-10 |  | 2026-02-03 | sprint-Arthur | 0 | 0 | FILTER

## Removed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Escape Defect | FILTER-7871 | P1 Escalation-Shortcut SmartPAC bypass; --user-agent ¦ Seattleschools |  |  | Ashish Temurnikar | Closed | Expected behavior | P1 | 2025-04-11 | 2026-01-19 | 2026-02-09 | sprint-Arthur | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_closed_notify, jira_escalated, jira_in_progress, jira_open, jira_reopened, p1escalation, unplanned-sprint |  | YES
Task | FDSE-140 | Implementation of Simple dropdown component with all the defined guidelines | FDSE-139 | Epic | Harshada Kude | Resolved | Fixed | P3 | 2025-12-09 | 2026-02-02 | 2026-02-02 | sprint-Arthur | 38 | 32 | FDSE |  |  | YES
Task | FILTER-11592 | [sprox] Function translation to sprox - Part 3 |  |  | Ravi Raj | Closed |  | P2 | 2026-01-05 |  | 2026-04-16 | sprint-Arthur | 24 | 1 | FILTER |  |  | YES
Task | FDSE-123 | Simple search component implementation without chip and without auto-complete | FDSE-122 | Epic | Shailendra Singh | Resolved |  | P3 | 2025-12-04 |  | 2026-02-11 | sprint-Arthur | 4 | 24 | FDSE | Capitalized-Feature, product-filter |  | YES
Task | FDSE-126 | Analysis - Search without chip but with auto-complete component implementation | FDSE-174 | Epic | Swaroop Chavhan | Resolved |  | P3 | 2025-12-04 |  | 2026-04-15 | sprint-Arthur | 12 | 12 | FDSE | Capitalized-Feature, product-filter |  | YES
Task | FDSE-137 | Analysis for timepicker component | FDSE-136 | Epic | Swaroop Chavhan | Resolved | Fixed | P3 | 2025-12-09 | 2026-02-02 | 2026-02-02 | sprint-Arthur | 16 | 16 | FDSE | product-filter |  | YES
Task | FDSE-142 | Dependabot issue fixes |  |  | Harsh Verma | Closed |  | P3 | 2026-01-05 |  | 2026-03-03 | sprint-Arthur | 5 | 8 | FDSE | product-filter
Task | FILTER-10900 | [Dependabot issues]Upgrade jspdf-autotable npm library to latest version (5.0) |  |  | Harshada Kude | Closed |  | P3 | 2025-11-21 |  | 2026-03-03 | sprint-Arthur | 16 | 0 | FILTER
Task | FILTER-10743 | [sprox] main.rs module separation part-2 | FILTER-8230 | Epic | Pratik Tiwari | Closed |  | P2 | 2025-11-10 |  | 2026-04-16 | sprint-Arthur | 0 | 10 | FILTER
Defect | FILTER-11581 | NewFeatureBug: SupportTool Customlist API. Name field can be saved with spaces at start and end. Add/Update |  |  | Sagar Satpute | Closed without action |  | P3 | 2026-01-05 |  | 2026-02-05 | sprint-Arthur | 0 | 0 | FILTER | unplanned-sprint
Task | FDSE-112 | Implementation of Button bars as per the design | FDSE-111 | Epic | Shailendra Singh | Resolved | Fixed | P3 | 2025-11-20 | 2026-02-09 | 2026-02-09 | sprint-Arthur | 24 | 20 | FDSE | product-filter
Task | FDSE-148 | Checkbox implementation with new design changes | FDSE-54 | Epic | Shailendra Singh | Resolved | Fixed | P3 | 2026-01-19 | 2026-02-01 | 2026-02-02 | sprint-Arthur | 32 | 16 | FDSE | product-filter
Task | FDSE-138 | Implement Time range as well in the existing date picker component | FDSE-102 | Epic | Swaroop Chavhan | Open |  | P3 | 2025-12-09 |  | 2026-04-28 | sprint-Arthur | 0 | 24 | FDSE

## P1 Escalation
P1 Escalation — FILTER · sprint-Arthur (2026-01-06 → 2026-01-19)
sprint-Arthur tickets where Issue Type = Escape Defect AND Priority = P1 AND summary contains 'P1 Escalation' (regardless of bucket). Total = 9.
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Bucket
Escape Defect | FILTER-10237 | P1 escalation-Crextn-specific Bypass using upgraded credentials |  |  | Ashish Modak | Release in Progress | Fixed | P1 | 2025-09-26 | 2025-11-20 | 2026-02-03 | sprint-Arthur | 6 | 6 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_escalated, jira_in_progress, p1escalation, unplanned-sprint |  | Completed
Escape Defect | FILTER-7871 | P1 Escalation-Shortcut SmartPAC bypass; --user-agent ¦ Seattleschools |  |  | Ashish Temurnikar | Closed | Expected behavior | P1 | 2025-04-11 | 2026-01-19 | 2026-02-09 | sprint-Arthur | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_closed_notify, jira_escalated, jira_in_progress, jira_open, jira_reopened, p1escalation, unplanned-sprint |  | Removed
Escape Defect | FILTER-11365 | P1 Escalation-Activity Page is not loading for Portland Public Schools (OR) |  |  | Nicolas Lemaitre | Closed | Fixed | P1 | 2025-12-08 | 2026-01-13 | 2026-01-13 | sprint-Arthur | 0 | 0 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_closed_notify, jira_escalated, jira_in_progress, p1escalation, unplanned-sprint, zendesk_org_at_risk |  | Completed
Escape Defect | FILTER-10392 | P1 Escalation-YouTube Videos play in Gmail even when blocked in policy ¦ Downingtown |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-10-10 | 2026-02-10 | 2026-04-07 | sprint-Arthur | 16 | 16 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_closed_notify, jira_escalated, jira_in_progress, jira_qa_verified, jira_reopened, p1escalation, unplanned-sprint |  | Removed
Escape Defect | FILTER-11047 | P1 Escalation-Filter bypass using Chrome://chrome-signin ¦ Edmonds |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-11-26 | 2026-01-27 | 2026-04-20 | sprint-Arthur | 17 | 0 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_closed_notify, jira_done, jira_escalated, jira_in_progress, jira_open, jira_qa_verified, p1escalation |  | Removed
Escape Defect | FILTER-11443 | P1 Escalation-Chrome extension bypass using Omada DNS |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-12-15 | 2026-01-21 | 2026-04-07 | sprint-Arthur | 16 | 16 | FILTER | jira_added, jira_closed_notify, jira_done, jira_escalated, jira_p1, zendesk_enterprise |  | Removed
Escape Defect | FILTER-11557 | P1 Escalation-Copy & Paste movie script into search bar breaks extension |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-12-22 | 2026-01-16 | 2026-04-07 | sprint-Arthur | 10 | 12 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_done, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_qa_verified, jira_reopened, p1escalation, unplanned-sprint |  | Removed
Escape Defect | FILTER-11680 | P1 Escalation-[PageScan] SPAC Changes for better coverage |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-01-16 | 2026-01-21 | 2026-03-09 | sprint-Arthur | 14 | 0 | FILTER | Reverified-2026, p1escalation, unplanned-sprint |  | Removed
Escape Defect | FILTER-6563 | P1 Escalation-Adjust Filter UI for high Rez monitors |  |  | Shashank Tiwari | Done | Fixed | P1 | 2024-12-17 | 2025-12-22 | 2026-03-09 | sprint-Arthur | 5 | 16 | FILTER | jira_added, jira_escalated, jira_open, jira_qa_verified, p1escalation, unplanned-sprint, zendesk_org_at_risk |  | Completed