## Capacity vs Delivery
Capacity vs Delivery — FILTER · sprint-Bertha (Tue 20 Jan → Mon 02 Feb 2026)
Team Composition (per Securly-PjM-Skills.md Part 2 — Filter India roster). Inactive members for this sprint window are shaded grey with a roster note.
Name | Role | Function / Split | Allocation (FTE) | Seniority | Employment | Notes
Shashank Tiwari | Project Manager | PM / Delivery | 0 | Lead | FTE | Not counted in delivery capacity
Harsh Verma | FE | FrontEnd Architect (Angular) | 1 | Senior | FTE
Arun Thakur | FE + Ext | Angular / Extension | 1 | Medium | FTE
Harshada Kude | FE | Angular | 1 | Junior | FTE
Shailendra Singh | FE | Angular | 1 | Medium | FTE
Swaroop Chavhan | FE + Ext | Angular / Extension | 1 | Medium | FTE
Ashish Modak | BE Architect | Extension / Go / PHP | 1 | Senior | FTE
Prateek Fotedar | BE (www) | Go / PHP | 1 | Senior | FTE
Sagar Satpute | BE (www) | Go / PHP | 1 | Medium | FTE
Vaibhav Kumbhar | BE | Go / PHP | 1 | Medium | FTE
Ashish Temurnikar | BE | DNS / SPAC / Squid / Rust | 1 | Senior | FTE
Ravi Raj | BE | DNS / SPAC / Squid / Rust | 1 | Medium | FTE
Pratik Tiwari | BE + Ext | Extension / Go / Rust | 1 | Senior | FTE
Altamash Heroli | QA | Pri. Manual QA | 1 | Senior | FTE
Surabhi Choudhary | QA | Sr. Manual QA | 1 | Senior | FTE
Ayesha Kamde | QA | Manual QA | 1 | Junior | FTE
Amol Mithari | Auto QA Lead | Team Lead — Auto QA / SDET | 0 | Lead | FTE | Joined team on 20-Feb-2026 — not part of this sprint
Amit Shete | Auto QA | Pri. SDET | 1 | Senior | FTE
Rachit Mishra | Auto QA | SDET | 1 | Junior | FTE
Total FILTER allocation |  |  |  | FTE-equivalent heads available to FILTER
Capacity Parameters (yellow cells are inputs — re-run the script after edits)
Parameter | Value | Description
Sprint length (working days) | 10 | FILTER 15-day sprint Tue → Mon. sprint-Bertha = 2026-01-20 → 2026-02-02.
Company holidays in sprint | 1 | India calendar 2026 — 26-Jan: Republic Day
Effective working days (sprint − company holidays) |  | Used as the per-person calendar for availability
Hours per working day (nominal) | 8 | Standard working day
Focus factor (productive fraction) | 0.9 | 90% — what SLT expects (sprint-analysis default)
Misc buffer (meetings, scrums, code review, …) | 20% | 20% blanket reservation deducted from Available to get Net Available
Effective hours per FTE per sprint
Allocated FTE on FILTER (active this sprint) | 17 | Headcount actually working this sprint (excludes joiners/leavers outside window)
Ideal capacity for the sprint (hrs)
Issue scope (Jira projects) | FILTER, PTGM, FDSE | Tickets pulled with `project in (FILTER, PTGM, FDSE) AND sprint = …` — FDSE: 11 · FILTER: 273 · PTGM: 21
Capacity vs Actual Delivery — sprint-Bertha
Metric | Hours | % of Ideal | Rating | Notes
Actual Availability |  |  |  | Sum of per-person availability (Ideal − leaves)
Misc Buffer (20%) |  |  |  | Reserved for meetings, scrums, code reviews
Net Available (Available − Misc Buffer) |  |  |  | Realistic delivery capacity — used as the denominator for Completed %
Completed |  |  |  | Sum of in-sprint timeSpent (Completed bucket)
Not Completed (Spillover) |  |  |  | Original estimate for spillover (carried into next sprint)
Removed |  |  |  | Original estimate for issues removed mid-sprint
Completed by Priority
Tickets (parents) = unique parent items (Story / Task / Defect / Escape Defect) — subtasks roll up to their parent so 1 parent + 3 subtasks = 1 ticket. Tickets (incl. subtasks) = raw record count incl. every Dev / QA / Automation / Review / Test Case Creation / Debug subtask. Hours = sum across parents and subtasks; matches the core-team Completed hours on the Per-person Delivery sheet.
Priority | Tickets (parents) | Tickets (incl. subtasks) | Hours (incl. subtasks) | % of Completed Hrs | % of Tickets (parents) | Notes
P0 | 3 | 7 | 26.5 |  |  | Critical / production halting
P1 | 13 | 25 | 146.02 |  |  | P1 — high priority (see P1 Escalation tab for escalations)
P2 | 6 | 13 | 91 |  |  | Major
P3 | 31 | 100 | 780.32 |  |  | Standard
TOTAL | 53 | 145 | 1043.84 | 100% | 100% | Sum of Completed bucket (core roster)
Sprint Completion (spillover = Not Completed)
Metric | Tickets | Planned Hrs (OE) | % by Tickets | % by Hrs | Notes
Completed (closed in sprint) | 145 | 1034.5 |  |  | In-sprint deliverables
Spillover (not completed → carry-over) | 12 | 0.5 |  |  | Original estimate carried to next sprint
Removed (mid-sprint scope cut) | 12 | 136 | — | — | Excluded from completion ratio (out of scope)
Mid-sprint additions (core) | 14 |  | — | — | Late-arriving work (Jira issueKeysAddedDuringSprint)
Sprint completion rate (tickets) | 92.36% | On Target | Completed ÷ (Completed + Spillover)
Sprint completion rate (planned hrs) | 99.95% | On Target | Σ OE Completed ÷ Σ OE (Completed + Spillover)
Planned completion rate (tickets, excludes mid-sprint adds) | 91.72% | On Target | Originally-committed tickets only
Planned completion rate (planned hrs, excludes mid-sprint adds) | 99.94% | On Target | Originally-committed planned hours only
P1 Escalation snapshot
13 ticket(s) in sprint-Bertha match 'P1 Escalation' in the title — 12 closed, 1 still open. See the 'P1 Escalation' tab.
Mid-sprint additions snapshot
14 ticket(s) were added to sprint-Bertha after it started (issueKeysAddedDuringSprint) — Completed 12, Spillover 0, Removed 2. Highlighted in amber on every detail sheet (Added Mid-Sprint = YES).
Assumptions & caveats
• Sprint window from Jira (/rest/agile/1.0/sprint/4667): 2026-01-20 → 2026-02-02 (10 Mon–Fri working days). Refresh with fetch_filter_sprint_meta.py + fetch_filter_sprint_issues.py.
• Issues pulled from FILTER + PTGM + FDSE (project-scope expanded for the India scrum team's split across the three products).
• Date-aware roster: Amol Mithari joined 20-Feb-2026; Rachit Mishra's last day was 20-Feb-2026. Inactive members for this sprint window are shaded grey in the Team Composition table and excluded from per-person availability + delivery.
• Available (hrs) = (effective working days − leave days) × 8 × focus factor, where effective working days = sprint working days − company holidays falling inside the sprint − days outside the person's employment window. Per-person Delivery shows leave days in Column G to explain the delta from a full sprint.
• Net Available = Available − 20% Misc Buffer for meetings, scrums, code review, etc. Completed/Not Completed/Removed % of capacity use Net Available as the denominator.
• Time Spent on Completed sheet uses the in-sprint hybrid worklog rule (sprint-analysis.md): single-sprint = timespent; multi-sprint = SUM of worklogs whose started ∈ [sprintStart, sprintEnd].
• Not Completed and Removed totals use Original Estimate.
• Removed list comes from the Sprint Report puntedIssues (greenhopper API).
• Core roster only: assignees outside Securly-PjM-Skills.md Part 2 are dropped from per-person + detail sheets.
• P1 Escalation tab is filtered to Issue Type = Escape Defect AND Priority = P1 AND title contains 'P1 Escalation'.
• Completed by Priority — Tickets (parents) rolls subtasks up to their parent (each work item counted once at its parent priority); Tickets (incl. subtasks) shows the raw record count for comparison. The Hours column sums every record (parent + subtasks) and matches the core-team Completed total.
• Spillover = Not Completed bucket (tickets carried into the next sprint).
• Sprint completion rate uses Completed ÷ (Completed + Spillover); Removed tickets are excluded (treated as scope cut). 'Planned' rate also excludes mid-sprint additions.
• All detail sheets (Completed, Not Completed, Removed) highlight tickets added after sprint start (Jira sprint-report issueKeysAddedDuringSprint) in amber, with an 'Added Mid-Sprint = YES' tag column.
• Ratings: ≥85% On Target (green), 70–85% Below Target (amber), <70% Significantly Below (red).

## Per-person Delivery
Assignee | Completed (hrs) | Not Completed (hrs) | Removed (hrs) | Efficiency | Available (hrs) | Leave Days (sprint) | Misc Buffer 20% (hrs) | Net Available (hrs)
Harsh Verma | 62 | 0 | 32 |  | 43.2 | 3
Arun Thakur | 14.5 | 0.5 | 0 |  | 36 | 4
Harshada Kude | 55.5 | 0 | 8 |  | 64.8 | 0
Shailendra Singh | 38 | 0 | 44 |  | 64.8 | 0
Swaroop Chavhan | 48 | 0 | 12 |  | 64.8 | 0
Ashish Modak | 42 | 0 | 0 |  | 64.8 | 0
Prateek Fotedar | 105.5 | 0 | 0 |  | 64.8 | 0
Sagar Satpute | 197 | 0 | 0 |  | 64.8 | 0
Vaibhav Kumbhar | 24 | 0 | 0 |  | 64.8 | 0
Ashish Temurnikar | 62 | 0 | 16 |  | 64.8 | 0
Ravi Raj | 88 | 0 | 12 |  | 64.8 | 0
Pratik Tiwari | 72 | 0 | 12 |  | 64.8 | 0
Altamash Heroli | 88.34 | 0 | 0 |  | 43.2 | 3
Surabhi Choudhary | 21.5 | 0 | 0 |  | 64.8 | 0
Ayesha Kamde | 40 | 0 | 0 |  | 57.6 | 1
Amit Shete | 37.5 | 0 | 0 |  | 50.4 | 2
Rachit Mishra | 48 | 0 | 0 |  | 64.8 | 0
TOTAL

## Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Debug | FILTER-11747 | Image Blur – NSFW Model Switch (InceptionV3 → MobileNetV2) |  |  | Arun Thakur | Closed | Fixed | P3 | 2026-01-21 | 2026-01-22 | 2026-02-09 | sprint-Bertha | 8 | 8 | FILTER | unplanned-sprint |  | YES
Task | FILTER-11787 | Remove school.pepikutan.net - rammerhead from vector expansion config.json |  |  | Arun Thakur | Closed |  | P3 | 2026-01-23 |  | 2026-04-16 | sprint-Bertha | 3 | 3 | FILTER | unplanned-sprint |  | YES
Escape Defect | FILTER-7871 | P1 Escalation-Shortcut SmartPAC bypass; --user-agent ¦ Seattleschools |  |  | Ashish Temurnikar | Closed | Expected behavior | P1 | 2025-04-11 | 2026-01-19 | 2026-02-09 | sprint-Bertha | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_closed_notify, jira_escalated, jira_in_progress, jira_open, jira_reopened, p1escalation, unplanned-sprint |  | YES
Escape Defect | FILTER-11743 | Restrict AI power mode in search engines setting is currently a configurable setting in policies |  |  | Ayesha Kamde | Done | Done | P3 | 2026-01-20 | 2026-02-02 | 2026-04-15 | sprint-Bertha | 6 | 0 | FILTER | jira_added, jira_closed_notify, jira_done, jira_escalated, jira_p3, jira_qa_verified, unplanned-sprint |  | YES
Task | FILTER-11695 | Helping classroom team for PR review and Technical discussions |  |  | Harsh Verma | Closed |  | P3 | 2026-01-19 |  | 2026-04-17 | sprint-Bertha | 4 | 4 | FILTER | unplanned-sprint |  | YES
Task | FILTER-11696 | Helping Home Team for the overall architecture of Parent Portal design Revamp and and AI Chat for their dashobard requirement |  |  | Harsh Verma | Closed |  | P3 | 2026-01-19 |  | 2026-04-17 | sprint-Bertha | 24 | 24 | FILTER | unplanned-sprint |  | YES
Task | FILTER-11698 | Do a POC on CMS and its consumption in different products |  |  | Harsh Verma | Closed |  | P3 | 2026-01-19 |  | 2026-04-17 | sprint-Bertha | 28 | 40 | FILTER |  |  | YES
Task | FILTER-11770 | Fix GitHub Action build issue |  |  | Harsh Verma | Closed | Done | P3 | 2026-01-22 | 2026-01-28 | 2026-04-17 | sprint-Bertha | 6 | 8 | FILTER | unplanned-sprint |  | YES
Task | FDSE-141 | Cosume Label component | FDSE-146 | Epic | Harshada Kude | Resolved | Fixed | P3 | 2025-12-22 | 2026-01-22 | 2026-01-23 | sprint-Bertha | 5.5 | 8 | FDSE | product-filter |  | YES
Task | FILTER-11590 | [sprox] unwrap handling in main.rs - main.rs modularisation part 3 | FILTER-8230 | Epic | Pratik Tiwari | Closed |  | P2 | 2026-01-05 |  | 2026-04-16 | sprint-Bertha | 8 | 8 | FILTER |  |  | YES
Escape Defect | FILTER-8535 | P1 Escalation-Google search drag and drop bypass |  |  | Pratik Tiwari | Closed | Cannot Reproduce | P1 | 2025-05-30 | 2026-02-26 | 2026-02-26 | sprint-Bertha | 24 | 8 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_escalated, jira_qa_verified, p1escalation, unplanned-sprint |  | YES
Task | FDSE-147 | Datepicker Single Date and Date Range - UX enhancements, review comments | FDSE-102 | Epic | Swaroop Chavhan | Resolved | Fixed | P3 | 2026-01-19 | 2026-02-01 | 2026-02-02 | sprint-Bertha | 32 | 24 | FDSE | product-filter |  | YES
QA | FILTER-10858 | QA - List of custom list (New API) | FILTER-10835 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-13 | sprint-Bertha | 5 | 5 | FILTER | Capitalized-Feature
QA | FILTER-10861 | QA - Get Resources of securly custom list (New API) | FILTER-10835 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-09 | sprint-Bertha | 5 | 4 | FILTER | Capitalized-Feature
QA | FILTER-10864 | Add/Update custom list (New API) | FILTER-10835 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-09 | sprint-Bertha | 5 | 4 | FILTER | Capitalized-Feature
QA | FILTER-10867 | QA - Delete custom list (New API) | FILTER-10835 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-09 | sprint-Bertha | 5 | 10 | FILTER | Capitalized-Feature
QA | FILTER-10870 | How to Handle sycing Error | FILTER-10835 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-09 | sprint-Bertha | 5 | 0 | FILTER | Capitalized-Feature
QA | FILTER-10874 | Link polices to custom list in case of update | FILTER-10871 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-23 | sprint-Bertha | 3 | 6 | FILTER | Capitalized-Feature
QA | FILTER-10877 | New Feature ¦ Unlink polices to custom list in case of update | FILTER-10871 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-23 | sprint-Bertha | 1 | 6 | FILTER | Capitalized-Feature
QA | FILTER-10881 | New Feature ¦ Add custom list (New API) | FILTER-10878 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-23 | sprint-Bertha | 8 | 10 | FILTER | Capitalized-Feature
QA | FILTER-10884 | New Feature ¦ List of Policies (Might be existing API or New API) | FILTER-10878 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-23 | sprint-Bertha | 1 | 5 | FILTER | Capitalized-Feature
QA | FILTER-10887 | New Feature ¦ Get custom list Details (New API) | FILTER-10878 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-23 | sprint-Bertha | 3 | 3 | FILTER | Capitalized-Feature
QA | FILTER-10890 | New Feature ¦ Get custom list Resources (New API) | FILTER-10878 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-23 | sprint-Bertha | 4 | 5 | FILTER | Capitalized-Feature
QA | FILTER-10893 | New Feature ¦ Get custom list Association (New API) | FILTER-10878 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-23 | sprint-Bertha | 3 | 3 | FILTER | Capitalized-Feature
QA | FILTER-10896 | New Feature ¦ Update Custom List (New API) | FILTER-10878 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-23 | sprint-Bertha | 6 | 10 | FILTER | Capitalized-Feature
QA | FILTER-10899 | New Feature ¦ Delete Custom List (New API) | FILTER-10878 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-11-21 |  | 2026-01-23 | sprint-Bertha | 6 | 10 | FILTER | Capitalized-Feature
QA | FILTER-11077 | New Feature ¦ Add resource in custom list (New API) | FILTER-11074 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-12-01 |  | 2026-01-23 | sprint-Bertha | 3 | 5 | FILTER | Capitalized-Feature
QA | FILTER-11080 | New Feature ¦ Update resource of custom list (New API) | FILTER-11074 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-12-01 |  | 2026-01-23 | sprint-Bertha | 3 | 5 | FILTER | Capitalized-Feature
QA | FILTER-11083 | New Feature ¦ Delete resource or resource note from custom list (New API) | FILTER-11074 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-12-01 |  | 2026-01-23 | sprint-Bertha | 4 | 6 | FILTER | Capitalized-Feature
QA | FILTER-11086 | New Feature ¦ Clone Custom list (New API) | FILTER-11074 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-12-01 |  | 2026-01-23 | sprint-Bertha | 3 | 7 | FILTER | Capitalized-Feature
QA | FILTER-11090 | New Feature ¦ Local Custom Lists (FID-specific) | FILTER-11087 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-12-01 |  | 2026-01-27 | sprint-Bertha | 0.08 | 2 | FILTER | Capitalized-Feature
QA | FILTER-11093 | New Feature ¦ Global Custom Lists (Shared Across FIDs) | FILTER-11087 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-12-01 |  | 2026-01-27 | sprint-Bertha | 0.08 | 2 | FILTER | Capitalized-Feature
QA | FILTER-11101 | New Feature ¦ List of custom list (New API) | FILTER-11098 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-12-01 |  | 2026-01-23 | sprint-Bertha | 2 | 4 | FILTER | Capitalized-Feature
QA | FILTER-11104 | New Feature ¦ View the details of custom list | FILTER-11098 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-12-01 |  | 2026-01-27 | sprint-Bertha | 0.08 | 2 | FILTER | Capitalized-Feature
QA | FILTER-11107 | New Feature ¦ Add URL to the Allow/Block list (Existing API) | FILTER-11098 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-12-01 |  | 2026-01-23 | sprint-Bertha | 6 | 6 | FILTER | Capitalized-Feature
QA | FILTER-11110 | New Feature ¦ Deleting URL from the Allow/Block list (Existing API) | FILTER-11098 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-12-01 |  | 2026-01-23 | sprint-Bertha | 4 | 6 | FILTER | Capitalized-Feature
QA | FILTER-11113 | New Feature ¦ Fetching allow/block list of policy | FILTER-11098 | Story | Altamash Heroli | QA Verified |  | P3 | 2025-12-01 |  | 2026-01-27 | sprint-Bertha | 0.08 | 2 | FILTER | Capitalized-Feature
QA | FILTER-11209 | QA - main.rs module separation part-2 | FILTER-10743 | Task | Altamash Heroli | Closed without action |  | P3 | 2025-12-03 |  | 2025-12-08 | sprint-Bertha | 0 | 0 | FILTER
QA | FILTER-11281 | QA - [sprox] SQS connection service implementation | FILTER-10744 | Task | Altamash Heroli | Closed without action |  | P3 | 2025-12-04 |  | 2025-12-08 | sprint-Bertha | 0 | 0 | FILTER
QA | FILTER-11284 | QA - [sprox] Td-Agent service implementation | FILTER-10745 | Task | Altamash Heroli | Closed without action |  | P3 | 2025-12-04 |  | 2025-12-08 | sprint-Bertha | 0 | 0 | FILTER
QA | FILTER-11542 | Manual QA Validation: Broker Stability and Log Audit (us-east-1 AL2) | FILTER-11312 | Escape Defect | Altamash Heroli | Closed without action |  | P2 | 2025-12-21 |  | 2026-02-02 | sprint-Bertha | 0 | 0 | FILTER
QA | FILTER-11641 | Manual QA Validation for Youtube Unrestricted mode | FILTER-11638 | Escape Defect | Altamash Heroli | Done |  | P3 | 2026-01-14 |  | 2026-04-16 | sprint-Bertha | 1 | 4 | FILTER
QA | FILTER-11648 | QA Task ¦ P1 Escalation-Shortcut SmartPAC bypass; --user-agent ¦ Seattleschools | FILTER-7871 | Escape Defect | Altamash Heroli | Closed without action |  | P1 | 2026-01-15 |  | 2026-01-27 | sprint-Bertha | 0 | 0 | FILTER
QA | FILTER-11730 | Manual QA task for retesting | FILTER-11678 | Defect | Altamash Heroli | Closed without action |  | P0 | 2026-01-20 |  | 2026-01-20 | sprint-Bertha | 0 | 0 | FILTER
QA | FILTER-11738 | QA Task for retest | FILTER-11689 | Defect | Altamash Heroli | QA Verified |  | P1 | 2026-01-20 |  | 2026-02-12 | sprint-Bertha | 1 | 1 | FILTER | Capitalized-Feature
QA | FILTER-11739 | QA task for retest | FILTER-11690 | Defect | Altamash Heroli | Done |  | P1 | 2026-01-20 |  | 2026-02-12 | sprint-Bertha | 1.02 | 1 | FILTER | Capitalized-Feature
Automation | FILTER-10857 | Automation - List of custom list (New API) | FILTER-10835 | Story | Amit Shete | Done |  | P3 | 2025-11-21 |  | 2026-01-09 | sprint-Bertha | 8.5 | 8 | FILTER | Capitalized-Feature
Automation | FILTER-10860 | Automation - Get Resources of securly custom list (New API) | FILTER-10835 | Story | Amit Shete | Done |  | P3 | 2025-11-21 |  | 2026-01-09 | sprint-Bertha | 6 | 5 | FILTER | Capitalized-Feature
Automation | FILTER-10863 | Add/Update custom list (New API) | FILTER-10835 | Story | Amit Shete | Done |  | P3 | 2025-11-21 |  | 2026-01-09 | sprint-Bertha | 4.5 | 5 | FILTER | Capitalized-Feature
Automation | FILTER-10866 | Automation - Delete custom list (New API) | FILTER-10835 | Story | Amit Shete | Done |  | P3 | 2025-11-21 |  | 2026-01-09 | sprint-Bertha | 3.5 | 4 | FILTER | Capitalized-Feature
Automation | FILTER-10869 | How to Handle sycing Error | FILTER-10835 | Story | Amit Shete | Done |  | P3 | 2025-11-21 |  | 2026-02-03 | sprint-Bertha | 6 | 6 | FILTER | Capitalized-Feature
Automation | FILTER-11089 | New Feature ¦ Local Custom Lists (FID-specific) | FILTER-11087 | Story | Amit Shete | Done |  | P3 | 2025-12-01 |  | 2026-02-02 | sprint-Bertha | 4.5 | 5 | FILTER | Capitalized-Feature
Automation | FILTER-11092 | New Feature ¦ Global Custom Lists (Shared Across FIDs) | FILTER-11087 | Story | Amit Shete | Done |  | P3 | 2025-12-01 |  | 2026-02-02 | sprint-Bertha | 4.5 | 5 | FILTER | Capitalized-Feature
Automation | FILTER-11468 | Automation task for backmerge to TS Extension FILTER-8535 | FILTER-11465 | Task | Amit Shete | Closed without action |  | P3 | 2025-12-18 |  | 2026-01-15 | sprint-Bertha | 0 | 0 | FILTER
Automation | FILTER-11541 | Automated P1 Regression: Stress Test Broker with Malformed Time Strings and Null Auth | FILTER-11312 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2025-12-21 |  | 2026-02-03 | sprint-Bertha | 0 | 6 | FILTER
Automation | FILTER-11663 | Create Automated Tests for iOS Image Sidebar Inappropriate Image Leak Fix | FILTER-11644 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-01-15 |  | 2026-02-03 | sprint-Bertha | 0 | 5 | FILTER
Defect | FILTER-10624 | NewFeatureBug: Block page shows blurred image and Image results do not show info |  |  | Arun Thakur | RELEASED TO PROD | Fixed | P3 | 2025-11-05 | 2025-11-06 | 2026-02-12 | sprint-Bertha | 0.5 | 0.5 | FILTER | unplanned-sprint
Dev | FILTER-11917 | Remove school.pepikutan.net - rammerhead from vector expansion config.json | FILTER-11787 | Task | Arun Thakur | Done |  | P3 | 2026-02-02 |  | 2026-02-02 | sprint-Bertha | 3 | 3 | FILTER
Escape Defect | FILTER-10237 | P1 escalation-Crextn-specific Bypass using upgraded credentials |  |  | Ashish Modak | Release in Progress | Fixed | P1 | 2025-09-26 | 2025-11-20 | 2026-02-03 | sprint-Bertha | 6 | 6 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_escalated, jira_in_progress, p1escalation, unplanned-sprint
Dev | FILTER-11377 | Broker Logic Fix: Prevent Managed Chromebooks from Redirecting to DNS Broker when DNS Bit is ON | FILTER-11325 | Story | Ashish Modak | Done |  | P1 | 2025-12-09 |  | 2026-01-27 | sprint-Bertha | 12 | 12 | FILTER
Dev | FILTER-11391 | Fix CKEC Filter Bypass: Intercept Navigation from chrome://chrome-signin Internal Pages | FILTER-11047 | Escape Defect | Ashish Modak | Done |  | P1 | 2025-12-09 |  | 2026-01-27 | sprint-Bertha | 16 | 16 | FILTER
Dev | FILTER-11810 | [Extension] POC to avoid double filtering on Managed chromebooks. | FILTER-11325 | Story | Ashish Modak | Done |  | P3 | 2026-01-28 |  | 2026-01-28 | sprint-Bertha | 8 | 8 | FILTER
Dev | FILTER-11279 | [sprox] SQS connection service implementation | FILTER-10744 | Task | Ashish Temurnikar | Done |  | P3 | 2025-12-04 |  | 2026-02-02 | sprint-Bertha | 16 | 8 | FILTER
Dev | FILTER-11282 | [sprox] Td-Agent service implementation | FILTER-10745 | Task | Ashish Temurnikar | Done |  | P3 | 2025-12-04 |  | 2026-02-02 | sprint-Bertha | 16 | 8 | FILTER
Dev | FILTER-11647 | P1 Escalation-Shortcut SmartPAC bypass; --user-agent ¦ Seattleschools | FILTER-7871 | Escape Defect | Ashish Temurnikar | Closed without action |  | P1 | 2026-01-15 |  | 2026-01-27 | sprint-Bertha | 0 | 0 | FILTER
Dev | FILTER-11662 | Fix Image Sidebar Leaking Inappropriate Images on iOS (iPadOS/Safari) | FILTER-11644 | Escape Defect | Ashish Temurnikar | Done |  | P1 | 2026-01-15 |  | 2026-01-29 | sprint-Bertha | 12 | 12 | FILTER
Dev | FILTER-11681 | [SPAC] Domains request from SPAC to Pagescan | FILTER-11680 | Escape Defect | Ashish Temurnikar | Done |  | P1 | 2026-01-16 |  | 2026-01-21 | sprint-Bertha | 10 | 8 | FILTER
Dev | FILTER-11809 | [dns/spac] Squid logic to check extension variable in url | FILTER-11325 | Story | Ashish Temurnikar | Done |  | P3 | 2026-01-28 |  | 2026-01-29 | sprint-Bertha | 8 | 6 | FILTER
QA | FILTER-11509 | Manual QA Validation: Verify Activity Log Consistency for Eaglercraft (US East2) | FILTER-10069 | Escape Defect | Ayesha Kamde | Done |  | P3 | 2025-12-19 |  | 2026-02-02 | sprint-Bertha | 2 | 2 | FILTER
QA | FILTER-11576 | Manual QA Validation: Broker Stability Audit & Log Monitoring | FILTER-11478 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2026-01-05 |  | 2026-01-09 | sprint-Bertha | 4 | 4 | FILTER
QA | FILTER-11594 | QA - P1 Escalation-Copy & Paste movie script into search bar breaks extension | FILTER-11557 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2026-01-06 |  | 2026-01-30 | sprint-Bertha | 4 | 3 | FILTER
QA | FILTER-11733 | QA Validation to test hotfix is handling the deleted user case but isn't handling the disabled user case. | FILTER-11707 | Task | Ayesha Kamde | Done |  | P0 | 2026-01-20 |  | 2026-01-20 | sprint-Bertha | 4 | 3 | FILTER
QA | FILTER-11785 | QA task Check if archived users are not getting imported through OU import | FILTER-11783 | Task | Ayesha Kamde | Done |  | P0 | 2026-01-23 |  | 2026-01-23 | sprint-Bertha | 4 | 3 | FILTER
QA | FILTER-11786 | QA Validation task | FILTER-11743 | Escape Defect | Ayesha Kamde | QA Verified |  | P3 | 2026-01-23 |  | 2026-01-30 | sprint-Bertha | 6 | 4 | FILTER
QA | FILTER-11821 | Post release validation for FILTER-11783 | FILTER-11783 | Task | Ayesha Kamde | QA Verified |  | P3 | 2026-01-29 |  | 2026-02-03 | sprint-Bertha | 4 | 4 | FILTER
QA | FILTER-11823 | Post release validation for FILTER-6563 | FILTER-11822 | Task | Ayesha Kamde | Done |  | P3 | 2026-01-29 |  | 2026-01-29 | sprint-Bertha | 6 | 10 | FILTER
Task | FDSE-140 | Implementation of Simple dropdown component with all the defined guidelines | FDSE-139 | Epic | Harshada Kude | Resolved | Fixed | P3 | 2025-12-09 | 2026-02-02 | 2026-02-02 | sprint-Bertha | 38 | 32 | FDSE
Debug | FILTER-11584 | Dev Task - [Dependabot issues]Upgrade jspdf-autotable npm library to latest version (5.0) |  |  | Harshada Kude | Closed |  | P3 | 2026-01-05 |  | 2026-02-02 | sprint-Bertha | 12 | 14 | FILTER
Dev | FILTER-10854 | List of custom list (New API) | FILTER-10835 | Story | Prateek Fotedar | Done |  | P3 | 2025-11-21 |  | 2026-01-22 | sprint-Bertha | 7 | 7 | FILTER | Capitalized-Feature
Dev | FILTER-10859 | Get Resources of Securly custom list (New API) | FILTER-10835 | Story | Prateek Fotedar | Done |  | P3 | 2025-11-21 |  | 2026-01-22 | sprint-Bertha | 6 | 6 | FILTER | Capitalized-Feature
Dev | FILTER-10862 | Add/Update custom list (New API) | FILTER-10835 | Story | Prateek Fotedar | Done |  | P3 | 2025-11-21 |  | 2026-01-22 | sprint-Bertha | 4 | 4 | FILTER | Capitalized-Feature
Dev | FILTER-10865 | Delete custom list (New API) | FILTER-10835 | Story | Prateek Fotedar | Done |  | P3 | 2025-11-21 |  | 2026-01-22 | sprint-Bertha | 4 | 4 | FILTER | Capitalized-Feature
Dev | FILTER-10868 | How to Handle sycing Error | FILTER-10835 | Story | Prateek Fotedar | Done |  | P3 | 2025-11-21 |  | 2026-01-22 | sprint-Bertha | 7 | 7 | FILTER | Capitalized-Feature
Dev | FILTER-10872 | Link polices to custom list in case of update | FILTER-10871 | Story | Prateek Fotedar | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 8 | 8 | FILTER | Capitalized-Feature
Dev | FILTER-10875 | Unlink polices to custom list in case of update | FILTER-10871 | Story | Prateek Fotedar | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 8 | 8 | FILTER | Capitalized-Feature
Dev | FILTER-10882 | List of Policies (Might be existing API or New API) | FILTER-10878 | Story | Prateek Fotedar | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 7 | 8 | FILTER | Capitalized-Feature
Dev | FILTER-11075 | Add resource in custom list (New API) | FILTER-11074 | Story | Prateek Fotedar | Done |  | P3 | 2025-12-01 |  | 2026-01-21 | sprint-Bertha | 8 | 8 | FILTER | Capitalized-Feature
Dev | FILTER-11078 | Update resource of custom list (New API) | FILTER-11074 | Story | Prateek Fotedar | Done |  | P3 | 2025-12-01 |  | 2026-01-21 | sprint-Bertha | 10 | 10 | FILTER | Capitalized-Feature
Dev | FILTER-11081 | New Feature ¦ Delete resource or resource note from custom list (New API) | FILTER-11074 | Story | Prateek Fotedar | Done |  | P3 | 2025-12-01 |  | 2026-01-21 | sprint-Bertha | 14 | 14 | FILTER | Capitalized-Feature
Dev | FILTER-11084 | New Feature ¦ Clone Custom list (New API) | FILTER-11074 | Story | Prateek Fotedar | Done |  | P3 | 2025-12-01 |  | 2026-01-21 | sprint-Bertha | 14 | 14 | FILTER | Capitalized-Feature
Dev | FILTER-11683 | Investigate and fix 400 Bad Request error in PUT /api/custom-list/resource API | FILTER-11678 | Defect | Prateek Fotedar | Closed without action |  | P0 | 2026-01-16 |  | 2026-01-16 | sprint-Bertha | 1.5 | 1.5 | FILTER
Dev | FILTER-11699 | Fix issues for custom list | FILTER-11689 | Defect | Prateek Fotedar | Done |  | P1 | 2026-01-19 |  | 2026-02-12 | sprint-Bertha | 5 | 5 | FILTER | Capitalized-Feature
Dev | FILTER-11703 | Investigate and fix API logic to prevent linking the same custom list to the same policy with both ALLOW and BLOCK association types | FILTER-11690 | Defect | Prateek Fotedar | Done |  | P1 | 2026-01-19 |  | 2026-02-12 | sprint-Bertha | 2 | 2 | FILTER | Capitalized-Feature
Task | FILTER-10743 | [sprox] main.rs module separation part-2 | FILTER-8230 | Epic | Pratik Tiwari | Closed |  | P2 | 2025-11-10 |  | 2026-04-16 | sprint-Bertha | 0 | 10 | FILTER
Dev | FILTER-11351 | [sprox] main.rs module separation part-2 | FILTER-10743 | Task | Pratik Tiwari | Closed without action |  | P3 | 2025-12-08 |  | 2026-01-26 | sprint-Bertha | 0 | 8 | FILTER
Dev | FILTER-11384 | Fix CRXTN/YouTube Stuck Overlay in Fail Open Mode | FILTER-10842 | Defect | Pratik Tiwari | Closed without action |  | P1 | 2025-12-09 |  | 2026-01-11 | sprint-Bertha | 0 | 12 | FILTER
Dev | FILTER-11466 | Dev Task for Backmerge to TS Extension FILTER-8535 | FILTER-11465 | Task | Pratik Tiwari | Closed without action |  | P3 | 2025-12-18 |  | 2026-01-16 | sprint-Bertha | 0 | 6 | FILTER
Dev | FILTER-11591 | unwrap handling in main.rs | FILTER-11590 | Task | Pratik Tiwari | Done |  | P3 | 2026-01-05 |  | 2026-02-03 | sprint-Bertha | 8 | 8 | FILTER
Dev | FILTER-11593 | P1 Escalation-Copy & Paste movie script into search bar breaks extension | FILTER-11557 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-01-06 |  | 2026-01-28 | sprint-Bertha | 16 | 12 | FILTER
Task | FILTER-11714 | [sprox] Implementation of Github action & workflow decisions | FILTER-8230 | Epic | Pratik Tiwari | Closed |  | P3 | 2026-01-19 |  | 2026-02-03 | sprint-Bertha | 8 | 8 | FILTER
Dev | FILTER-11721 | [sprox] Implementation of Github action & workflow decisions | FILTER-11714 | Task | Pratik Tiwari | Done |  | P3 | 2026-01-19 |  | 2026-02-03 | sprint-Bertha | 8 | 8 | FILTER
Automation | FILTER-10880 | New Feature ¦ Add custom list (New API) | FILTER-10878 | Story | Rachit Mishra | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 7.5 | 8 | FILTER | Capitalized-Feature
Automation | FILTER-10886 | New Feature ¦ Get custom list Details (New API) | FILTER-10878 | Story | Rachit Mishra | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 7 | 8 | FILTER | Capitalized-Feature
Automation | FILTER-10889 | New Feature ¦ Get custom list Resources (New API) | FILTER-10878 | Story | Rachit Mishra | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 5 | 6 | FILTER | Capitalized-Feature
Automation | FILTER-10895 | New Feature ¦ Update Custom List (New API) | FILTER-10878 | Story | Rachit Mishra | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 8 | 7 | FILTER | Capitalized-Feature
Automation | FILTER-10898 | New Feature ¦ Delete Custom List (New API) | FILTER-10878 | Story | Rachit Mishra | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 6.5 | 7 | FILTER | Capitalized-Feature
Automation | FILTER-11508 | Automated E2E Regression: Validate Log Status for Blocked PAC Domains | FILTER-10069 | Escape Defect | Rachit Mishra | Done |  | P3 | 2025-12-19 |  | 2026-02-03 | sprint-Bertha | 3 | 6 | FILTER
Automation | FILTER-11728 | Unplanned Automation execution request during the sprint-Bertha | FILTER-11727 | Task | Rachit Mishra | Done |  | P3 | 2026-01-20 |  | 2026-01-26 | sprint-Bertha | 5 | 5 | FILTER
Automation | FILTER-11729 | Unplanned automation execution request during the sprint-Bertha | FILTER-11727 | Task | Rachit Mishra | Done |  | P3 | 2026-01-20 |  | 2026-01-29 | sprint-Bertha | 5 | 6 | FILTER
QA | FILTER-11746 | Fix UA parsing errors for valid UAs | FILTER-11685 | Escape Defect | Rachit Mishra | Done |  | P1 | 2026-01-20 |  | 2026-01-29 | sprint-Bertha | 1 | 1 | FILTER
Dev | FILTER-11573 | [sprox] Function translation to sprox - Part 3 | FILTER-11592 | Task | Ravi Raj | Done |  | P3 | 2026-01-04 |  | 2026-02-02 | sprint-Bertha | 24 | 16 | FILTER
Task | FILTER-11592 | [sprox] Function translation to sprox - Part 3 |  |  | Ravi Raj | Closed |  | P2 | 2026-01-05 |  | 2026-04-16 | sprint-Bertha | 24 | 1 | FILTER
Task | FILTER-11716 | [sprox] Broker & Blocked redirection implementation with interpret header call | FILTER-8230 | Epic | Ravi Raj | Closed |  | P3 | 2026-01-19 |  | 2026-02-02 | sprint-Bertha | 20 | 1 | FILTER | unplanned-sprint
Dev | FILTER-11719 | [sprox] Broker & Blocked redirection implementation with interpret header call | FILTER-11716 | Task | Ravi Raj | Done |  | P3 | 2026-01-19 |  | 2026-02-02 | sprint-Bertha | 20 | 16 | FILTER
Dev | FILTER-10879 | Add custom list (New API) | FILTER-10878 | Story | Sagar Satpute | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 28 | 24 | FILTER | Capitalized-Feature
Dev | FILTER-10885 | Get custom list Details (New API) | FILTER-10878 | Story | Sagar Satpute | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 0 | 8 | FILTER | Capitalized-Feature
Dev | FILTER-10888 | Get custom list Resources (New API) | FILTER-10878 | Story | Sagar Satpute | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 5 | 8 | FILTER | Capitalized-Feature
Dev | FILTER-10891 | Get custom list Association (New API) | FILTER-10878 | Story | Sagar Satpute | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 12 | 8 | FILTER | Capitalized-Feature
Dev | FILTER-10894 | Update Custom List (New API) | FILTER-10878 | Story | Sagar Satpute | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 20 | 16 | FILTER | Capitalized-Feature
Dev | FILTER-10897 | Delete Custom List (New API) | FILTER-10878 | Story | Sagar Satpute | Done |  | P3 | 2025-11-21 |  | 2026-01-21 | sprint-Bertha | 20 | 16 | FILTER | Capitalized-Feature
Dev | FILTER-11088 | Local Custom Lists (FID-specific) | FILTER-11087 | Story | Sagar Satpute | Done |  | P3 | 2025-12-01 |  | 2026-01-21 | sprint-Bertha | 1 | 1 | FILTER | Capitalized-Feature
Dev | FILTER-11091 | Global Custom Lists (Shared Across FIDs) | FILTER-11087 | Story | Sagar Satpute | Done |  | P3 | 2025-12-01 |  | 2026-01-21 | sprint-Bertha | 1 | 1 | FILTER | Capitalized-Feature
Dev | FILTER-11099 | List of custom list (New API) | FILTER-11098 | Story | Sagar Satpute | Done |  | P3 | 2025-12-01 |  | 2026-01-21 | sprint-Bertha | 8 | 8 | FILTER | Capitalized-Feature
Dev | FILTER-11102 | View the details of custom list | FILTER-11098 | Story | Sagar Satpute | Done |  | P3 | 2025-12-01 |  | 2026-01-21 | sprint-Bertha | 0 | 8 | FILTER | Capitalized-Feature
Dev | FILTER-11105 | New Feature ¦ Add URL to the Allow/Block list (Existing API) | FILTER-11098 | Story | Sagar Satpute | Done |  | P3 | 2025-12-01 |  | 2026-01-21 | sprint-Bertha | 24 | 16 | FILTER | Capitalized-Feature
Dev | FILTER-11108 | New Feature ¦ Deleting URL from the Allow/Block list (Existing API) | FILTER-11098 | Story | Sagar Satpute | Done |  | P3 | 2025-12-01 |  | 2026-01-21 | sprint-Bertha | 20 | 16 | FILTER | Capitalized-Feature
Dev | FILTER-11111 | New Feature ¦ Fetching allow/block list of policy | FILTER-11098 | Story | Sagar Satpute | Done |  | P3 | 2025-12-01 |  | 2026-01-21 | sprint-Bertha | 24 | 16 | FILTER | Capitalized-Feature
Dev | FILTER-11526 | SEC-IDP: Upgrade IDP Stack to TLS 1.3 and Resolve Secure Cookie Mismatch | FILTER-11471 | Task | Sagar Satpute | Done |  | P2 | 2025-12-19 |  | 2026-01-19 | sprint-Bertha | 13 | 13 | FILTER
Dev | FILTER-11540 | Fix PHP Fatal Errors in broker.php and Missing Auth Logic post-AL2 Rollout | FILTER-11312 | Escape Defect | Sagar Satpute | Done |  | P2 | 2025-12-21 |  | 2026-01-29 | sprint-Bertha | 8 | 21 | FILTER
Dev | FILTER-11708 | RAILROAD hotfix is handling the deleted user case but isn't handling the disabled user case. | FILTER-11707 | Task | Sagar Satpute | Done |  | P0 | 2026-01-19 |  | 2026-01-20 | sprint-Bertha | 8 | 8 | FILTER
Dev | FILTER-11784 | Dev task - Check if archived users are not getting imported through OU import | FILTER-11783 | Task | Sagar Satpute | Done |  | P0 | 2026-01-23 |  | 2026-01-23 | sprint-Bertha | 5 | 5 | FILTER
Task | FDSE-148 | Checkbox implementation with new design changes | FDSE-54 | Epic | Shailendra Singh | Resolved | Fixed | P3 | 2026-01-19 | 2026-02-01 | 2026-02-02 | sprint-Bertha | 32 | 16 | FDSE | product-filter
Dev | FILTER-11754 | Dev Task - Fix broken UI | FILTER-11753 | Escape Defect | Shailendra Singh | Done |  | P3 | 2026-01-21 |  | 2026-01-28 | sprint-Bertha | 6 | 6 | FILTER
QA | FILTER-11379 | Manual QA Validation for DNS Filtering Conflict on Managed Chromebooks | FILTER-11325 | Story | Surabhi Choudhary | Done |  | P1 | 2025-12-09 |  | 2026-02-02 | sprint-Bertha | 6 | 4 | FILTER
QA | FILTER-11393 | Manual QA Validation for Filter Bypass via chrome://chrome-signin | FILTER-11047 | Escape Defect | Surabhi Choudhary | Done |  | P1 | 2025-12-09 |  | 2026-02-02 | sprint-Bertha | 1 | 4 | FILTER
QA | FILTER-11585 | QA: Image Blurring incorrectly applied to Block Page and missing metadata on search results | FILTER-10624 | Defect | Surabhi Choudhary | Done |  | P3 | 2026-01-05 |  | 2026-01-21 | sprint-Bertha | 4 | 4 | FILTER
QA | FILTER-11664 | Test iOS Image Sidebar Inappropriate Image Leak Fix | FILTER-11644 | Escape Defect | Surabhi Choudhary | Done |  | P1 | 2026-01-15 |  | 2026-02-02 | sprint-Bertha | 5 | 5 | FILTER
QA | FILTER-11704 | Regression Testing on IDP Servers | FILTER-11471 | Task | Surabhi Choudhary | Done |  | P3 | 2026-01-19 |  | 2026-01-20 | sprint-Bertha | 1 | 1 | FILTER
QA | FILTER-11710 | Manual QA Task to validate the SPAC changes | FILTER-11680 | Escape Defect | Surabhi Choudhary | Done |  | P1 | 2026-01-19 |  | 2026-02-02 | sprint-Bertha | 4 | 4 | FILTER
QA | FILTER-11755 | QA task for retesting broken UI | FILTER-11753 | Escape Defect | Surabhi Choudhary | Done |  | P3 | 2026-01-21 |  | 2026-01-29 | sprint-Bertha | 0.5 | 0.5 | FILTER
Task | FDSE-137 | Analysis for timepicker component | FDSE-136 | Epic | Swaroop Chavhan | Resolved | Fixed | P3 | 2025-12-09 | 2026-02-02 | 2026-02-02 | sprint-Bertha | 16 | 16 | FDSE | product-filter
Defect | FILTER-10491 | NewFeatureBug: FID user email can access safety console in current session after deleting the email from admin group |  |  | Vaibhav Kumbhar | Closed without action |  | P2 | 2025-10-24 |  | 2026-03-26 | sprint-Bertha | 5 | 0 | FILTER
Dev | FILTER-11507 | Correct "Allowed" Status in Activity Logs for Blocked Eaglercraft.com Traffic (EXTN) | FILTER-10069 | Escape Defect | Vaibhav Kumbhar | Closed without action |  | P3 | 2025-12-19 |  | 2026-01-23 | sprint-Bertha | 8 | 16 | FILTER
Dev | FILTER-11640 | Extension: Fix Youtube unresticted mode dynamic rules | FILTER-11638 | Escape Defect | Vaibhav Kumbhar | Done |  | P3 | 2026-01-14 |  | 2026-01-19 | sprint-Bertha | 6 | 6 | FILTER
Sub-task | FILTER-11758 | Authorization fixes for FID user | FILTER-10491 | Defect | Vaibhav Kumbhar | Closed |  | P3 | 2026-01-21 |  | 2026-01-23 | sprint-Bertha | 5 | 8 | FILTER

## Not Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Code Review | FILTER-11311 | Review PR for the REL : REL-10348 |  |  | Arun Thakur | Backlog |  | P3 | 2025-12-04 |  | 2026-02-03 | sprint-Bertha | 0 | 0.25 | FILTER
Code Review | FILTER-11327 | Review PR for the REL : REL-10355 |  |  | Arun Thakur | Backlog |  | P3 | 2025-12-05 |  | 2026-02-03 | sprint-Bertha | 0 | 0.25 | FILTER
Code Review | FILTER-11406 | Review PR for the REL : REL-10361 |  |  | Arun Thakur | Backlog |  | P3 | 2025-12-10 |  | 2026-02-03 | sprint-Bertha | 0 | 0 | FILTER
Code Review | FILTER-11063 | Review PR for the REL : REL-10254 |  |  | Harsh Verma | Backlog |  | P3 | 2025-11-28 |  | 2026-02-03 | sprint-Bertha | 0 | 0 | FILTER
Code Review | FILTER-11427 | Review PR for the REL : REL-10316 |  |  | Harsh Verma | Backlog |  | P3 | 2025-12-11 |  | 2026-02-03 | sprint-Bertha | 0 | 0 | FILTER
Code Review | FILTER-11303 | Review PR for the REL : REL-10345 |  |  | Pratik Tiwari | Backlog |  | P3 | 2025-12-04 |  | 2026-02-03 | sprint-Bertha | 0 | 0 | FILTER
Code Review | FILTER-11310 | Review PR for the REL : REL-10321 |  |  | Pratik Tiwari | Backlog |  | P3 | 2025-12-04 |  | 2026-02-03 | sprint-Bertha | 0 | 0 | FILTER
Code Review | FILTER-11404 | Review PR for the REL : REL-10361 |  |  | Pratik Tiwari | Backlog |  | P3 | 2025-12-10 |  | 2026-02-03 | sprint-Bertha | 0 | 0 | FILTER
Code Review | FILTER-11064 | Review PR for the REL : REL-10254 |  |  | Swaroop Chavhan | Backlog |  | P3 | 2025-11-28 |  | 2026-02-03 | sprint-Bertha | 0 | 0 | FILTER
Code Review | FILTER-11301 | Review PR for the REL : REL-10345 |  |  | Swaroop Chavhan | Backlog |  | P3 | 2025-12-04 |  | 2026-02-03 | sprint-Bertha | 0 | 0 | FILTER
Code Review | FILTER-11372 | Review PR for the REL : REL-10198 |  |  | Swaroop Chavhan | Backlog |  | P3 | 2025-12-09 |  | 2026-02-03 | sprint-Bertha | 0 | 0 | FILTER
Code Review | FILTER-11405 | Review PR for the REL : REL-10361 |  |  | Swaroop Chavhan | Backlog |  | P3 | 2025-12-10 |  | 2026-02-03 | sprint-Bertha | 0 | 0 | FILTER

## Removed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Task | FILTER-11697 | Extension of FILTER-11605 |  |  | Harsh Verma | In Progress |  | P3 | 2026-01-19 |  | 2026-04-27 | sprint-Bertha | 0 | 24 | FILTER | unplanned-sprint |  | YES
Task | FDSE-145 | Side Drawer Design Changes | FDSE-109 | Epic | Harshada Kude | Open |  | P3 | 2026-01-16 |  | 2026-01-20 | sprint-Bertha | 0 | 8 | FDSE |  |  | YES
Task | FILTER-11713 | [sprox] Securly cookie creation logic implementation | FILTER-8230 | Epic | Ashish Temurnikar | Closed |  | P3 | 2026-01-19 |  | 2026-03-05 | sprint-Bertha | 20 | 8 | FILTER
Defect | FILTER-9299 | NewFeatureBug: SPAC/DNS. Posts on X.com are getting logged twice. One as post and One as search. |  |  | Ashish Temurnikar | Reopened | Fixed | P2 | 2025-07-23 | 2025-07-25 | 2026-03-02 | sprint-Bertha | 18 | 8 | FILTER
Task | FDSE-142 | Dependabot issue fixes |  |  | Harsh Verma | Closed |  | P3 | 2026-01-05 |  | 2026-03-03 | sprint-Bertha | 5 | 8 | FDSE | product-filter
Task | FILTER-10900 | [Dependabot issues]Upgrade jspdf-autotable npm library to latest version (5.0) |  |  | Harshada Kude | Closed |  | P3 | 2025-11-21 |  | 2026-03-03 | sprint-Bertha | 16 | 0 | FILTER
Task | FILTER-11711 | [sprox] Changes certificate logic to be backward compatible with existing redis DB24 | FILTER-8230 | Epic | Pratik Tiwari | Closed | Fixed | P2 | 2026-01-19 | 2026-02-10 | 2026-03-03 | sprint-Bertha | 12 | 12 | FILTER
Task | FILTER-9275 | [SPAC] Moving cluster & proxy URL to globals |  |  | Ravi Raj | Closed |  | P2 | 2025-07-22 |  | 2026-03-03 | sprint-Bertha | 20 | 12 | FILTER
Defect | FILTER-11581 | NewFeatureBug: SupportTool Customlist API. Name field can be saved with spaces at start and end. Add/Update |  |  | Sagar Satpute | Closed without action |  | P3 | 2026-01-05 |  | 2026-02-05 | sprint-Bertha | 0 | 0 | FILTER | unplanned-sprint
Task | FDSE-112 | Implementation of Button bars as per the design | FDSE-111 | Epic | Shailendra Singh | Resolved | Fixed | P3 | 2025-11-20 | 2026-02-09 | 2026-02-09 | sprint-Bertha | 24 | 20 | FDSE | product-filter
Task | FDSE-123 | Simple search component implementation without chip and without auto-complete | FDSE-122 | Epic | Shailendra Singh | Resolved |  | P3 | 2025-12-04 |  | 2026-02-11 | sprint-Bertha | 4 | 24 | FDSE | Capitalized-Feature, product-filter
Task | FDSE-126 | Analysis - Search without chip but with auto-complete component implementation | FDSE-174 | Epic | Swaroop Chavhan | Resolved |  | P3 | 2025-12-04 |  | 2026-04-15 | sprint-Bertha | 12 | 12 | FDSE | Capitalized-Feature, product-filter

## P1 Escalation
P1 Escalation — FILTER · sprint-Bertha (2026-01-20 → 2026-02-02)
sprint-Bertha tickets where Issue Type = Escape Defect AND Priority = P1 AND summary contains 'P1 Escalation' (regardless of bucket). Total = 13.
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Bucket
Escape Defect | FILTER-11610 | P1 Escalation-CORs Errors at BlueBeam and Boomerang S3 Amazon domains ¦ St. Vrain |  |  | Ramani Cheruvu | In Progress | Fixed | P1 | 2026-01-08 | 2026-01-27 | 2026-04-27 | sprint-Bertha | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_reopened, p1escalation, unplanned-sprint, zendesk_enterprise |  | Removed
Escape Defect | FILTER-10237 | P1 escalation-Crextn-specific Bypass using upgraded credentials |  |  | Ashish Modak | Release in Progress | Fixed | P1 | 2025-09-26 | 2025-11-20 | 2026-02-03 | sprint-Bertha | 6 | 6 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_escalated, jira_in_progress, p1escalation, unplanned-sprint |  | Completed
Escape Defect | FILTER-7871 | P1 Escalation-Shortcut SmartPAC bypass; --user-agent ¦ Seattleschools |  |  | Ashish Temurnikar | Closed | Expected behavior | P1 | 2025-04-11 | 2026-01-19 | 2026-02-09 | sprint-Bertha | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_closed_notify, jira_escalated, jira_in_progress, jira_open, jira_reopened, p1escalation, unplanned-sprint |  | Completed
Escape Defect | FILTER-8535 | P1 Escalation-Google search drag and drop bypass |  |  | Pratik Tiwari | Closed | Cannot Reproduce | P1 | 2025-05-30 | 2026-02-26 | 2026-02-26 | sprint-Bertha | 24 | 8 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_escalated, jira_qa_verified, p1escalation, unplanned-sprint |  | Completed
Escape Defect | FILTER-10034 | P1 Escalation-YouTube blocked while doing a Google Search |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-09-12 | 2025-11-24 | 2026-04-16 | sprint-Bertha | 5 | 5 | FILTER | jira_added, jira_closed_notify, jira_confirmation, jira_done, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_p3, jira_qa_verified, jira_reopened, p1escalation, unplanned-sprint, zendesk_org_at_risk |  | Removed
Escape Defect | FILTER-10392 | P1 Escalation-YouTube Videos play in Gmail even when blocked in policy ¦ Downingtown |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-10-10 | 2026-02-10 | 2026-04-07 | sprint-Bertha | 16 | 16 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_closed_notify, jira_escalated, jira_in_progress, jira_qa_verified, jira_reopened, p1escalation, unplanned-sprint |  | Removed
Escape Defect | FILTER-11047 | P1 Escalation-Filter bypass using Chrome://chrome-signin ¦ Edmonds |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-11-26 | 2026-01-27 | 2026-04-20 | sprint-Bertha | 17 | 0 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_closed_notify, jira_done, jira_escalated, jira_in_progress, jira_open, jira_qa_verified, p1escalation |  | Completed
Escape Defect | FILTER-11443 | P1 Escalation-Chrome extension bypass using Omada DNS |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-12-15 | 2026-01-21 | 2026-04-07 | sprint-Bertha | 16 | 16 | FILTER | jira_added, jira_closed_notify, jira_done, jira_escalated, jira_p1, zendesk_enterprise |  | Removed
Escape Defect | FILTER-11557 | P1 Escalation-Copy & Paste movie script into search bar breaks extension |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-12-22 | 2026-01-16 | 2026-04-07 | sprint-Bertha | 10 | 12 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_done, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_qa_verified, jira_reopened, p1escalation, unplanned-sprint |  | Completed
Escape Defect | FILTER-11644 | P1 Escalation-Image side bar is leaking inappropriate images on iOS |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-01-14 | 2026-01-29 | 2026-04-06 | sprint-Bertha | 17 | 0 | FILTER | jira_added, jira_closed_notify, jira_done, jira_escalated, jira_p1, zendesk_enterprise |  | Completed
Escape Defect | FILTER-11654 | P1 Escalation-Crextn blocking issue with Google Workspace apps | FILTER-4326 | Epic | Shashank Tiwari | QA Verified | Done | P1 | 2026-01-15 | 2026-04-06 | 2026-04-28 | sprint-Bertha | 0 | 0 | FILTER | jira_added, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_qa_verified, jira_resolved |  | Removed
Escape Defect | FILTER-11680 | P1 Escalation-[PageScan] SPAC Changes for better coverage |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-01-16 | 2026-01-21 | 2026-03-09 | sprint-Bertha | 14 | 0 | FILTER | Reverified-2026, p1escalation, unplanned-sprint |  | Completed
Escape Defect | FILTER-11777 | P1 Escalation-Google search overloading/breaking chrome extension |  |  | Shashank Tiwari | Closed | Duplicate | P1 | 2026-01-22 | 2026-01-27 | 2026-02-10 | sprint-Bertha | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_closed_notify, jira_escalated, p1escalation, unplanned-sprint |  | Completed