## Capacity vs Delivery
Capacity vs Delivery — FILTER · sprint-Cristobal (Tue 03 Feb → Mon 16 Feb 2026)
Team Composition (per Securly-PjM-Skills.md Part 2 — Filter India roster). Inactive members for this sprint window are shaded grey with a roster note.
Name | Role | Function / Split | Allocation (FTE) | Seniority | Employment | Notes
Shashank Tiwari | Project Manager | PM / Delivery | 0 | Lead | FTE | Not counted in delivery capacity
Harsh Verma | FE | FrontEnd Architect (Angular) | 1 | Senior | FTE
Arun Thakur | FE + Ext | Angular / Extension | 1 | Medium | FTE
Harshada Kude | FE | Angular | 1 | Junior | FTE
Shailendra Singh | FE | Angular | 1 | Medium | FTE
Swaroop Chavhan | FE + Ext | Angular / Extension | 1 | Medium | FTE
Ashish Modak | BE Architect | Extension / Go / PHP | 1 | Senior | FTE
Prateek Fotedar | BE (www) | Go / PHP | 1 | Senior | FTE
Sagar Satpute | BE (www) | Go / PHP | 1 | Medium | FTE
Vaibhav Kumbhar | BE | Go / PHP | 1 | Medium | FTE
Ashish Temurnikar | BE | DNS / SPAC / Squid / Rust | 1 | Senior | FTE
Ravi Raj | BE | DNS / SPAC / Squid / Rust | 1 | Medium | FTE
Pratik Tiwari | BE + Ext | Extension / Go / Rust | 1 | Senior | FTE
Altamash Heroli | QA | Pri. Manual QA | 1 | Senior | FTE
Surabhi Choudhary | QA | Sr. Manual QA | 1 | Senior | FTE
Ayesha Kamde | QA | Manual QA | 1 | Junior | FTE
Amol Mithari | Auto QA Lead | Team Lead — Auto QA / SDET | 0 | Lead | FTE | Joined team on 20-Feb-2026 — not part of this sprint
Amit Shete | Auto QA | Pri. SDET | 1 | Senior | FTE
Rachit Mishra | Auto QA | SDET | 1 | Junior | FTE
Total FILTER allocation |  |  |  | FTE-equivalent heads available to FILTER
Capacity Parameters (yellow cells are inputs — re-run the script after edits)
Parameter | Value | Description
Sprint length (working days) | 10 | FILTER 15-day sprint Tue → Mon. sprint-Cristobal = 2026-02-03 → 2026-02-16.
Company holidays in sprint | 1 | India calendar 2026 — 16-Feb: Securly Wellness Day
Effective working days (sprint − company holidays) |  | Used as the per-person calendar for availability
Hours per working day (nominal) | 8 | Standard working day
Focus factor (productive fraction) | 0.9 | 90% — what SLT expects (sprint-analysis default)
Misc buffer (meetings, scrums, code review, …) | 20% | 20% blanket reservation deducted from Available to get Net Available
Effective hours per FTE per sprint
Allocated FTE on FILTER (active this sprint) | 17 | Headcount actually working this sprint (excludes joiners/leavers outside window)
Ideal capacity for the sprint (hrs)
Issue scope (Jira projects) | FILTER, PTGM, FDSE | Tickets pulled with `project in (FILTER, PTGM, FDSE) AND sprint = …` — FDSE: 4 · FILTER: 218 · PTGM: 7
Capacity vs Actual Delivery — sprint-Cristobal
Metric | Hours | % of Ideal | Rating | Notes
Actual Availability |  |  |  | Sum of per-person availability (Ideal − leaves)
Misc Buffer (20%) |  |  |  | Reserved for meetings, scrums, code reviews
Net Available (Available − Misc Buffer) |  |  |  | Realistic delivery capacity — used as the denominator for Completed %
Completed |  |  |  | Sum of in-sprint timeSpent (Completed bucket)
Not Completed (Spillover) |  |  |  | Original estimate for spillover (carried into next sprint)
Removed |  |  |  | Original estimate for issues removed mid-sprint
Completed by Priority
Tickets (parents) = unique parent items (Story / Task / Defect / Escape Defect) — subtasks roll up to their parent so 1 parent + 3 subtasks = 1 ticket. Tickets (incl. subtasks) = raw record count incl. every Dev / QA / Automation / Review / Test Case Creation / Debug subtask. Hours = sum across parents and subtasks; matches the core-team Completed hours on the Per-person Delivery sheet.
Priority | Tickets (parents) | Tickets (incl. subtasks) | Hours (incl. subtasks) | % of Completed Hrs | % of Tickets (parents) | Notes
P1 | 12 | 25 | 122 |  |  | P1 — high priority (see P1 Escalation tab for escalations)
P2 | 20 | 43 | 208.5 |  |  | Major
P3 | 29 | 51 | 393.5 |  |  | Standard
TOTAL | 61 | 119 | 724 | 100% | 100% | Sum of Completed bucket (core roster)
Sprint Completion (spillover = Not Completed)
Metric | Tickets | Planned Hrs (OE) | % by Tickets | % by Hrs | Notes
Completed (closed in sprint) | 119 | 789.5 |  |  | In-sprint deliverables
Spillover (not completed → carry-over) | 1 | 0 |  |  | Original estimate carried to next sprint
Removed (mid-sprint scope cut) | 5 | 58 | — | — | Excluded from completion ratio (out of scope)
Mid-sprint additions (core) | 13 |  | — | — | Late-arriving work (Jira issueKeysAddedDuringSprint)
Sprint completion rate (tickets) | 99.17% | On Target | Completed ÷ (Completed + Spillover)
Sprint completion rate (planned hrs) | 100% | On Target | Σ OE Completed ÷ Σ OE (Completed + Spillover)
Planned completion rate (tickets, excludes mid-sprint adds) | 99.07% | On Target | Originally-committed tickets only
Planned completion rate (planned hrs, excludes mid-sprint adds) | 100% | On Target | Originally-committed planned hours only
P1 Escalation snapshot
6 ticket(s) in sprint-Cristobal match 'P1 Escalation' in the title — 5 closed, 1 still open. See the 'P1 Escalation' tab.
Mid-sprint additions snapshot
13 ticket(s) were added to sprint-Cristobal after it started (issueKeysAddedDuringSprint) — Completed 12, Spillover 0, Removed 1. Highlighted in amber on every detail sheet (Added Mid-Sprint = YES).
Assumptions & caveats
• Sprint window from Jira (/rest/agile/1.0/sprint/5131): 2026-02-03 → 2026-02-16 (10 Mon–Fri working days). Refresh with fetch_filter_sprint_meta.py + fetch_filter_sprint_issues.py.
• Issues pulled from FILTER + PTGM + FDSE (project-scope expanded for the India scrum team's split across the three products).
• Date-aware roster: Amol Mithari joined 20-Feb-2026; Rachit Mishra's last day was 20-Feb-2026. Inactive members for this sprint window are shaded grey in the Team Composition table and excluded from per-person availability + delivery.
• Available (hrs) = (effective working days − leave days) × 8 × focus factor, where effective working days = sprint working days − company holidays falling inside the sprint − days outside the person's employment window. Per-person Delivery shows leave days in Column G to explain the delta from a full sprint.
• Net Available = Available − 20% Misc Buffer for meetings, scrums, code review, etc. Completed/Not Completed/Removed % of capacity use Net Available as the denominator.
• Time Spent on Completed sheet uses the in-sprint hybrid worklog rule (sprint-analysis.md): single-sprint = timespent; multi-sprint = SUM of worklogs whose started ∈ [sprintStart, sprintEnd].
• Not Completed and Removed totals use Original Estimate.
• Removed list comes from the Sprint Report puntedIssues (greenhopper API).
• Core roster only: assignees outside Securly-PjM-Skills.md Part 2 are dropped from per-person + detail sheets.
• P1 Escalation tab is filtered to Issue Type = Escape Defect AND Priority = P1 AND title contains 'P1 Escalation'.
• Completed by Priority — Tickets (parents) rolls subtasks up to their parent (each work item counted once at its parent priority); Tickets (incl. subtasks) shows the raw record count for comparison. The Hours column sums every record (parent + subtasks) and matches the core-team Completed total.
• Spillover = Not Completed bucket (tickets carried into the next sprint).
• Sprint completion rate uses Completed ÷ (Completed + Spillover); Removed tickets are excluded (treated as scope cut). 'Planned' rate also excludes mid-sprint additions.
• All detail sheets (Completed, Not Completed, Removed) highlight tickets added after sprint start (Jira sprint-report issueKeysAddedDuringSprint) in amber, with an 'Added Mid-Sprint = YES' tag column.
• Ratings: ≥85% On Target (green), 70–85% Below Target (amber), <70% Significantly Below (red).

## Per-person Delivery
Assignee | Completed (hrs) | Not Completed (hrs) | Removed (hrs) | Efficiency | Available (hrs) | Leave Days (sprint) | Misc Buffer 20% (hrs) | Net Available (hrs)
Harsh Verma | 56 | 0 | 32 |  | 57.6 | 1
Arun Thakur | 16.5 | 0 | 2 |  | 64.8 | 0
Harshada Kude | 56 | 0 | 16 |  | 64.8 | 0
Shailendra Singh | 46 | 0 | 0 |  | 57.6 | 1
Swaroop Chavhan | 40 | 0 | 0 |  | 64.8 | 0
Ashish Modak | 61 | 0 | 0 |  | 64.8 | 0
Prateek Fotedar | 23.5 | 0 | 0 |  | 57.6 | 1
Sagar Satpute | 63 | 0 | 0 |  | 64.8 | 0
Vaibhav Kumbhar | 111 | 0 | 0 |  | 64.8 | 0
Ashish Temurnikar | 17 | 0 | 8 |  | 64.8 | 0
Ravi Raj | 64 | 0 | 0 |  | 57.6 | 1
Pratik Tiwari | 44 | 0 | 0 |  | 64.8 | 0
Altamash Heroli | 27 | 0 | 0 |  | 57.6 | 1
Surabhi Choudhary | 16 | 0 | 0 |  | 64.8 | 0
Ayesha Kamde | 29.5 | 0 | 0 |  | 57.6 | 1
Amit Shete | 4 | 0 | 0 |  | 64.8 | 0
Rachit Mishra | 49.5 | 0 | 0 |  | 57.6 | 1
TOTAL

## Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Escape Defect | FILTER-11909 | A large number of sites have been recategorised as Network Misuse after AWS disruption. |  |  | Ashish Modak | Closed | Won't Fix | P2 | 2026-01-30 | 2026-02-10 | 2026-02-10 | sprint-Cristobal | 8 | 8 | FILTER | Reverified-2026, jira_added, jira_escalated, jira_in_progress, unplanned-sprint, zendesk_org_at_risk |  | YES
Task | FILTER-11962 | Change Blocked APIs code to not work for Categorized Queue and allow those APIs |  |  | Ashish Modak | Closed |  | P1 | 2026-02-04 |  | 2026-02-08 | sprint-Cristobal | 12 | 12 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12016 | POC for extension api fortification |  |  | Ashish Modak | Closed |  | P1 | 2026-02-11 |  | 2026-03-10 | sprint-Cristobal | 24 | 24 | FILTER | 2026-Tech-debt, unplanned-sprint |  | YES
Debug | FILTER-11987 | [RTQA4] SPAC traffic analysis for ddos attack |  |  | Ashish Temurnikar | Closed |  | P3 | 2026-02-08 |  | 2026-03-03 | sprint-Cristobal | 6 | 6 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-11988 | [RTQA5] Restrict Squid Instance traffic from LB only |  |  | Ashish Temurnikar | Closed |  | P3 | 2026-02-09 |  | 2026-03-03 | sprint-Cristobal | 8 | 8 | FILTER | unplanned-sprint |  | YES
Task | FILTER-11898 | Helping classroom team for PR review and Technical discussions |  |  | Harsh Verma | Closed |  | P3 | 2026-01-30 |  | 2026-03-03 | sprint-Cristobal | 3 | 4 | FILTER | unplanned-sprint |  | YES
Task | FILTER-11899 | Helping Home Team for the overall architecture of Parent Portal design Revamp and and AI Chat for their dashobard requirement |  |  | Harsh Verma | Closed |  | P3 | 2026-01-30 |  | 2026-03-03 | sprint-Cristobal | 24 | 24 | FILTER | unplanned-sprint |  | YES
Task | FILTER-11919 | Continuation task on - FILTER-11698 - Do a POC on CMS and its consumption in different products |  |  | Harsh Verma | Closed |  | P3 | 2026-02-02 |  | 2026-03-03 | sprint-Cristobal | 24 | 16 | FILTER |  |  | YES
Task | FILTER-11740 | Phase 2: Fixing Dependabot Issues for Support tool |  |  | Harshada Kude | Closed | Done | P3 | 2026-01-20 | 2026-02-12 | 2026-03-03 | sprint-Cristobal | 24 | 24 | FILTER |  |  | YES
Story | FILTER-11922 | [sprox] Initial TC setup & adding to CI pipeline |  |  | Pratik Tiwari | Closed without action |  | P3 | 2026-02-02 |  | 2026-02-17 | sprint-Cristobal | 10 | 10 | FILTER |  |  | YES
Task | FILTER-12049 | Tracking ticket for AICHAT |  |  | Swaroop Chavhan | Closed |  | P3 | 2026-02-13 |  | 2026-04-17 | sprint-Cristobal | 20 | 20 | FILTER | unplanned-sprint |  | YES
Task | FILTER-10521 | Cleanup MainDomainCategorizationEnabled from www-filter code, as it is deprecated. |  |  | Vaibhav Kumbhar | Closed | Done | P3 | 2025-10-28 | 2026-02-06 | 2026-03-03 | sprint-Cristobal | 0 | 2 | FILTER |  |  | YES
QA | FILTER-11582 | QA Task - Regression Testing - Moving cluster & proxy URL to globals | FILTER-9275 | Task | Altamash Heroli | Closed without action |  | P2 | 2026-01-05 |  | 2026-02-05 | sprint-Cristobal | 0 | 0 | FILTER
QA | FILTER-11587 | QA: Confirmation popup for unsaved Image Blur settings is not translated (French/Spanish) | FILTER-10925 | Defect | Altamash Heroli | QA Verified |  | P3 | 2026-01-05 |  | 2026-02-05 | sprint-Cristobal | 1 | 1 | FILTER
QA | FILTER-11651 | Test Cron Job for Custom List Sync Error Recovery | FILTER-11649 | Task | Altamash Heroli | QA Verified |  | P3 | 2026-01-15 |  | 2026-02-13 | sprint-Cristobal | 4 | 24 | FILTER | Capitalized-Feature
QA | FILTER-11670 | Test Fix for Unable to Remove ChatGPT Entry from Filter UI | FILTER-11571 | Task | Altamash Heroli | QA Verified |  | P2 | 2026-01-15 |  | 2026-02-05 | sprint-Cristobal | 3 | 2 | FILTER
QA | FILTER-11850 | HACKERONE - Verify Fix for IDOR Vulnerabilities - IP Allowlist Enumeration & Deletion | FILTER-10346 | Defect | Altamash Heroli | QA Verified |  | P2 | 2026-01-29 |  | 2026-02-11 | sprint-Cristobal | 5 | 10 | FILTER
QA | FILTER-11858 | Verify Clone CustomList API validates "usage" field correctly | FILTER-11789 | Defect | Altamash Heroli | Closed without action |  | P2 | 2026-01-29 |  | 2026-03-03 | sprint-Cristobal | 0 | 2 | FILTER
QA | FILTER-11879 | HACKERONE - Verify fix for IDOR vulnerability in getScheduledReportList - Cross-FID authorization | FILTER-10476 | Defect | Altamash Heroli | QA Verified |  | P3 | 2026-01-29 |  | 2026-02-11 | sprint-Cristobal | 4 | 3 | FILTER
QA | FILTER-11912 | Verify fix for Invalid student_email parameter in postMonitoringNotice API | FILTER-11910 | Task | Altamash Heroli | Closed without action |  | P1 | 2026-01-30 |  | 2026-02-04 | sprint-Cristobal | 0 | 0 | FILTER
QA | FILTER-11916 | Manual QA for Lookup tool uncategorized block changes | FILTER-11577 | Task | Altamash Heroli | QA Verified |  | P3 | 2026-02-02 |  | 2026-02-13 | sprint-Cristobal | 3 | 4 | FILTER
QA | FILTER-11928 | Verify deleted users are not logged for SmartPAC and DNS (user verification for broker) | FILTER-11926 | Defect | Altamash Heroli | Closed without action |  | P1 | 2026-02-03 |  | 2026-02-09 | sprint-Cristobal | 0 | 0 | FILTER
QA | FILTER-11956 | QA task to validate Cross-FID Bypass - Admin from one FID can access/modify custom lists of another FID | FILTER-11813 | Defect | Altamash Heroli | QA Verified |  | P3 | 2026-02-04 |  | 2026-02-13 | sprint-Cristobal | 7 | 5 | FILTER | Capitalized-Feature
QA | FILTER-11981 | Validate changes on Prod | FILTER-11962 | Task | Altamash Heroli | Closed without action |  | P1 | 2026-02-06 |  | 2026-02-08 | sprint-Cristobal | 0 | 0 | FILTER
Automation | FILTER-11261 | Automated E2E Test: Validate Datepicker Accessibility (Keyboard Focus) and Styling | FILTER-11114 | Story | Amit Shete | Closed without action |  | P3 | 2025-12-03 |  | 2026-01-15 | sprint-Cristobal | 0 | 0 | FILTER
Automation | FILTER-11859 | Add test coverage for Clone CustomList API usage field validation | FILTER-11789 | Defect | Amit Shete | Done |  | P2 | 2026-01-29 |  | 2026-03-16 | sprint-Cristobal | 4 | 4 | FILTER
Defect | FILTER-10630 | NewFeatureBug: JS extn: Empty class images are getting blurred |  |  | Arun Thakur | RELEASED TO PROD | Fixed | P3 | 2025-11-05 | 2025-11-06 | 2026-03-03 | sprint-Cristobal | 8 | 2 | FILTER | Image-Blur-JavaScript, unplanned-sprint
Defect | FILTER-10643 | NewFeatureBug: JS extn: (NotPresentInPreviousTag) Blurred images do not have NSFW debug callout |  |  | Arun Thakur | RELEASED TO PROD | Fixed | P3 | 2025-11-06 | 2025-11-06 | 2026-03-03 | sprint-Cristobal | 0.5 | 0.5 | FILTER | Image-Blur-JavaScript, NotPresentInPreviousTags
Dev | FILTER-10953 | Fix Timestamp Format and Search Term Quotes in Blocked Search Email Alert (X.com/Go Broker) | FILTER-9912 | Defect | Arun Thakur | Closed without action |  | P2 | 2025-11-24 |  | 2026-02-11 | sprint-Cristobal | 2 | 2 | FILTER
Dev | FILTER-10956 | Fix Loss of Column Sorting Options and Selected Columns After Filtering in Mock Session UI | FILTER-9846 | Defect | Arun Thakur | Closed without action |  | P3 | 2025-11-24 |  | 2026-02-11 | sprint-Cristobal | 0 | 6 | FILTER
Dev | FILTER-10975 | Blocked Search Term Not Bold in Email Body (Filter Alert Emails) | FILTER-9908 | Defect | Arun Thakur | Closed without action |  | P3 | 2025-11-24 |  | 2026-02-06 | sprint-Cristobal | 0 | 2 | FILTER
Dev | FILTER-11486 | Fix JS Extension: Pinterest Images Failing to Blur and Remaining Clickable | FILTER-10760 | Defect | Arun Thakur | Done |  | P2 | 2025-12-19 |  | 2026-02-06 | sprint-Cristobal | 6 | 6 | FILTER
Dev | FILTER-11966 | Dev Changes | FILTER-11962 | Task | Ashish Modak | Closed without action |  | P1 | 2026-02-05 |  | 2026-02-06 | sprint-Cristobal | 1 | 1 | FILTER
Dev | FILTER-12385 | Dev Task to Analysis reopen issue for FITLER-10034 | FILTER-10034 | Escape Defect | Ashish Modak | Done |  | P1 | 2026-03-09 |  | 2026-03-13 | sprint-Cristobal | 16 | 16 | FILTER
Dev | FILTER-11927 | Extend user verification for broker to SmartPAC and DNS filtering methods | FILTER-11926 | Defect | Ashish Temurnikar | Closed without action |  | P1 | 2026-02-03 |  | 2026-02-09 | sprint-Cristobal | 0 | 0 | FILTER
Dev | FILTER-11939 | Pagescan logs not received for uncategorized site when no bit is set | FILTER-11921 | Defect | Ashish Temurnikar | Closed without action |  | P2 | 2026-02-03 |  | 2026-02-08 | sprint-Cristobal | 3 | 3 | FILTER
QA | FILTER-10955 | Manual QA Validation for X.com Blocked Search Email Data Accuracy (Timestamp & Quotes) | FILTER-9912 | Defect | Ayesha Kamde | Closed without action |  | P2 | 2025-11-24 |  | 2026-02-17 | sprint-Cristobal | 0 | 2 | FILTER
QA | FILTER-10958 | Manual QA Validation for Column Sorter Options and Selected Column Persistence in Mock Session | FILTER-9846 | Defect | Ayesha Kamde | Closed without action |  | P3 | 2025-11-24 |  | 2026-02-17 | sprint-Cristobal | 0 | 1 | FILTER
QA | FILTER-10977 | Manual QA Validation for Font Weight Consistency in Blocked Search Alert Emails | FILTER-9908 | Defect | Ayesha Kamde | Closed without action |  | P3 | 2025-11-24 |  | 2026-02-17 | sprint-Cristobal | 0 | 3 | FILTER
QA | FILTER-11155 | Manual QA Validation for Filter Activity Log Category Mismatch | FILTER-10375 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2025-12-02 |  | 2026-01-30 | sprint-Cristobal | 6 | 7 | FILTER
QA | FILTER-11165 | Manual QA Validation for Filter Activities Column Order Reset Failure | FILTER-10489 | Escape Defect | Ayesha Kamde | Closed without action |  | P3 | 2025-12-02 |  | 2026-02-04 | sprint-Cristobal | 1 | 2 | FILTER
QA | FILTER-11227 | Manual QA Validation for False Positive Block on Google Search Embeds (CRXTN) | FILTER-10034 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2025-12-03 |  | 2026-02-04 | sprint-Cristobal | 5 | 5 | FILTER
QA | FILTER-11257 | Manual QA Validation for "Uncategorized" Sort Filter Failure | FILTER-4843 | Support Escalation (OLD) | Ayesha Kamde | Done |  | P3 | 2025-12-03 |  | 2026-02-09 | sprint-Cristobal | 2 | 2 | FILTER
QA | FILTER-11262 | Manual QA Validation for Datepicker Accessibility and Styling Regression | FILTER-11114 | Story | Ayesha Kamde | Done |  | P3 | 2025-12-03 |  | 2026-02-13 | sprint-Cristobal | 5.5 | 3 | FILTER
QA | FILTER-11396 | Manual QA Validation for YouTube Video Playback Bypass within Gmail | FILTER-10392 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2025-12-09 |  | 2026-02-04 | sprint-Cristobal | 2 | 4 | FILTER
QA | FILTER-11488 | Manual QA Validation: Pinterest.com Image Blur and Interaction Lock | FILTER-10760 | Defect | Ayesha Kamde | Done |  | P2 | 2025-12-19 |  | 2026-02-13 | sprint-Cristobal | 2 | 2 | FILTER
QA | FILTER-12419 | QA task to test reopen issue for FILTER-10034 | FILTER-10034 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2026-03-12 |  | 2026-03-13 | sprint-Cristobal | 6 | 6 | FILTER
Task | FDSE-142 | Dependabot issue fixes |  |  | Harsh Verma | Closed |  | P3 | 2026-01-05 |  | 2026-03-03 | sprint-Cristobal | 5 | 8 | FDSE | product-filter
Task | FILTER-10900 | [Dependabot issues]Upgrade jspdf-autotable npm library to latest version (5.0) |  |  | Harshada Kude | Closed |  | P3 | 2025-11-21 |  | 2026-03-03 | sprint-Cristobal | 16 | 0 | FILTER
Dev | FILTER-11706 | Phase 1: Common package.json for Filter, Aware, Support-tool, cases | FILTER-10900 | Task | Harshada Kude | Done |  | P3 | 2026-01-19 |  | 2026-02-09 | sprint-Cristobal | 16 | 16 | FILTER | unplanned-sprint
Dev | FILTER-11933 | Phase 2: Fixing Dependabot Issues for support tool | FILTER-11740 | Task | Harshada Kude | Done |  | P3 | 2026-02-03 |  | 2026-02-12 | sprint-Cristobal | 0 | 0 | FILTER
Dev | FILTER-11520 | Update SIS Data Readiness Screen to Display Sync Data for Product-Less FIDs | FILTER-9605 | Task | Prateek Fotedar | Closed without action |  | P1 | 2025-12-19 |  | 2026-02-11 | sprint-Cristobal | 8 | 8 | FILTER
Dev | FILTER-11811 | Update destination cluster mapping in support tool | FILTER-11649 | Task | Prateek Fotedar | Done |  | P3 | 2026-01-28 |  | 2026-01-28 | sprint-Cristobal | 1.5 | 1.5 | FILTER | Capitalized-Feature
Dev | FILTER-11824 | Dev task for JS Extension changes | FILTER-10034 | Escape Defect | Prateek Fotedar | Closed without action |  | P1 | 2026-01-29 |  | 2026-03-11 | sprint-Cristobal | 8 | 8 | FILTER
Dev | FILTER-11837 | SIS Data Readiness Report - Download fails for PDF and CSV formats | FILTER-11826 | Defect | Prateek Fotedar | Done |  | P1 | 2026-01-29 |  | 2026-02-11 | sprint-Cristobal | 6 | 6 | FILTER
Dev | FILTER-11394 | Fix CKEC Bypass: YouTube Videos Play Unfiltered Inside mail.google.com | FILTER-10392 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2025-12-09 |  | 2026-01-11 | sprint-Cristobal | 0 | 16 | FILTER
Dev | FILTER-11446 | Fix CKEC Bypass: Prevent Filtering Exploit by Changing Chromebook DNS to Omada DNS | FILTER-11443 | Escape Defect | Pratik Tiwari | Closed without action |  | P1 | 2025-12-15 |  | 2026-01-23 | sprint-Cristobal | 0 | 0 | FILTER
Task | FILTER-11711 | [sprox] Changes certificate logic to be backward compatible with existing redis DB24 | FILTER-8230 | Epic | Pratik Tiwari | Closed | Fixed | P2 | 2026-01-19 | 2026-02-10 | 2026-03-03 | sprint-Cristobal | 12 | 12 | FILTER
Dev | FILTER-11724 | [sprox] Changes certificate logic to be backward compatible with existing redis DB24 | FILTER-11711 | Task | Pratik Tiwari | Done |  | P3 | 2026-01-19 |  | 2026-02-17 | sprint-Cristobal | 12 | 12 | FILTER
Dev | FILTER-11923 | [sprox] Initial TC setup & adding to CI pipeline | FILTER-11922 | Story | Pratik Tiwari | Done |  | P3 | 2026-02-02 |  | 2026-02-17 | sprint-Cristobal | 10 | 10 | FILTER
Automation | FILTER-10954 | Automated E2E Test for X.com Blocked Search Email Content Validation | FILTER-9912 | Defect | Rachit Mishra | Done |  | P2 | 2025-11-24 |  | 2026-02-10 | sprint-Cristobal | 6.5 | 6 | FILTER
Automation | FILTER-10957 | Automated E2E Test for Column Visibility and Sorter Option Persistence on Filter Change | FILTER-9846 | Defect | Rachit Mishra | Done |  | P3 | 2025-11-24 |  | 2026-02-17 | sprint-Cristobal | 5.5 | 4.5 | FILTER
Automation | FILTER-10976 | Automated E2E Test for Email Template: Blocked Search Term Bold Assertion | FILTER-9908 | Defect | Rachit Mishra | Done |  | P3 | 2025-11-24 |  | 2026-02-16 | sprint-Cristobal | 6 | 6.5 | FILTER
Automation | FILTER-11164 | Validate Persistence of Custom Activities Column Order | FILTER-10489 | Escape Defect | Rachit Mishra | Done |  | P3 | 2025-12-02 |  | 2026-02-04 | sprint-Cristobal | 7 | 6 | FILTER
Automation | FILTER-11172 | Fix YouTube Blocked Video Incorrectly Logged as "Allowed" | FILTER-7286 | Escape Defect | Rachit Mishra | Done |  | P3 | 2025-12-02 |  | 2026-02-17 | sprint-Cristobal | 4.5 | 4 | FILTER
Automation | FILTER-11226 | Automated E2E Regression Test: Fix False Positive Block on Google Search Embeds (YouTube/Reddit) | FILTER-10034 | Escape Defect | Rachit Mishra | Done |  | P1 | 2025-12-03 |  | 2026-02-17 | sprint-Cristobal | 5 | 7 | FILTER
Automation | FILTER-11296 | Automated E2E Test: Fix Excessive Email Alerts for Single Block Action | FILTER-4362 | Escape Defect | Rachit Mishra | Done |  | P3 | 2025-12-04 |  | 2026-01-19 | sprint-Cristobal | 7 | 6 | FILTER
Automation | FILTER-11487 | Automated E2E Regression: Pinterest NSFW Blur and Interactivity Validation | FILTER-10760 | Defect | Rachit Mishra | Done |  | P2 | 2025-12-19 |  | 2026-02-16 | sprint-Cristobal | 4 | 3 | FILTER
Automation | FILTER-11839 | Add test coverage for SIS Data Readiness Report Download | FILTER-11826 | Defect | Rachit Mishra | Closed without action |  | P1 | 2026-01-29 |  | 2026-02-17 | sprint-Cristobal | 0 | 8 | FILTER
Automation | FILTER-11853 | Add test coverage for SIS Data Readiness feature | FILTER-11768 | Defect | Rachit Mishra | Closed without action |  | P2 | 2026-01-29 |  | 2026-02-17 | sprint-Cristobal | 0 | 5 | FILTER
Automation | FILTER-11856 | Add Test Coverage - SIS Data Readiness Product Count Validation | FILTER-11825 | Defect | Rachit Mishra | Closed without action |  | P2 | 2026-01-29 |  | 2026-02-17 | sprint-Cristobal | 0 | 5 | FILTER
QA | FILTER-12000 | Investigate and fix recurring user-agent parsing errors | FILTER-11998 | Escape Defect | Rachit Mishra | Done |  | P1 | 2026-02-03 |  | 2026-02-12 | sprint-Cristobal | 4 | 4 | FILTER
Dev | FILTER-11718 | [sprox] Social media request processing & logging | FILTER-11717 | Task | Ravi Raj | Done |  | P3 | 2026-01-19 |  | 2026-02-16 | sprint-Cristobal | 16 | 16 | FILTER
Dev | FILTER-11720 | [sprox] Function translation to sprox - Part 4 | FILTER-11715 | Task | Ravi Raj | Done |  | P3 | 2026-01-19 |  | 2026-02-12 | sprint-Cristobal | 20 | 16 | FILTER
Dev | FILTER-11723 | [sprox] Redirection logic verification with wrapper flags | FILTER-11712 | Task | Ravi Raj | Done |  | P3 | 2026-01-19 |  | 2026-02-16 | sprint-Cristobal | 8 | 8 | FILTER
Task | FILTER-9275 | [SPAC] Moving cluster & proxy URL to globals |  |  | Ravi Raj | Closed |  | P2 | 2025-07-22 |  | 2026-03-03 | sprint-Cristobal | 20 | 12 | FILTER
Dev | FILTER-11255 | Reopened - Fix Activities Log Sort Failure: Ensure "Uncategorized" Filter Only Returns Uncategorized Sites | FILTER-4843 | Support Escalation (OLD) | Sagar Satpute | Closed without action |  | P3 | 2025-12-03 |  | 2026-01-29 | sprint-Cristobal | 4 | 8 | FILTER
Dev | FILTER-11547 | Reopened - Dev Task - excessive email alerts for blocked activity | FILTER-4362 | Escape Defect | Sagar Satpute | Closed without action |  | P3 | 2025-12-21 |  | 2026-01-16 | sprint-Cristobal | 0 | 1 | FILTER
Defect | FILTER-11581 | NewFeatureBug: SupportTool Customlist API. Name field can be saved with spaces at start and end. Add/Update |  |  | Sagar Satpute | Closed without action |  | P3 | 2026-01-05 |  | 2026-02-05 | sprint-Cristobal | 0 | 0 | FILTER | unplanned-sprint
Dev | FILTER-11650 | Implement Cron Job for Custom List Sync Error Recovery | FILTER-11649 | Task | Sagar Satpute | Done |  | P3 | 2026-01-15 |  | 2026-01-27 | sprint-Cristobal | 30 | 32 | FILTER | Capitalized-Feature
Dev | FILTER-11857 | Clone CustomList API accepts invalid values for "usage" field | FILTER-11789 | Defect | Sagar Satpute | Closed without action |  | P2 | 2026-01-29 |  | 2026-03-06 | sprint-Cristobal | 4 | 4 | FILTER
Dev | FILTER-11911 | Fix Invalid student_email parameter causing 400 error in postMonitoringNotice API on UK cluster | FILTER-11910 | Task | Sagar Satpute | Done |  | P1 | 2026-01-30 |  | 2026-02-04 | sprint-Cristobal | 8 | 8 | FILTER
Dev | FILTER-11943 | Add Source field to OS demo data in Respond demo cron job | FILTER-11942 | Task | Sagar Satpute | Done |  | P1 | 2026-02-03 |  | 2026-02-05 | sprint-Cristobal | 8 | 8 | FILTER
Dev | FILTER-11957 | Dev Task for Cross-FID Bypass - Admin from one FID can access/modify custom lists of another FID | FILTER-11813 | Defect | Sagar Satpute | Done |  | P3 | 2026-02-04 |  | 2026-02-04 | sprint-Cristobal | 4 | 4 | FILTER | Capitalized-Feature
Dev | FILTER-11959 | Dev request to provide account expiry logs for FID securly@dcpschools.org (trial, creation, expiry) | FILTER-11958 | Task | Sagar Satpute | Closed without action |  | P1 | 2026-02-04 |  | 2026-02-05 | sprint-Cristobal | 0 | 4 | FILTER
Dev | FILTER-11968 | BUGCROWD - Unauthorized IP Deletion via IDOR in `ip_ops_delete.php`. | FILTER-11965 | Defect | Sagar Satpute | Done |  | P2 | 2026-02-05 |  | 2026-02-06 | sprint-Cristobal | 5 | 5 | FILTER
Task | FDSE-112 | Implementation of Button bars as per the design | FDSE-111 | Epic | Shailendra Singh | Resolved | Fixed | P3 | 2025-11-20 | 2026-02-09 | 2026-02-09 | sprint-Cristobal | 24 | 20 | FDSE | product-filter
Task | FDSE-123 | Simple search component implementation without chip and without auto-complete | FDSE-122 | Epic | Shailendra Singh | Resolved |  | P3 | 2025-12-04 |  | 2026-02-11 | sprint-Cristobal | 4 | 24 | FDSE | Capitalized-Feature, product-filter
Defect | FILTER-10713 | NewFeatureBug. Image Blurr setting. Expection list. Add Drawer does not follow the same CSS as other Add drawers |  |  | Shailendra Singh | RELEASED TO PROD | Fixed | P2 | 2025-11-07 | 2025-11-17 | 2026-03-03 | sprint-Cristobal | 2 | 2 | FILTER | unplanned-sprint
Defect | FILTER-10714 | NewFeatureBug. Image Blurr setting. Expection list. Add Drawer's Add button is active even if the website format is incorrect |  |  | Shailendra Singh | RELEASED TO PROD | Fixed | P2 | 2025-11-07 | 2025-11-17 | 2026-03-03 | sprint-Cristobal | 6 | 6 | FILTER | unplanned-sprint
Defect | FILTER-10925 | NewFeatureBug: Image Blur setting. Confirmation popup is not translated |  |  | Shailendra Singh | RELEASED TO PROD | Fixed | P3 | 2025-11-24 | 2025-11-26 | 2026-03-03 | sprint-Cristobal | 2 | 2 | FILTER | Image-Blur-JavaScript, unplanned-sprint
Dev | FILTER-11606 | Update SIS Data Readiness Screen to Display Sync Data for Product-Less FIDs- UI | FILTER-9605 | Task | Shailendra Singh | Closed without action |  | P1 | 2026-01-08 |  | 2026-02-09 | sprint-Cristobal | 4 | 4 | FILTER
Defect | FILTER-11768 | InProd:No, SIS data readiness does not show data on UI |  |  | Shailendra Singh | RELEASED TO PROD | Fixed | P2 | 2026-01-22 | 2026-02-08 | 2026-03-03 | sprint-Cristobal | 1 | 2 | FILTER
Dev | FILTER-11851 | SIS Data Readiness - Data not displaying on UI despite successful API response | FILTER-11768 | Defect | Shailendra Singh | Closed without action |  | P2 | 2026-01-29 |  | 2026-02-08 | sprint-Cristobal | 1 | 3 | FILTER
Dev | FILTER-11854 | SIS Data Readiness - Product Count Shows 0 for FIDs with Multiple Products | FILTER-11825 | Defect | Shailendra Singh | Done |  | P2 | 2026-01-29 |  | 2026-02-09 | sprint-Cristobal | 2 | 2 | FILTER
QA | FILTER-11173 | Manual QA Validation for YouTube Blocked Video Logging Inconsistency | FILTER-7286 | Escape Defect | Surabhi Choudhary | Done |  | P3 | 2025-12-02 |  | 2026-02-04 | sprint-Cristobal | 5 | 6 | FILTER
QA | FILTER-11297 | Manual QA Validation for Excessive Email Alerts on Blocked Activity | FILTER-4362 | Escape Defect | Surabhi Choudhary | Closed without action |  | P3 | 2025-12-04 |  | 2026-02-11 | sprint-Cristobal | 0.5 | 0 | FILTER
QA | FILTER-11522 | Manual QA Validation: SIS Data Readiness Display for Sync-Only FIDs | FILTER-9605 | Task | Surabhi Choudhary | Done |  | P1 | 2025-12-19 |  | 2026-02-12 | sprint-Cristobal | 3 | 3 | FILTER
QA | FILTER-11578 | QA Task - Empty class images are getting blurred | FILTER-10630 | Defect | Surabhi Choudhary | Done |  | P3 | 2026-01-05 |  | 2026-02-10 | sprint-Cristobal | 2 | 2 | FILTER
QA | FILTER-11586 | QA: NSFW Debug Callout missing on blurred images when setNSFWDebugAllTabs is active | FILTER-10643 | Defect | Surabhi Choudhary | Done |  | P3 | 2026-01-05 |  | 2026-02-04 | sprint-Cristobal | 1 | 1 | FILTER
QA | FILTER-11838 | Verify SIS Data Readiness Report Download - PDF and CSV | FILTER-11826 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-01-29 |  | 2026-02-12 | sprint-Cristobal | 2 | 2 | FILTER
QA | FILTER-11852 | Verify fix for SIS Data Readiness UI display issue | FILTER-11768 | Defect | Surabhi Choudhary | Done |  | P2 | 2026-01-29 |  | 2026-02-09 | sprint-Cristobal | 1 | 1 | FILTER
QA | FILTER-11855 | Verify Fix - SIS Data Readiness Product Count for FIDs | FILTER-11825 | Defect | Surabhi Choudhary | Done |  | P2 | 2026-01-29 |  | 2026-02-09 | sprint-Cristobal | 0.5 | 0.5 | FILTER
QA | FILTER-11940 | SPAC – Pagescan logs not received for uncategorized site when no bit is set | FILTER-11921 | Defect | Surabhi Choudhary | Closed without action |  | P2 | 2026-02-03 |  | 2026-02-09 | sprint-Cristobal | 0 | 0 | FILTER
QA | FILTER-11983 | Manual QA: Keyboard tab opens the YouTube video preview on google | FILTER-11709 | Defect | Surabhi Choudhary | Done |  | P3 | 2026-02-06 |  | 2026-02-11 | sprint-Cristobal | 1 | 1 | FILTER
Task | FDSE-126 | Analysis - Search without chip but with auto-complete component implementation | FDSE-174 | Epic | Swaroop Chavhan | Resolved |  | P3 | 2025-12-04 |  | 2026-04-15 | sprint-Cristobal | 12 | 12 | FDSE | Capitalized-Feature, product-filter
Dev | FILTER-11245 | Reopened - Fix CRXTN Failure to Block URLs at script.google.com Due to Internal Whitelist | FILTER-7127 | Escape Defect | Swaroop Chavhan | Done |  | P2 | 2025-12-03 |  | 2026-02-04 | sprint-Cristobal | 4 | 16 | FILTER
Dev | FILTER-11260 | FE: Fix Date Range Picker Accessibility (Keyboard Focus) and Styling Regression (Material 17) | FILTER-11114 | Story | Swaroop Chavhan | Done |  | P3 | 2025-12-03 |  | 2026-02-02 | sprint-Cristobal | 4 | 4 | FILTER
Dev | FILTER-11530 | Fix Activity Tab Column Persistence (Layout Resets on Navigation/Relogin) | FILTER-10489 | Escape Defect | Vaibhav Kumbhar | Closed without action |  | P3 | 2025-12-19 |  | 2026-01-29 | sprint-Cristobal | 3 | 6 | FILTER
Dev | FILTER-11543 | YouTube Category Blocks correctly enforced but incorrectly logged as "ALLOWED" in Activity UI | FILTER-7286 | Escape Defect | Vaibhav Kumbhar | Done |  | P3 | 2025-12-21 |  | 2026-02-04 | sprint-Cristobal | 19 | 16 | FILTER
Dev | FILTER-11549 | Dev Task - P1 Escalation-Filter Activity report shows incorrect Category | FILTER-10375 | Escape Defect | Vaibhav Kumbhar | Done |  | P1 | 2025-12-21 |  | 2026-01-28 | sprint-Cristobal | 32 | 18 | FILTER
Dev | FILTER-11599 | Improve logging for the php broker | FILTER-10375 | Escape Defect | Vaibhav Kumbhar | Done |  | P1 | 2026-01-06 |  | 2026-01-11 | sprint-Cristobal | 6 | 2 | FILTER
Dev | FILTER-11669 | Fix Unable to Remove ChatGPT Entry from Filter UI | FILTER-11571 | Task | Vaibhav Kumbhar | Done |  | P2 | 2026-01-15 |  | 2026-01-27 | sprint-Cristobal | 14 | 14 | FILTER
Defect | FILTER-11709 | NewFeatureBug: Keyboard tab opens the YouTube video preview on google |  |  | Vaibhav Kumbhar | RELEASED TO PROD | Fixed | P2 | 2026-01-19 | 2026-02-09 | 2026-04-07 | sprint-Cristobal | 5 | 6 | FILTER
Dev | FILTER-11726 | Lookup tool changes for uncatagorized block refactoring | FILTER-11577 | Task | Vaibhav Kumbhar | Done |  | P3 | 2026-01-20 |  | 2026-02-04 | sprint-Cristobal | 7 | 6 | FILTER
Dev | FILTER-11849 | HACKERONE - Fix IDOR Vulnerabilities in IP Allowlist APIs - Exposure & Deletion of Cross-Tenant Data | FILTER-10346 | Defect | Vaibhav Kumbhar | Done |  | P2 | 2026-01-29 |  | 2026-02-06 | sprint-Cristobal | 9 | 12 | FILTER
Dev | FILTER-11878 | HACKERONE - Fix IDOR vulnerability in getScheduledReportList endpoint - Cross-FID PII disclosure | FILTER-10476 | Defect | Vaibhav Kumbhar | Done |  | P3 | 2026-01-29 |  | 2026-02-09 | sprint-Cristobal | 12 | 14 | FILTER
Dev | FILTER-11920 | Cleanup MainDomainCategorizationEnabled from www-filter code, as it is deprecated. | FILTER-10521 | Task | Vaibhav Kumbhar | Done |  | P3 | 2026-02-02 |  | 2026-02-06 | sprint-Cristobal | 2 | 2 | FILTER
Dev | FILTER-11986 | [Dev TS Extension]: Keyboard tab opens the YouTube video preview on google | FILTER-11709 | Defect | Vaibhav Kumbhar | Done |  | P3 | 2026-02-08 |  | 2026-02-10 | sprint-Cristobal | 2 | 3 | FILTER

## Not Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Epic | FILTER-10635 | Force PR to get blocked if PR checks are failing |  |  | Harsh Verma | Development In Progress |  | P2 | 2025-11-06 |  | 2026-03-03 | sprint-Cristobal | 8 | 0 | FILTER | unplanned-sprint

## Removed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Task | FILTER-10604 | Placeholder task to track the efforts used for Vanta tool task completion |  |  | Harsh Verma | In Progress |  | P3 | 2025-11-03 |  | 2026-04-27 | sprint-Cristobal | 0 | 8 | FILTER | unplanned-sprint |  | YES
Escape Defect | FILTER-9853 | Filter >> Activities and Emails for Blocked search terms on Yandex, Baidu and DuckDuckGo, do not have search query in external links |  |  | Arun Thakur | Open |  | P3 | 2025-08-31 |  | 2026-04-10 | sprint-Cristobal | 6.5 | 2 | FILTER
Task | FILTER-11713 | [sprox] Securly cookie creation logic implementation | FILTER-8230 | Epic | Ashish Temurnikar | Closed |  | P3 | 2026-01-19 |  | 2026-03-05 | sprint-Cristobal | 20 | 8 | FILTER
Task | FILTER-11697 | Extension of FILTER-11605 |  |  | Harsh Verma | In Progress |  | P3 | 2026-01-19 |  | 2026-04-27 | sprint-Cristobal | 0 | 24 | FILTER | unplanned-sprint
Task | FILTER-6852 | Add unit tests for chrome and edge extensions for background script |  |  | Harshada Kude | Backlog |  | P3 | 2025-01-27 |  | 2026-02-09 | sprint-Cristobal | 0 | 16 | FILTER

## P1 Escalation
P1 Escalation — FILTER · sprint-Cristobal (2026-02-03 → 2026-02-16)
sprint-Cristobal tickets where Issue Type = Escape Defect AND Priority = P1 AND summary contains 'P1 Escalation' (regardless of bucket). Total = 6.
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Bucket
Escape Defect | FILTER-11610 | P1 Escalation-CORs Errors at BlueBeam and Boomerang S3 Amazon domains ¦ St. Vrain |  |  | Ramani Cheruvu | In Progress | Fixed | P1 | 2026-01-08 | 2026-01-27 | 2026-04-27 | sprint-Cristobal | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_reopened, p1escalation, unplanned-sprint, zendesk_enterprise |  | Removed
Escape Defect | FILTER-10034 | P1 Escalation-YouTube blocked while doing a Google Search |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-09-12 | 2025-11-24 | 2026-04-16 | sprint-Cristobal | 5 | 5 | FILTER | jira_added, jira_closed_notify, jira_confirmation, jira_done, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_p3, jira_qa_verified, jira_reopened, p1escalation, unplanned-sprint, zendesk_org_at_risk |  | Completed
Escape Defect | FILTER-10392 | P1 Escalation-YouTube Videos play in Gmail even when blocked in policy ¦ Downingtown |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-10-10 | 2026-02-10 | 2026-04-07 | sprint-Cristobal | 16 | 16 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_closed_notify, jira_escalated, jira_in_progress, jira_qa_verified, jira_reopened, p1escalation, unplanned-sprint |  | Completed
Escape Defect | FILTER-11443 | P1 Escalation-Chrome extension bypass using Omada DNS |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-12-15 | 2026-01-21 | 2026-04-07 | sprint-Cristobal | 16 | 16 | FILTER | jira_added, jira_closed_notify, jira_done, jira_escalated, jira_p1, zendesk_enterprise |  | Completed
Escape Defect | FILTER-11654 | P1 Escalation-Crextn blocking issue with Google Workspace apps | FILTER-4326 | Epic | Shashank Tiwari | QA Verified | Done | P1 | 2026-01-15 | 2026-04-06 | 2026-04-28 | sprint-Cristobal | 0 | 0 | FILTER | jira_added, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_qa_verified, jira_resolved |  | Removed
Escape Defect | FILTER-11985 | P1 Escalation-Extension bypass by adding a string at the end of the site |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-02-06 | 2026-02-25 | 2026-04-16 | sprint-Cristobal | 27 | 12 | FILTER | jira_added, jira_closed_notify, jira_done, jira_escalated, jira_p1, jira_qa_verified, zendesk_enterprise |  | Removed