## Capacity vs Delivery
Capacity vs Delivery — FILTER · sprint-Dolly (Tue 17 Feb → Mon 02 Mar 2026)
Team Composition (per Securly-PjM-Skills.md Part 2 — Filter India roster). Inactive members for this sprint window are shaded grey with a roster note.
Name | Role | Function / Split | Allocation (FTE) | Seniority | Employment | Notes
Shashank Tiwari | Project Manager | PM / Delivery | 0 | Lead | FTE | Not counted in delivery capacity
Harsh Verma | FE | FrontEnd Architect (Angular) | 1 | Senior | FTE
Arun Thakur | FE + Ext | Angular / Extension | 1 | Medium | FTE
Harshada Kude | FE | Angular | 1 | Junior | FTE
Shailendra Singh | FE | Angular | 1 | Medium | FTE
Swaroop Chavhan | FE + Ext | Angular / Extension | 1 | Medium | FTE
Ashish Modak | BE Architect | Extension / Go / PHP | 1 | Senior | FTE
Prateek Fotedar | BE (www) | Go / PHP | 1 | Senior | FTE
Sagar Satpute | BE (www) | Go / PHP | 1 | Medium | FTE
Vaibhav Kumbhar | BE | Go / PHP | 1 | Medium | FTE
Ashish Temurnikar | BE | DNS / SPAC / Squid / Rust | 1 | Senior | FTE
Ravi Raj | BE | DNS / SPAC / Squid / Rust | 1 | Medium | FTE
Pratik Tiwari | BE + Ext | Extension / Go / Rust | 1 | Senior | FTE
Altamash Heroli | QA | Pri. Manual QA | 1 | Senior | FTE
Surabhi Choudhary | QA | Sr. Manual QA | 1 | Senior | FTE
Ayesha Kamde | QA | Manual QA | 1 | Junior | FTE
Amol Mithari | Auto QA Lead | Team Lead — Auto QA / SDET | 1 | Lead | FTE | Joined 20-Feb-2026 (partial sprint)
Amit Shete | Auto QA | Pri. SDET | 1 | Senior | FTE
Rachit Mishra | Auto QA | SDET | 1 | Junior | FTE | Last day 20-Feb-2026 (partial sprint)
Total FILTER allocation |  |  |  | FTE-equivalent heads available to FILTER
Capacity Parameters (yellow cells are inputs — re-run the script after edits)
Parameter | Value | Description
Sprint length (working days) | 10 | FILTER 15-day sprint Tue → Mon. sprint-Dolly = 2026-02-17 → 2026-03-02.
Company holidays in sprint | 0 | India calendar 2026 — none in window
Effective working days (sprint − company holidays) |  | Used as the per-person calendar for availability
Hours per working day (nominal) | 8 | Standard working day
Focus factor (productive fraction) | 0.9 | 90% — what SLT expects (sprint-analysis default)
Misc buffer (meetings, scrums, code review, …) | 20% | 20% blanket reservation deducted from Available to get Net Available
Effective hours per FTE per sprint
Allocated FTE on FILTER (active this sprint) | 18 | Headcount actually working this sprint (excludes joiners/leavers outside window)
Ideal capacity for the sprint (hrs)
Issue scope (Jira projects) | FILTER, PTGM, FDSE | Tickets pulled with `project in (FILTER, PTGM, FDSE) AND sprint = …` — FDSE: 4 · FILTER: 127 · PTGM: 11
Capacity vs Actual Delivery — sprint-Dolly
Metric | Hours | % of Ideal | Rating | Notes
Actual Availability |  |  |  | Sum of per-person availability (Ideal − leaves)
Misc Buffer (20%) |  |  |  | Reserved for meetings, scrums, code reviews
Net Available (Available − Misc Buffer) |  |  |  | Realistic delivery capacity — used as the denominator for Completed %
Completed |  |  |  | Sum of in-sprint timeSpent (Completed bucket)
Not Completed (Spillover) |  |  |  | Original estimate for spillover (carried into next sprint)
Removed |  |  |  | Original estimate for issues removed mid-sprint
Completed by Priority
Tickets (parents) = unique parent items (Story / Task / Defect / Escape Defect) — subtasks roll up to their parent so 1 parent + 3 subtasks = 1 ticket. Tickets (incl. subtasks) = raw record count incl. every Dev / QA / Automation / Review / Test Case Creation / Debug subtask. Hours = sum across parents and subtasks; matches the core-team Completed hours on the Per-person Delivery sheet.
Priority | Tickets (parents) | Tickets (incl. subtasks) | Hours (incl. subtasks) | % of Completed Hrs | % of Tickets (parents) | Notes
P0 | 1 | 1 | 8 |  |  | Critical / production halting
P1 | 1 | 1 | 24 |  |  | P1 — high priority (see P1 Escalation tab for escalations)
P2 | 4 | 10 | 51.5 |  |  | Major
P3 | 27 | 38 | 484.5 |  |  | Standard
TOTAL | 33 | 50 | 568 | 100% | 100% | Sum of Completed bucket (core roster)
Sprint Completion (spillover = Not Completed)
Metric | Tickets | Planned Hrs (OE) | % by Tickets | % by Hrs | Notes
Completed (closed in sprint) | 50 | 516 |  |  | In-sprint deliverables
Spillover (not completed → carry-over) | 2 | 16 |  |  | Original estimate carried to next sprint
Removed (mid-sprint scope cut) | 7 | 151 | — | — | Excluded from completion ratio (out of scope)
Mid-sprint additions (core) | 15 |  | — | — | Late-arriving work (Jira issueKeysAddedDuringSprint)
Sprint completion rate (tickets) | 96.15% | On Target | Completed ÷ (Completed + Spillover)
Sprint completion rate (planned hrs) | 96.99% | On Target | Σ OE Completed ÷ Σ OE (Completed + Spillover)
Planned completion rate (tickets, excludes mid-sprint adds) | 94.87% | On Target | Originally-committed tickets only
Planned completion rate (planned hrs, excludes mid-sprint adds) | 95.84% | On Target | Originally-committed planned hours only
P1 Escalation snapshot
5 ticket(s) in sprint-Dolly match 'P1 Escalation' in the title — 4 closed, 1 still open. See the 'P1 Escalation' tab.
Mid-sprint additions snapshot
15 ticket(s) were added to sprint-Dolly after it started (issueKeysAddedDuringSprint) — Completed 13, Spillover 0, Removed 2. Highlighted in amber on every detail sheet (Added Mid-Sprint = YES).
Assumptions & caveats
• Sprint window from Jira (/rest/agile/1.0/sprint/5297): 2026-02-17 → 2026-03-02 (10 Mon–Fri working days). Refresh with fetch_filter_sprint_meta.py + fetch_filter_sprint_issues.py.
• Issues pulled from FILTER + PTGM + FDSE (project-scope expanded for the India scrum team's split across the three products).
• Date-aware roster: Amol Mithari joined 20-Feb-2026; Rachit Mishra's last day was 20-Feb-2026. Inactive members for this sprint window are shaded grey in the Team Composition table and excluded from per-person availability + delivery.
• Available (hrs) = (effective working days − leave days) × 8 × focus factor, where effective working days = sprint working days − company holidays falling inside the sprint − days outside the person's employment window. Per-person Delivery shows leave days in Column G to explain the delta from a full sprint.
• Net Available = Available − 20% Misc Buffer for meetings, scrums, code review, etc. Completed/Not Completed/Removed % of capacity use Net Available as the denominator.
• Time Spent on Completed sheet uses the in-sprint hybrid worklog rule (sprint-analysis.md): single-sprint = timespent; multi-sprint = SUM of worklogs whose started ∈ [sprintStart, sprintEnd].
• Not Completed and Removed totals use Original Estimate.
• Removed list comes from the Sprint Report puntedIssues (greenhopper API).
• Core roster only: assignees outside Securly-PjM-Skills.md Part 2 are dropped from per-person + detail sheets.
• P1 Escalation tab is filtered to Issue Type = Escape Defect AND Priority = P1 AND title contains 'P1 Escalation'.
• Completed by Priority — Tickets (parents) rolls subtasks up to their parent (each work item counted once at its parent priority); Tickets (incl. subtasks) shows the raw record count for comparison. The Hours column sums every record (parent + subtasks) and matches the core-team Completed total.
• Spillover = Not Completed bucket (tickets carried into the next sprint).
• Sprint completion rate uses Completed ÷ (Completed + Spillover); Removed tickets are excluded (treated as scope cut). 'Planned' rate also excludes mid-sprint additions.
• All detail sheets (Completed, Not Completed, Removed) highlight tickets added after sprint start (Jira sprint-report issueKeysAddedDuringSprint) in amber, with an 'Added Mid-Sprint = YES' tag column.
• Ratings: ≥85% On Target (green), 70–85% Below Target (amber), <70% Significantly Below (red).

## Per-person Delivery
Assignee | Completed (hrs) | Not Completed (hrs) | Removed (hrs) | Efficiency | Available (hrs) | Leave Days (sprint) | Misc Buffer 20% (hrs) | Net Available (hrs)
Harsh Verma | 50 | 16 | 32 |  | 50.4 | 3
Arun Thakur | 4 | 0 | 2 |  | 72 | 0
Harshada Kude | 61 | 0 | 0 |  | 72 | 0
Shailendra Singh | 0 | 0 | 0 |  | 72 | 0
Swaroop Chavhan | 51 | 0 | 52 |  | 72 | 0
Ashish Modak | 66 | 0 | 0 |  | 72 | 0
Prateek Fotedar | 0 | 0 | 0 |  | 72 | 0
Sagar Satpute | 14 | 0 | 0 |  | 64.8 | 1
Vaibhav Kumbhar | 89 | 0 | 0 |  | 72 | 0
Ashish Temurnikar | 84 | 0 | 0 |  | 72 | 0
Ravi Raj | 28 | 0 | 0 |  | 72 | 0
Pratik Tiwari | 24 | 0 | 0 |  | 50.4 | 3
Altamash Heroli | 0 | 0 | 65 |  | 72 | 0
Surabhi Choudhary | 10 | 0 | 0 |  | 50.4 | 3
Ayesha Kamde | 6 | 0 | 0 |  | 64.8 | 1
Amol Mithari | 77.5 | 0 | 0 |  | 50.4 | 0
Amit Shete | 3.5 | 0 | 0 |  | 72 | 0
Rachit Mishra | 0 | 0 | 0 |  | 28.8 | 0
TOTAL

## Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Task | FILTER-12250 | Migrate P0API DNS Test Suite for Custom Policy, Take Home Policy and PerIpPolicy for Sites to Use DNS Resolver | FILTER-11735 | Epic | Amol Mithari | Closed |  | P3 | 2026-02-26 |  | 2026-03-05 | sprint-Dolly | 23 | 1 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12016 | POC for extension api fortification |  |  | Ashish Modak | Closed |  | P1 | 2026-02-11 |  | 2026-03-10 | sprint-Dolly | 24 | 24 | FILTER | 2026-Tech-debt, unplanned-sprint |  | YES
Task | FILTER-12130 | Add IWF changes to go broker and back-merge the requried PRs |  |  | Ashish Modak | Closed |  | P3 | 2026-02-23 |  | 2026-03-02 | sprint-Dolly | 6 | 6 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12131 | Create a document with target date for extension release |  |  | Ashish Modak | Closed |  | P3 | 2026-02-23 |  | 2026-03-02 | sprint-Dolly | 4 | 4 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12135 | Move JS extension code to sprint-master |  |  | Ashish Modak | Closed |  | P3 | 2026-02-23 |  | 2026-03-02 | sprint-Dolly | 4 | 4 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12309 | Verified access POC |  |  | Ashish Modak | Closed |  | P3 | 2026-03-02 |  | 2026-03-05 | sprint-Dolly | 12 | 12 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-12302 | RTQA5 debugging for SPAC & DNS working state |  |  | Ashish Temurnikar | Closed |  | P3 | 2026-03-01 |  | 2026-03-02 | sprint-Dolly | 8 | 8 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-12303 | [sprox] sprox setup debugging on RTQA5 |  |  | Ashish Temurnikar | Closed |  | P3 | 2026-03-01 |  | 2026-03-05 | sprint-Dolly | 16 | 12 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12070 | Phase 3: Upgrade @ngx-translate to latest for Support-tool, Filter, Aware and Cases, home-alone |  |  | Harshada Kude | Resolved | Fixed | P3 | 2026-02-16 | 2026-02-23 | 2026-03-12 | sprint-Dolly | 13 | 24 | FILTER |  |  | YES
Task | FILTER-12318 | fix: breaking testcases for securly-extension repo |  |  | Pratik Tiwari | Closed |  | P3 | 2026-03-02 |  | 2026-04-16 | sprint-Dolly | 6 | 6 | FILTER | unplanned-sprint |  | YES
Task | FDSE-161 | Search without chip but with auto-complete component implementation | FDSE-174 | Epic | Swaroop Chavhan | Closed | Fixed | P3 | 2026-02-13 | 2026-02-27 | 2026-04-15 | sprint-Dolly | 32 | 32 | FDSE | Capitalized-Feature, product-filter |  | YES
Task | FILTER-12146 | Helping team with Accessibility |  |  | Swaroop Chavhan | Closed | Fixed | P3 | 2026-02-24 | 2026-03-03 | 2026-03-06 | sprint-Dolly | 9 | 10 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-12129 | Sync crextn_client code changes to securly_extension |  |  | Vaibhav Kumbhar | Closed without action |  | P3 | 2026-02-22 |  | 2026-02-22 | sprint-Dolly | 4 | 4 | FILTER | unplanned-sprint |  | YES
QA | FILTER-12030 | Verify fix – Admins unable to access Filter UI – "We're unable to locate the user" | FILTER-11982 | Escape Defect | Altamash Heroli | Closed without action |  | P3 | 2026-02-11 |  | 2026-02-22 | sprint-Dolly | 0 | 2 | FILTER
Automation | FILTER-11158 | Validate Account Deletion Request Expiry Page Load | FILTER-10227 | Defect | Amit Shete | Done |  | P2 | 2025-12-02 |  | 2026-03-02 | sprint-Dolly | 3.5 | 4 | FILTER
QA | FILTER-11205 | Manual QA Validation for AirPrint Failure on iOS 18 with MDM-Pushed SmartPAC | FILTER-6994 | Escape Defect | Amit Shete | QA Verified |  | P2 | 2025-12-03 |  | 2026-03-03 | sprint-Dolly | 0 | 3 | FILTER
Automation | FILTER-11174 | Fix YouTube Category Bypass via Google Videos Tab | FILTER-6620 | Support Escalation (OLD) | Amol Mithari | Done |  | P3 | 2025-12-02 |  | 2026-03-02 | sprint-Dolly | 8.5 | 6 | FILTER
Task | FILTER-12043 | Migrate P0API DNS Test Suite for All Search Engines to Use DNS Resolver | FILTER-11735 | Epic | Amol Mithari | Closed |  | P3 | 2026-02-12 |  | 2026-03-05 | sprint-Dolly | 1 | 1 | FILTER
Automation | FILTER-12044 | Automation - Migrate P0API DNS Test Suite for All Search Engines to Use DNS Resolver | FILTER-12043 | Task | Amol Mithari | Done |  | P3 | 2026-02-12 |  | 2026-02-27 | sprint-Dolly | 22 | 24 | FILTER
Automation | FILTER-12251 | Migrate P0API DNS Test Suite for Custom Policy | FILTER-12250 | Task | Amol Mithari | Done |  | P3 | 2026-02-26 |  | 2026-02-27 | sprint-Dolly | 8 | 8 | FILTER
Automation | FILTER-12252 | Migrate P0API DNS Test Suite for Take Home Policy | FILTER-12250 | Task | Amol Mithari | Done |  | P3 | 2026-02-26 |  | 2026-02-27 | sprint-Dolly | 7 | 8 | FILTER
Automation | FILTER-12253 | Migrate P0API DNS Test Suite for perIP Policy | FILTER-12250 | Task | Amol Mithari | Done |  | P3 | 2026-02-26 |  | 2026-02-27 | sprint-Dolly | 8 | 8 | FILTER
Dev | FILTER-11490 | Fix Expiry Page Timezone (IST to UTC) and Update Headline Formatting | FILTER-10227 | Defect | Arun Thakur | Done |  | P2 | 2025-12-19 |  | 2026-02-24 | sprint-Dolly | 4 | 4 | FILTER
Dev | FILTER-11788 | Creating task for Dev triage | FILTER-11819 | Task | Ashish Modak | Done |  | P2 | 2026-01-23 |  | 2026-04-16 | sprint-Dolly | 8 | 8 | FILTER
Dev | FILTER-12066 | DEV - Investigate and Mitigate Potential IWF Data Security Breach | FILTER-12065 | Escape Defect | Ashish Modak | Done |  | P1 | 2026-02-16 |  | 2026-02-18 | sprint-Dolly | 8 | 8 | FILTER
Dev | FILTER-11390 | Investigate/Fix AirPrint Failure on iOS 18 Managed iPads (JAMF/Mosyle) due to MDM-Pushed SmartPAC | FILTER-6994 | Escape Defect | Ashish Temurnikar | Done |  | P2 | 2025-12-09 |  | 2026-02-25 | sprint-Dolly | 20 | 16 | FILTER | jira_added, jira_done, jira_escalated, jira_open
Task | FILTER-11713 | [sprox] Securly cookie creation logic implementation | FILTER-8230 | Epic | Ashish Temurnikar | Closed |  | P3 | 2026-01-19 |  | 2026-03-05 | sprint-Dolly | 20 | 8 | FILTER
Dev | FILTER-11722 | [sprox] Securly cookie creation logic implementation | FILTER-11713 | Task | Ashish Temurnikar | Done |  | P3 | 2026-01-19 |  | 2026-03-02 | sprint-Dolly | 20 | 8 | FILTER
QA | FILTER-11175 | Manual QA Validation for YouTube Category Block Bypass via Google Video Tab | FILTER-6620 | Support Escalation (OLD) | Ayesha Kamde | Done |  | P3 | 2025-12-02 |  | 2026-02-04 | sprint-Dolly | 6 | 4 | FILTER
Task | FDSE-162 | Improved Translation strategy | FDSE-118 | Epic | Harsh Verma | Closed | Done | P3 | 2026-02-17 | 2026-02-19 | 2026-03-05 | sprint-Dolly | 16 | 16 | FDSE | product-filter
Task | FILTER-12050 | Helping classroom team for PR review and Technical discussions |  |  | Harsh Verma | Closed |  | P3 | 2026-02-13 |  | 2026-03-05 | sprint-Dolly | 4 | 4 | FILTER | unplanned-sprint
Task | FILTER-12051 | Helping Home Team for the overall architecture of Parent Portal design Revamp and and AI Chat for their dashobard requirement |  |  | Harsh Verma | Closed |  | P3 | 2026-02-13 |  | 2026-03-05 | sprint-Dolly | 30 | 24 | FILTER | unplanned-sprint
Task | FILTER-11979 | Need code changes to keep more versions of UI artifacts - Part 1 |  |  | Harshada Kude | Closed |  | P3 | 2026-02-05 |  | 2026-03-05 | sprint-Dolly | 12 | 16 | FILTER
Dev | FILTER-12112 | Create the en-Us.json file and consume translations in Filter Application | FILTER-12111 | Story | Harshada Kude | Done |  | P3 | 2026-02-20 |  | 2026-03-02 | sprint-Dolly | 36 | 24 | FILTER
Dev | FILTER-12075 | [sprox] yaml extraction through Secret Manager | FILTER-12069 | Story | Pratik Tiwari | Done |  | P3 | 2026-02-17 |  | 2026-02-24 | sprint-Dolly | 12 | 8 | FILTER
Dev | FILTER-12320 | Dev task to fix: breaking testcases for securly-extension repo | FILTER-12318 | Task | Pratik Tiwari | Done |  | P3 | 2026-03-02 |  | 2026-03-02 | sprint-Dolly | 6 | 6 | FILTER
Dev | FILTER-12073 | [sprox] Wrapper code comparison with Squid for any missing functions | FILTER-12072 | Story | Ravi Raj | Done |  | P3 | 2026-02-17 |  | 2026-03-02 | sprint-Dolly | 10 | 10 | FILTER
Dev | FILTER-12243 | Go migration for AirPrint Failure on iOS 18 Managed iPads Fix | FILTER-6994 | Escape Defect | Ravi Raj | Done |  | P2 | 2026-02-26 |  | 2026-02-26 | sprint-Dolly | 6 | 6 | FILTER
Dev | FILTER-12322 | [sprox] Enable commented code in Wrapper and Fix get header crash | FILTER-12321 | Story | Ravi Raj | Done |  | P3 | 2026-03-02 |  | 2026-03-02 | sprint-Dolly | 12 | 12 | FILTER
Dev | FILTER-12029 | Investigate and fix: Admins unable to access Filter UI – "We're unable to locate the user" | FILTER-11982 | Escape Defect | Sagar Satpute | Done |  | P3 | 2026-02-11 |  | 2026-02-20 | sprint-Dolly | 6 | 13 | FILTER
Dev | FILTER-12314 | Dev Task for the Fix | FILTER-12313 | Task | Sagar Satpute | Done |  | P3 | 2026-03-02 |  | 2026-03-02 | sprint-Dolly | 8 | 8 | FILTER
QA | FILTER-11159 | Manual QA Validation for Account Deletion Request Expiry Page Failure | FILTER-10227 | Defect | Surabhi Choudhary | Done |  | P2 | 2025-12-02 |  | 2026-02-25 | sprint-Dolly | 3 | 3 | FILTER
QA | FILTER-12077 | Validate changes done on FILTER-11788 | FILTER-11819 | Task | Surabhi Choudhary | Done |  | P3 | 2026-02-17 |  | 2026-04-16 | sprint-Dolly | 2 | 2 | FILTER
QA | FILTER-12261 | QA- http/2 protocol could exceed allowed header size | FILTER-12259 | Escape Defect | Surabhi Choudhary | Done |  | P1 | 2026-02-26 |  | 2026-03-10 | sprint-Dolly | 5 | 3 | FILTER
Task | FILTER-12375 | Helping team with PR reviews, Accessibility |  |  | Swaroop Chavhan | Resolved | Fixed | P3 | 2026-03-06 | 2026-03-16 | 2026-03-16 | sprint-Dolly | 10 | 10 | FILTER | unplanned-sprint
Dev | FILTER-11544 | Fix Filter Bypass: YouTube Category Blocks Not Enforced in Google Search Video Tab | FILTER-6620 | Support Escalation (OLD) | Vaibhav Kumbhar | Done |  | P3 | 2025-12-21 |  | 2026-02-02 | sprint-Dolly | 22 | 20 | FILTER
Dev | FILTER-11832 | Dev Task to To verify if we need additional fixes for uncategorized logging | FILTER-11819 | Task | Vaibhav Kumbhar | Closed without action |  | P3 | 2026-01-29 |  | 2026-02-17 | sprint-Dolly | 9 | 16 | FILTER
Dev | FILTER-12260 | DEV - http/2 protocol could exceed allowed header size | FILTER-12259 | Escape Defect | Vaibhav Kumbhar | Done |  | P1 | 2026-02-26 |  | 2026-03-01 | sprint-Dolly | 4 | 4 | FILTER
Dev | PTGM-653 | Use context in www-filter repo | PTGM-665 | Story | Vaibhav Kumbhar | Done |  | P2 | 2025-12-10 |  | 2026-03-02 | sprint-Dolly | 30 | 32 | PTGM
Dev | PTGM-680 | Use context for broker APIs in www-filter | PTGM-665 | Story | Vaibhav Kumbhar | Done |  | P2 | 2026-02-17 |  | 2026-03-03 | sprint-Dolly | 20 | 12 | PTGM

## Not Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Task | FILTER-12052 | Continuation task on - FILTER-11919 - Complete the changes and give sessions to the team to consume it |  |  | Harsh Verma | Backlog |  | P3 | 2026-02-13 |  | 2026-03-03 | sprint-Dolly | 0 | 16 | FILTER
Epic | FILTER-12240 | [In All Frontend repos] - Making PR checks required and removing Jenkins Job dependency for merging the PRs |  |  | Harsh Verma | Backlog |  | P3 | 2026-02-26 |  | 2026-03-03 | sprint-Dolly | 0 | 0 | FILTER | unplanned-sprint

## Removed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Task | FDSE-155 | Implementation for timepicker component | FDSE-136 | Epic | Swaroop Chavhan | Open |  | P3 | 2026-01-29 |  | 2026-04-28 | sprint-Dolly | 0 | 32 | FDSE | product-filter |  | YES
Task | FDSE-164 | Search with auto-complete component enhancement | FDSE-174 | Epic | Swaroop Chavhan | Open |  | P3 | 2026-02-26 |  | 2026-04-28 | sprint-Dolly | 0 | 20 | FDSE | Capitalized-Feature, product-filter |  | YES
Story | FILTER-11974 | Verify all Image Blur test cases for JS | FILTER-11972 | Epic | Altamash Heroli | Done |  | P2 | 2026-02-05 |  | 2026-04-15 | sprint-Dolly | 55 | 65 | FILTER
Escape Defect | FILTER-9853 | Filter >> Activities and Emails for Blocked search terms on Yandex, Baidu and DuckDuckGo, do not have search query in external links |  |  | Arun Thakur | Open |  | P3 | 2025-08-31 |  | 2026-04-10 | sprint-Dolly | 6.5 | 2 | FILTER
Task | FILTER-10604 | Placeholder task to track the efforts used for Vanta tool task completion |  |  | Harsh Verma | In Progress |  | P3 | 2025-11-03 |  | 2026-04-27 | sprint-Dolly | 0 | 8 | FILTER | unplanned-sprint
Task | FILTER-11697 | Extension of FILTER-11605 |  |  | Harsh Verma | In Progress |  | P3 | 2026-01-19 |  | 2026-04-27 | sprint-Dolly | 0 | 24 | FILTER | unplanned-sprint
Escape Defect | FILTER-12010 | P1 Escalation-Extension Bypass - Bookmark + stop page |  |  | Pratik Tiwari | Confirmation | Fixed | P1 | 2026-02-10 | 2026-04-06 | 2026-04-28 | sprint-Dolly | 20 | 0 | FILTER | jira_added, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_p1, jira_qa_verified, zendesk_enterprise, zendesk_org_at_risk

## P1 Escalation
P1 Escalation — FILTER · sprint-Dolly (2026-02-17 → 2026-03-02)
sprint-Dolly tickets where Issue Type = Escape Defect AND Priority = P1 AND summary contains 'P1 Escalation' (regardless of bucket). Total = 5.
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Bucket
Escape Defect | FILTER-11610 | P1 Escalation-CORs Errors at BlueBeam and Boomerang S3 Amazon domains ¦ St. Vrain |  |  | Ramani Cheruvu | In Progress | Fixed | P1 | 2026-01-08 | 2026-01-27 | 2026-04-27 | sprint-Dolly | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_reopened, p1escalation, unplanned-sprint, zendesk_enterprise |  | Removed
Escape Defect | FILTER-11964 | P1 Escalation-Extension bypass by overloading Chromebook |  |  | Dmitri Zhylienkov | Closed | Cannot Reproduce | P1 | 2026-02-04 | 2026-02-22 | 2026-02-24 | sprint-Dolly | 0 | 0 | FILTER | jira_added, jira_escalated, jira_open, p1escalation |  | Completed
Escape Defect | FILTER-12010 | P1 Escalation-Extension Bypass - Bookmark + stop page |  |  | Pratik Tiwari | Confirmation | Fixed | P1 | 2026-02-10 | 2026-04-06 | 2026-04-28 | sprint-Dolly | 20 | 0 | FILTER | jira_added, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_p1, jira_qa_verified, zendesk_enterprise, zendesk_org_at_risk |  | Removed
Escape Defect | FILTER-11985 | P1 Escalation-Extension bypass by adding a string at the end of the site |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-02-06 | 2026-02-25 | 2026-04-16 | sprint-Dolly | 27 | 12 | FILTER | jira_added, jira_closed_notify, jira_done, jira_escalated, jira_p1, jira_qa_verified, zendesk_enterprise |  | Removed
Escape Defect | FILTER-12012 | P1 Escalation-drive.google.com.108.181.32.77.sslip.io is not blocking for extension filtering |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-02-10 | 2026-03-05 | 2026-04-16 | sprint-Dolly | 0.2 | 0 | FILTER | jira_added, jira_done, jira_escalated, jira_p1, zendesk_enterprise |  | Removed