## Capacity vs Delivery
Capacity vs Delivery — FILTER · sprint-Edouard (Tue 03 Mar → Mon 16 Mar 2026)
Team Composition (per Securly-PjM-Skills.md Part 2 — Filter India roster). Inactive members for this sprint window are shaded grey with a roster note.
Name | Role | Function / Split | Allocation (FTE) | Seniority | Employment | Notes
Shashank Tiwari | Project Manager | PM / Delivery | 0 | Lead | FTE | Not counted in delivery capacity
Harsh Verma | FE | FrontEnd Architect (Angular) | 1 | Senior | FTE
Arun Thakur | FE + Ext | Angular / Extension | 1 | Medium | FTE
Harshada Kude | FE | Angular | 1 | Junior | FTE
Shailendra Singh | FE | Angular | 1 | Medium | FTE
Swaroop Chavhan | FE + Ext | Angular / Extension | 1 | Medium | FTE
Ashish Modak | BE Architect | Extension / Go / PHP | 1 | Senior | FTE
Prateek Fotedar | BE (www) | Go / PHP | 1 | Senior | FTE
Sagar Satpute | BE (www) | Go / PHP | 1 | Medium | FTE
Vaibhav Kumbhar | BE | Go / PHP | 1 | Medium | FTE
Ashish Temurnikar | BE | DNS / SPAC / Squid / Rust | 1 | Senior | FTE
Ravi Raj | BE | DNS / SPAC / Squid / Rust | 1 | Medium | FTE
Pratik Tiwari | BE + Ext | Extension / Go / Rust | 1 | Senior | FTE
Altamash Heroli | QA | Pri. Manual QA | 1 | Senior | FTE
Surabhi Choudhary | QA | Sr. Manual QA | 1 | Senior | FTE
Ayesha Kamde | QA | Manual QA | 1 | Junior | FTE
Amol Mithari | Auto QA Lead | Team Lead — Auto QA / SDET | 1 | Lead | FTE
Amit Shete | Auto QA | Pri. SDET | 1 | Senior | FTE
Rachit Mishra | Auto QA | SDET | 0 | Junior | FTE | Left team on 20-Feb-2026 — not part of this sprint
Total FILTER allocation |  |  |  | FTE-equivalent heads available to FILTER
Capacity Parameters (yellow cells are inputs — re-run the script after edits)
Parameter | Value | Description
Sprint length (working days) | 10 | FILTER 15-day sprint Tue → Mon. sprint-Edouard = 2026-03-03 → 2026-03-16.
Company holidays in sprint | 1 | India calendar 2026 — 04-Mar: Holi
Effective working days (sprint − company holidays) |  | Used as the per-person calendar for availability
Hours per working day (nominal) | 8 | Standard working day
Focus factor (productive fraction) | 0.9 | 90% — what SLT expects (sprint-analysis default)
Misc buffer (meetings, scrums, code review, …) | 20% | 20% blanket reservation deducted from Available to get Net Available
Effective hours per FTE per sprint
Allocated FTE on FILTER (active this sprint) | 17 | Headcount actually working this sprint (excludes joiners/leavers outside window)
Ideal capacity for the sprint (hrs)
Issue scope (Jira projects) | FILTER, PTGM, FDSE | Tickets pulled with `project in (FILTER, PTGM, FDSE) AND sprint = …` — FDSE: 2 · FILTER: 327 · PTGM: 4
Capacity vs Actual Delivery — sprint-Edouard
Metric | Hours | % of Ideal | Rating | Notes
Actual Availability |  |  |  | Sum of per-person availability (Ideal − leaves)
Misc Buffer (20%) |  |  |  | Reserved for meetings, scrums, code reviews
Net Available (Available − Misc Buffer) |  |  |  | Realistic delivery capacity — used as the denominator for Completed %
Completed |  |  |  | Sum of in-sprint timeSpent (Completed bucket)
Not Completed (Spillover) |  |  |  | Original estimate for spillover (carried into next sprint)
Removed |  |  |  | Original estimate for issues removed mid-sprint
Completed by Priority
Tickets (parents) = unique parent items (Story / Task / Defect / Escape Defect) — subtasks roll up to their parent so 1 parent + 3 subtasks = 1 ticket. Tickets (incl. subtasks) = raw record count incl. every Dev / QA / Automation / Review / Test Case Creation / Debug subtask. Hours = sum across parents and subtasks; matches the core-team Completed hours on the Per-person Delivery sheet.
Priority | Tickets (parents) | Tickets (incl. subtasks) | Hours (incl. subtasks) | % of Completed Hrs | % of Tickets (parents) | Notes
P0 | 1 | 2 | 13 |  |  | Critical / production halting
P1 | 16 | 36 | 167 |  |  | P1 — high priority (see P1 Escalation tab for escalations)
P2 | 20 | 48 | 378.5 |  |  | Major
P3 | 40 | 98 | 902.5 |  |  | Standard
P4 | 4 | 8 | 47 |  |  | Minor / nice-to-have
TOTAL | 81 | 192 | 1508 | 100% | 100% | Sum of Completed bucket (core roster)
Sprint Completion (spillover = Not Completed)
Metric | Tickets | Planned Hrs (OE) | % by Tickets | % by Hrs | Notes
Completed (closed in sprint) | 192 | 1417 |  |  | In-sprint deliverables
Spillover (not completed → carry-over) | 28 | 128 |  |  | Original estimate carried to next sprint
Removed (mid-sprint scope cut) | 9 | 92 | — | — | Excluded from completion ratio (out of scope)
Mid-sprint additions (core) | 18 |  | — | — | Late-arriving work (Jira issueKeysAddedDuringSprint)
Sprint completion rate (tickets) | 87.27% | On Target | Completed ÷ (Completed + Spillover)
Sprint completion rate (planned hrs) | 91.72% | On Target | Σ OE Completed ÷ Σ OE (Completed + Spillover)
Planned completion rate (tickets, excludes mid-sprint adds) | 86.83% | On Target | Originally-committed tickets only
Planned completion rate (planned hrs, excludes mid-sprint adds) | 91.36% | On Target | Originally-committed planned hours only
P1 Escalation snapshot
11 ticket(s) in sprint-Edouard match 'P1 Escalation' in the title — 9 closed, 2 still open. See the 'P1 Escalation' tab.
Mid-sprint additions snapshot
18 ticket(s) were added to sprint-Edouard after it started (issueKeysAddedDuringSprint) — Completed 14, Spillover 1, Removed 3. Highlighted in amber on every detail sheet (Added Mid-Sprint = YES).
Assumptions & caveats
• Sprint window from Jira (/rest/agile/1.0/sprint/5298): 2026-03-03 → 2026-03-16 (10 Mon–Fri working days). Refresh with fetch_filter_sprint_meta.py + fetch_filter_sprint_issues.py.
• Issues pulled from FILTER + PTGM + FDSE (project-scope expanded for the India scrum team's split across the three products).
• Date-aware roster: Amol Mithari joined 20-Feb-2026; Rachit Mishra's last day was 20-Feb-2026. Inactive members for this sprint window are shaded grey in the Team Composition table and excluded from per-person availability + delivery.
• Available (hrs) = (effective working days − leave days) × 8 × focus factor, where effective working days = sprint working days − company holidays falling inside the sprint − days outside the person's employment window. Per-person Delivery shows leave days in Column G to explain the delta from a full sprint.
• Net Available = Available − 20% Misc Buffer for meetings, scrums, code review, etc. Completed/Not Completed/Removed % of capacity use Net Available as the denominator.
• Time Spent on Completed sheet uses the in-sprint hybrid worklog rule (sprint-analysis.md): single-sprint = timespent; multi-sprint = SUM of worklogs whose started ∈ [sprintStart, sprintEnd].
• Not Completed and Removed totals use Original Estimate.
• Removed list comes from the Sprint Report puntedIssues (greenhopper API).
• Core roster only: assignees outside Securly-PjM-Skills.md Part 2 are dropped from per-person + detail sheets.
• P1 Escalation tab is filtered to Issue Type = Escape Defect AND Priority = P1 AND title contains 'P1 Escalation'.
• Completed by Priority — Tickets (parents) rolls subtasks up to their parent (each work item counted once at its parent priority); Tickets (incl. subtasks) shows the raw record count for comparison. The Hours column sums every record (parent + subtasks) and matches the core-team Completed total.
• Spillover = Not Completed bucket (tickets carried into the next sprint).
• Sprint completion rate uses Completed ÷ (Completed + Spillover); Removed tickets are excluded (treated as scope cut). 'Planned' rate also excludes mid-sprint additions.
• All detail sheets (Completed, Not Completed, Removed) highlight tickets added after sprint start (Jira sprint-report issueKeysAddedDuringSprint) in amber, with an 'Added Mid-Sprint = YES' tag column.
• Ratings: ≥85% On Target (green), 70–85% Below Target (amber), <70% Significantly Below (red).

## Per-person Delivery
Assignee | Completed (hrs) | Not Completed (hrs) | Removed (hrs) | Efficiency | Available (hrs) | Leave Days (sprint) | Misc Buffer 20% (hrs) | Net Available (hrs)
Harsh Verma | 56 | 0 | 32 |  | 64.8 | 0
Arun Thakur | 49 | 42 | 4 |  | 64.8 | 0
Harshada Kude | 116 | 0 | 0 |  | 64.8 | 0
Shailendra Singh | 131 | 0 | 0 |  | 64.8 | 0
Swaroop Chavhan | 20 | 0 | 52 |  | 64.8 | 0
Ashish Modak | 40 | 0 | 0 |  | 64.8 | 0
Prateek Fotedar | 130.5 | 32 | 0 |  | 57.6 | 1
Sagar Satpute | 137 | 0 | 0 |  | 50.4 | 2
Vaibhav Kumbhar | 101 | 0 | 4 |  | 64.8 | 0
Ashish Temurnikar | 78 | 8 | 0 |  | 64.8 | 0
Ravi Raj | 100 | 0 | 0 |  | 57.6 | 1
Pratik Tiwari | 70 | 0 | 0 |  | 64.8 | 0
Altamash Heroli | 188 | 0 | 0 |  | 64.8 | 0
Surabhi Choudhary | 136 | 20 | 0 |  | 50.4 | 2
Ayesha Kamde | 72.5 | 22 | 0 |  | 64.8 | 0
Amol Mithari | 10.5 | 0 | 0 |  | 57.6 | 1
Amit Shete | 72.5 | 4 | 0 |  | 64.8 | 0
TOTAL

## Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Task | FILTER-12389 | P0 Escalation-[Extension] Youtube keyword blocking is not working |  |  | Ashish Modak | RELEASED TO PROD | Fixed | P0 | 2026-03-09 | 2026-03-09 | 2026-03-19 | sprint-Edouard | 8 | 8 | FILTER | jira_added, jira_escalated, zendesk_enterprise |  | YES
Task | FILTER-12402 | Fix dependabot alerts for Extensions repositories |  |  | Ashish Modak | Resolved |  | P3 | 2026-03-10 |  | 2026-03-13 | sprint-Edouard | 8 | 8 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12079 | POC – Send URL data from Squid to PageScan for categorization (US clusters, Event Bus + Lambda) |  |  | Ashish Temurnikar | Closed |  | P1 | 2026-02-17 |  | 2026-03-18 | sprint-Edouard | 8 | 0 | FILTER | 2026-Tech-debt |  | YES
Task | FILTER-12486 | [sprox] Refactor broker URL handling: only strip broker hash when request is not from redirect | FILTER-8230 | Epic | Ashish Temurnikar | Closed |  | P3 | 2026-03-16 |  | 2026-04-09 | sprint-Edouard | 16 | 16 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-12490 | [sprox] Transparent TLS – cert chain + SNI for upstream | FILTER-8230 | Epic | Ashish Temurnikar | Closed |  | P3 | 2026-03-16 |  | 2026-04-09 | sprint-Edouard | 16 | 16 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-12499 | Tracking card for Accessibilty related work |  |  | Harsh Verma | Resolved |  | P3 | 2026-03-16 |  | 2026-03-16 | sprint-Edouard | 16 | 16 | FILTER | unplanned-sprint |  | YES
Story | FILTER-12293 | [Filter] Translations for Spanish & French - Json Creation & Verify | FILTER-12099 | Epic | Harshada Kude | RELEASED TO PROD |  | P3 | 2026-02-27 |  | 2026-04-27 | sprint-Edouard | 24 | 0 | FILTER | unplanned-sprint |  | YES
Story | FILTER-12305 | [Filter] Consumption of json Translations in Settings | FILTER-12099 | Epic | Harshada Kude | RELEASED TO PROD |  | P3 | 2026-03-02 |  | 2026-04-27 | sprint-Edouard | 10.5 | 0 | FILTER |  |  | YES
Story | FILTER-12311 | [Filter] Cross check Filter Application Other Remaining instances of ¦ translate or instant | FILTER-12099 | Epic | Harshada Kude | RELEASED TO PROD |  | P3 | 2026-03-02 |  | 2026-04-27 | sprint-Edouard | 18.5 | 0 | FILTER |  |  | YES
Task | FILTER-12372 | Update Query to consider the current quarter only, instead of the last 90 days, when deleting the data |  |  | Sagar Satpute | Closed |  | P3 | 2026-03-06 |  | 2026-04-16 | sprint-Edouard | 5 | 0 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12200 | SPROX Manual Testing | FILTER-8230 | Epic | Surabhi Choudhary | QA Verified |  | P2 | 2026-02-25 |  | 2026-04-25 | sprint-Edouard | 24 | 0 | FILTER |  |  | YES
Task | FILTER-12365 | Tracking card for AICHAT tasks |  |  | Swaroop Chavhan | Resolved | Fixed | P3 | 2026-03-05 | 2026-03-17 | 2026-03-17 | sprint-Edouard | 10 | 10 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12375 | Helping team with PR reviews, Accessibility |  |  | Swaroop Chavhan | Resolved | Fixed | P3 | 2026-03-06 | 2026-03-16 | 2026-03-16 | sprint-Edouard | 10 | 10 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-12532 | [Debug]AI Testing POC using cursor browser automation/ agent browser |  |  | Vaibhav Kumbhar | Closed without action |  | P3 | 2026-03-17 |  | 2026-03-17 | sprint-Edouard | 16 | 0 | FILTER | unplanned-sprint |  | YES
QA | FILTER-11376 | Manual QA Validation for Account Deletion Server Error in Support Tool | FILTER-10728 | Escape Defect | Altamash Heroli | Done |  | P3 | 2025-12-09 |  | 2026-03-26 | sprint-Edouard | 4 | 3 | FILTER
QA | FILTER-11835 | End to End Custom List functionality validation for Support Tool | FILTER-11827 | Story | Altamash Heroli | QA Verified |  | P3 | 2026-01-29 |  | 2026-04-14 | sprint-Edouard | 22 | 20 | FILTER | Capitalized-Feature
QA | FILTER-11858 | Verify Clone CustomList API validates "usage" field correctly | FILTER-11789 | Defect | Altamash Heroli | Closed without action |  | P2 | 2026-01-29 |  | 2026-03-03 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-11864 | Verify XSS Sanitization in SafetyConsole Custom List API (POST & PUT) | FILTER-11734 | Defect | Altamash Heroli | Closed without action |  | P2 | 2026-01-29 |  | 2026-03-03 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-11867 | Verify XSS sanitization fix for SafetyConsole Custom List API (POST/PUT) | FILTER-11732 | Defect | Altamash Heroli | Closed without action |  | P2 | 2026-01-29 |  | 2026-03-03 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-11870 | Verify XSS Sanitization for Resource Notes in Custom List API (POST/PUT) | FILTER-11731 | Defect | Altamash Heroli | Closed without action |  | P3 | 2026-01-29 |  | 2026-03-03 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-11876 | Verify XSS vulnerability fix in SafetyConsole Get CustomList API | FILTER-11767 | Defect | Altamash Heroli | Closed without action |  | P3 | 2026-01-29 |  | 2026-03-03 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-11884 | HACKERONE - Verify Server-Side Authorization Fix for Policy Editor and Advanced Report Features | FILTER-10347 | Defect | Altamash Heroli | Done |  | P3 | 2026-01-29 |  | 2026-03-26 | sprint-Edouard | 6 | 6 | FILTER
QA | FILTER-11886 | BUGCROWD - Verify Fix for Open Redirect Vulnerability in Logout Endpoint | FILTER-11806 | Defect | Altamash Heroli | Done |  | P3 | 2026-01-29 |  | 2026-03-26 | sprint-Edouard | 5 | 3 | FILTER
QA | FILTER-11888 | BUGCROWD - Verify Fix for Open Redirect Vulnerability in smart.pac Endpoint | FILTER-11802 | Defect | Altamash Heroli | Done |  | P3 | 2026-01-29 |  | 2026-03-26 | sprint-Edouard | 3 | 3 | FILTER
QA | FILTER-11890 | BUGCROWD - Verify Fix for Open Redirect Vulnerability in clean-cookies API | FILTER-11782 | Defect | Altamash Heroli | Done |  | P3 | 2026-01-29 |  | 2026-03-26 | sprint-Edouard | 3 | 3 | FILTER
QA | FILTER-11892 | BUGCROWD - Verify Fix for Open Redirect Vulnerability in /geo Endpoint | FILTER-11778 | Defect | Altamash Heroli | Done |  | P3 | 2026-01-29 |  | 2026-03-26 | sprint-Edouard | 3 | 3 | FILTER
Story | FILTER-11974 | Verify all Image Blur test cases for JS | FILTER-11972 | Epic | Altamash Heroli | Done |  | P2 | 2026-02-05 |  | 2026-04-15 | sprint-Edouard | 55 | 65 | FILTER
QA | FILTER-12057 | QA- Category Look up drawer gives Error on URL check | FILTER-12055 | Defect | Altamash Heroli | Done |  | P3 | 2026-02-13 |  | 2026-03-26 | sprint-Edouard | 2 | 1 | FILTER
QA | FILTER-12166 | Filter blocks W3Schools-style sandbox bypass via CDN/iframe (jsdelivr, Vercel, W3Spaces) | FILTER-12093 | Escape Defect | Altamash Heroli | Done |  | P1 | 2026-02-24 |  | 2026-04-06 | sprint-Edouard | 5 | 6 | FILTER
QA | FILTER-12169 | Deny list applies to Google Docs/Slides when URL contains scrlybrkr parameter | FILTER-11893 | Escape Defect | Altamash Heroli | Done |  | P2 | 2026-02-24 |  | 2026-03-26 | sprint-Edouard | 9 | 8 | FILTER
QA | FILTER-12184 | Verify POC – Squid URL data to PageScan via Event Bus + Lambda (US clusters) | FILTER-12079 | Task | Altamash Heroli | Closed without action |  | P1 | 2026-02-25 |  | 2026-03-06 | sprint-Edouard | 0 | 0 | FILTER
QA | FILTER-12196 | [BugCrowd] Verify unauthenticated beta FID API is removed and beta FID controls are secure | FILTER-12003 | Defect | Altamash Heroli | Done |  | P3 | 2026-02-25 |  | 2026-04-14 | sprint-Edouard | 1.5 | 4 | FILTER
QA | FILTER-12271 | QA- CLONE - JS (Windows+ Edge) Extensions. Securly Filter Dashboard YT videos thumbnails are blurred | FILTER-12269 | Defect | Altamash Heroli | Closed without action |  | P1 | 2026-02-26 |  | 2026-03-17 | sprint-Edouard | 0 | 0 | FILTER
QA | FILTER-12287 | Verify all Image Blur test cases for JS | FILTER-11974 | Story | Altamash Heroli | Done |  | P3 | 2026-02-27 |  | 2026-04-12 | sprint-Edouard | 55 | 65 | FILTER
QA | FILTER-12339 | Verify deactivated GAC user (tfisher@d84.org) no longer appears in extension logs/reports | FILTER-12300 | Escape Defect | Altamash Heroli | Closed without action |  | P2 | 2026-03-03 |  | 2026-03-23 | sprint-Edouard | 0 | 0 | FILTER
QA | FILTER-12347 | Verify getSchoolAccounts returns sub-domains for school accounts | FILTER-4949 | Task | Altamash Heroli | Done |  | P2 | 2026-03-03 |  | 2026-03-17 | sprint-Edouard | 1 | 1 | FILTER
QA | FILTER-12350 | Verify Support Tool FID search and display (all FIDs, including no-domain) | FILTER-5401 | Task | Altamash Heroli | Done |  | P3 | 2026-03-03 |  | 2026-04-14 | sprint-Edouard | 1 | 2 | FILTER
QA | FILTER-12353 | Verify Support Tool search includes FIDs with no domain/sub-domain | FILTER-5679 | Task | Altamash Heroli | Done |  | P3 | 2026-03-03 |  | 2026-04-21 | sprint-Edouard | 2 | 2 | FILTER
QA | FILTER-12371 | QA- Unable to add domains to Filter via Filter UI or Support Tool | FILTER-12369 | Escape Defect | Altamash Heroli | Done |  | P1 | 2026-03-06 |  | 2026-03-29 | sprint-Edouard | 3 | 4 | FILTER
QA | FILTER-12528 | Verify Translations for Spanish & French | FILTER-12293 | Story | Altamash Heroli | Done |  | P3 | 2026-03-17 |  | 2026-04-21 | sprint-Edouard | 6 | 6 | FILTER
QA | FILTER-12529 | Verify Consumption of json Translations in Settings | FILTER-12305 | Story | Altamash Heroli | QA Verified |  | P3 | 2026-03-17 |  | 2026-04-09 | sprint-Edouard | 0.5 | 3 | FILTER
QA | FILTER-12530 | Verify Consumption of json Translations in Policy Map | FILTER-12307 | Story | Altamash Heroli | QA Verified |  | P3 | 2026-03-17 |  | 2026-04-09 | sprint-Edouard | 0.5 | 6 | FILTER
QA | FILTER-12531 | Cross check Filter Application Other Remaining instances of ¦ translate or instant | FILTER-12311 | Story | Altamash Heroli | QA Verified |  | P3 | 2026-03-17 |  | 2026-04-09 | sprint-Edouard | 0.5 | 10 | FILTER
Automation | FILTER-11146 | Validate Click Prevention on Blurred YouTube Thumbnails | FILTER-10631 | Defect | Amit Shete | Done |  | P2 | 2025-12-02 |  | 2026-03-18 | sprint-Edouard | 6 | 6 | FILTER
Automation | FILTER-11375 | Automated E2E Regression Test: Validate Account Deletion Functionality in Support Tool | FILTER-10728 | Escape Defect | Amit Shete | Done |  | P3 | 2025-12-09 |  | 2026-03-03 | sprint-Edouard | 5 | 6 | FILTER
Automation | FILTER-11537 | New Feature ¦ Automation Suite Development (Tokenization & Resilience) | FILTER-11532 | Story | Amit Shete | Closed without action |  | P3 | 2025-12-19 |  | 2026-04-28 | sprint-Edouard | 0 | 6 | FILTER | Capitalized-Feature
Automation | FILTER-11660 | Create Automated Tests for FluentD Tokenization Phase 3 (UserToken) | FILTER-11631 | Story | Amit Shete | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Edouard | 6 | 6 | FILTER | Capitalized-Feature
Automation | FILTER-11836 | Create an Automation suite to Validate End to End functionality of custom list for support tool | FILTER-11827 | Story | Amit Shete | Done |  | P3 | 2026-01-29 |  | 2026-04-28 | sprint-Edouard | 6 | 6 | FILTER | Capitalized-Feature
Automation | FILTER-11845 | Add test cases for SafetyConsole CustomList API token invalidation | FILTER-11687 | Defect | Amit Shete | Done |  | P2 | 2026-01-29 |  | 2026-04-14 | sprint-Edouard | 4 | 4 | FILTER
Automation | FILTER-11859 | Add test coverage for Clone CustomList API usage field validation | FILTER-11789 | Defect | Amit Shete | Done |  | P2 | 2026-01-29 |  | 2026-03-16 | sprint-Edouard | 4 | 4 | FILTER
Automation | FILTER-11865 | Add API Tests for XSS Sanitization in Custom List Notes Fields | FILTER-11734 | Defect | Amit Shete | Done |  | P2 | 2026-01-29 |  | 2026-03-16 | sprint-Edouard | 4 | 4 | FILTER
Automation | FILTER-11868 | Add XSS sanitization test cases for Custom List API (POST/PUT) | FILTER-11732 | Defect | Amit Shete | Done |  | P2 | 2026-01-29 |  | 2026-03-16 | sprint-Edouard | 6 | 6 | FILTER
Automation | FILTER-11871 | Add API Tests for XSS Sanitization in Custom List Resource Notes | FILTER-11731 | Defect | Amit Shete | Done |  | P3 | 2026-01-29 |  | 2026-03-16 | sprint-Edouard | 5 | 5 | FILTER
Automation | FILTER-11874 | Add tests for CustomList API token invalidation on Filter Product disable | FILTER-11688 | Escape Defect | Amit Shete | Done |  | P3 | 2026-01-29 |  | 2026-04-14 | sprint-Edouard | 4 | 4 | FILTER
Automation | FILTER-11877 | Add XSS security tests for SafetyConsole Get CustomList API | FILTER-11767 | Defect | Amit Shete | Done |  | P3 | 2026-01-29 |  | 2026-03-16 | sprint-Edouard | 4 | 4 | FILTER
Automation | FILTER-11975 | Run all automated Image Blur test cases and confirm results to support release readiness decision for the new NSFW model (MobileNetV2). | FILTER-11974 | Story | Amit Shete | Done |  | P2 | 2026-02-05 |  | 2026-03-02 | sprint-Edouard | 2 | 3 | FILTER
Automation | FILTER-12080 | Automation task to validate the fix | FILTER-11812 | Defect | Amit Shete | Done |  | P3 | 2026-02-17 |  | 2026-03-17 | sprint-Edouard | 1 | 1 | FILTER | Capitalized-Feature
Automation | FILTER-12088 | QA- Policy Editor: When multiple custom lists are linked, deleting a URL from one custom list does not copy remaining URLs to the policy after unlink | FILTER-12086 | Defect | Amit Shete | Done |  | P3 | 2026-02-18 |  | 2026-03-20 | sprint-Edouard | 1 | 1 | FILTER | Capitalized-Feature
Task | FILTER-12117 | Create a Automation to test publish/Unpublish API | FILTER-3618 | Epic | Amit Shete | Code Review |  | P3 | 2026-02-20 |  | 2026-04-28 | sprint-Edouard | 0 | 6 | FILTER | Capitalized-Feature
Automation | FILTER-12167 | Sandbox bypass prevention – iframe/CDN block (W3Schools-style) | FILTER-12093 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-02-24 |  | 2026-04-06 | sprint-Edouard | 0 | 5 | FILTER
Automation | FILTER-12170 | Deny-list matching with scrlybrkr-normalized Google Docs URLs | FILTER-11893 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-02-24 |  | 2026-03-17 | sprint-Edouard | 0 | 4 | FILTER
Automation | FILTER-12187 | Scripting for GO broker SSO cookie and JWT auth regression | FILTER-12048 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-02-25 |  | 2026-04-20 | sprint-Edouard | 0 | 8 | FILTER
Automation | FILTER-12201 | SPROX Testing with P0 suite | FILTER-12199 | Task | Amit Shete | Done |  | P2 | 2026-02-25 |  | 2026-04-14 | sprint-Edouard | 4.5 | 8 | FILTER
Automation | FILTER-12340 | Scripting for “deactivated GAC user not in extension logs” verification | FILTER-12300 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-03-03 |  | 2026-03-23 | sprint-Edouard | 0 | 0 | FILTER
Automation | FILTER-12348 | Scripting for getSchoolAccounts sub-domains response | FILTER-4949 | Task | Amit Shete | Closed without action |  | P2 | 2026-03-03 |  | 2026-03-17 | sprint-Edouard | 0 | 0 | FILTER
Automation | FILTER-12351 | Scripting for Support Tool FID search and display (all FIDs, no-domain included) | FILTER-5401 | Task | Amit Shete | Done |  | P3 | 2026-03-03 |  | 2026-03-31 | sprint-Edouard | 4 | 5 | FILTER
Automation | FILTER-12354 | Scripting for Support Tool search including FIDs with no domain/sub-domain | FILTER-5679 | Task | Amit Shete | Closed without action |  | P3 | 2026-03-03 |  | 2026-03-31 | sprint-Edouard | 0 | 0 | FILTER
Automation | FILTER-12364 | Scripting for Support Tool IP add and Redis DB4 persistence | FILTER-11913 | Escape Defect | Amit Shete | Closed without action |  | P3 | 2026-03-04 |  | 2026-03-17 | sprint-Edouard | 0 | 0 | FILTER
Automation | FILTER-12502 | QA- Tracking card for Accessibilty related work | FILTER-12499 | Debug | Amit Shete | Closed without action |  | P3 | 2026-03-16 |  | 2026-03-16 | sprint-Edouard | 0 | 0 | FILTER
Automation | FILTER-12562 | Re-run SPROX Testing with P0 suite post Dev Fixes | FILTER-12199 | Task | Amit Shete | Done |  | P2 | 2026-03-18 |  | 2026-04-14 | sprint-Edouard | 6 | 6 | FILTER
Automation | FILTER-11997 | Add tests for extension filter bypass — URLs with /?scrlcbp=. must be blocked | FILTER-11985 | Escape Defect | Amol Mithari | Done |  | P1 | 2026-02-09 |  | 2026-03-16 | sprint-Edouard | 6 | 6 | FILTER
Automation | FILTER-12015 | Add tests for extension blocking of drive.google.com.108.181.32.77.sslip.io (Network Misuse / global block) | FILTER-12012 | Escape Defect | Amol Mithari | Done |  | P1 | 2026-02-10 |  | 2026-03-12 | sprint-Edouard | 4.5 | 6 | FILTER
Dev | FILTER-11355 | Reopened - Fix Unwanted 'Ask for Leaving Page' Popup on Search Sites When Overlay is Enabled | FILTER-10558 | Escape Defect | Arun Thakur | Closed without action |  | P2 | 2025-12-08 |  | 2026-04-14 | sprint-Edouard | 3 | 8 | FILTER
Dev | FILTER-11374 | Fix Unhandled Backend Error When Deleting Filter Account via Support Tool | FILTER-10728 | Escape Defect | Arun Thakur | Done |  | P3 | 2025-12-09 |  | 2026-03-03 | sprint-Edouard | 8 | 8 | FILTER
Dev | FILTER-11846 | GIF on Mouse Hover Becomes Visible and Clickable When Blur is Applied | FILTER-11033 | Defect | Arun Thakur | Closed without action |  | P2 | 2026-01-29 |  | 2026-04-06 | sprint-Edouard | 10 | 8 | FILTER
Dev | FILTER-12133 | DEV - JS Extn (Chromebook) : Image Blur Not Working for GIF Content on Tenor and Giphy | FILTER-12132 | Defect | Arun Thakur | Done |  | P3 | 2026-02-23 |  | 2026-03-05 | sprint-Edouard | 8 | 8 | FILTER
Dev | FILTER-12137 | DEV - JS Extn (Chromebook) : Different Probability Scores for Same Image (Thumbnail vs Full Image) Causing Inconsistent Blur Behavior on Google Search | FILTER-12136 | Defect | Arun Thakur | Closed without action |  | P2 | 2026-02-23 |  | 2026-03-05 | sprint-Edouard | 0 | 0 | FILTER
Dev | FILTER-12154 | JS (All Extensions): Esc Button is circumventing image blur | FILTER-12153 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-02-24 |  | 2026-03-23 | sprint-Edouard | 0 | 0 | FILTER
Dev | FILTER-12229 | DEV - JS (All Extensions): Youtube.YT logo on YT page, YT search page, YT video page and YT shorts is not clickable | FILTER-12228 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-02-25 |  | 2026-04-15 | sprint-Edouard | 0 | 0 | FILTER
Dev | FILTER-12266 | DEV - JS (All Extensions): Securly Filter Dashboard YT videos thumbnails are blurred | FILTER-12265 | Defect | Arun Thakur | Closed without action |  | P2 | 2026-02-26 |  | 2026-04-06 | sprint-Edouard | 0 | 0 | FILTER
Dev | FILTER-12270 | DEV - CLONE - JS (Windows+ Edge) Extensions. Securly Filter Dashboard YT videos thumbnails are blurred | FILTER-12265 | Defect | Arun Thakur | Done |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Edouard | 4 | 4 | FILTER
Dev | FILTER-12273 | DEV - CLONE - JS (Windows+ Edge) Extensions. SFW images are also getting blurred by the model | FILTER-12272 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Edouard | 0 | 0 | FILTER
Dev | FILTER-12276 | DEV - CLONE - JS (Windows+ Edge) Extensions. Image Blur. Amazon.com is accessible but links/logo/dropdowns not clickable | FILTER-12272 | Defect | Arun Thakur | Done |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Edouard | 6 | 6 | FILTER
Dev | FILTER-12279 | DEV -JS (All Extensions) Image Blur on Search sites is bluring non blurred images on click | FILTER-12278 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-02-26 |  | 2026-03-23 | sprint-Edouard | 0 | 0 | FILTER
Dev | FILTER-12285 | DEV - JS (All Extensions) image blur on GDrive. blurred images can be accessed by accessing unblurred images | FILTER-12284 | Defect | Arun Thakur | Done |  | P1 | 2026-02-26 |  | 2026-04-08 | sprint-Edouard | 10 | 10 | FILTER
Dev | FILTER-12394 | DEV - DA Filter >> Activities. DA is able to see activities of kids from other OU as well | FILTER-12393 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-03-09 |  | 2026-04-14 | sprint-Edouard | 0 | 4 | FILTER
Dev | FILTER-12385 | Dev Task to Analysis reopen issue for FITLER-10034 | FILTER-10034 | Escape Defect | Ashish Modak | Done |  | P1 | 2026-03-09 |  | 2026-03-13 | sprint-Edouard | 16 | 16 | FILTER
Dev | FILTER-12430 | Dev task to Fix dependabot alerts for Extensions repositories | FILTER-12402 | Task | Ashish Modak | Done |  | P3 | 2026-03-12 |  | 2026-03-17 | sprint-Edouard | 8 | 8 | FILTER
Dev | FILTER-11994 | New Feature ¦ DNS and SPAC changes for Tokenization | FILTER-11532 | Story | Ashish Temurnikar | Done |  | P3 | 2026-02-09 |  | 2026-04-14 | sprint-Edouard | 20 | 10 | FILTER | Capitalized-Feature
Dev | FILTER-12183 | POC: Send URL data from Squid to PageScan via AWS Event Bus + Lambda (US clusters) | FILTER-12079 | Task | Ashish Temurnikar | Closed without action |  | P1 | 2026-02-25 |  | 2026-03-17 | sprint-Edouard | 8 | 8 | FILTER
Dev | FILTER-12382 | [Squid] OU not getting logged with OS preference is 0 | FILTER-12017 | Escape Defect | Ashish Temurnikar | Done |  | P3 | 2026-03-09 |  | 2026-03-10 | sprint-Edouard | 10 | 8 | FILTER
QA | FILTER-11149 | Manual QA Validation for "Leaving Page" Popup on Search Engines (Overlay Enabled) | FILTER-10558 | Escape Defect | Ayesha Kamde | Done |  | P2 | 2025-12-02 |  | 2026-04-21 | sprint-Edouard | 3 | 3 | FILTER
QA | FILTER-11227 | Manual QA Validation for False Positive Block on Google Search Embeds (CRXTN) | FILTER-10034 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2025-12-03 |  | 2026-02-04 | sprint-Edouard | 5 | 5 | FILTER
QA | FILTER-11684 | QA Task | FILTER-11482 | Escape Defect | Ayesha Kamde | Done |  | P3 | 2026-01-16 |  | 2026-03-26 | sprint-Edouard | 3 | 2 | FILTER
QA | FILTER-11847 | Verify Fix for GIF Hover Visibility and Clickability Issue on Blurred Content | FILTER-11033 | Defect | Ayesha Kamde | Done |  | P2 | 2026-01-29 |  | 2026-04-08 | sprint-Edouard | 2 | 2 | FILTER
QA | FILTER-11897 | Vector Expansion - Verify if http://kiddle/co/ is added to search scanning | FILTER-11895 | Story | Ayesha Kamde | Done |  | P2 | 2026-01-29 |  | 2026-04-06 | sprint-Edouard | 5 | 6 | FILTER
QA | FILTER-11996 | Verify bypass fix for /?scrlcbp=. on blocked sites | FILTER-11985 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2026-02-09 |  | 2026-03-05 | sprint-Edouard | 9 | 2 | FILTER
QA | FILTER-12102 | Regression and translation checking for Dashboard page only for all 3 languages English, French and Spanish | FILTER-12100 | Story | Ayesha Kamde | Closed without action |  | P3 | 2026-02-19 |  | 2026-03-29 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-12134 | QA- JS Extn (Chromebook) : Image Blur Not Working for GIF Content on Tenor and Giphy | FILTER-12132 | Defect | Ayesha Kamde | Done |  | P3 | 2026-02-23 |  | 2026-03-09 | sprint-Edouard | 3 | 3 | FILTER
QA | FILTER-12138 | QA- JS Extn (Chromebook) : Different Probability Scores for Same Image (Thumbnail vs Full Image) Causing Inconsistent Blur Behavior on Google Search | FILTER-12136 | Defect | Ayesha Kamde | Closed without action |  | P2 | 2026-02-23 |  | 2026-03-06 | sprint-Edouard | 0 | 0 | FILTER
QA | FILTER-12230 | QA- JS (All Extensions): Youtube.YT logo on YT page, YT search page, YT video page and YT shorts is not clickable | FILTER-12228 | Defect | Ayesha Kamde | Done |  | P1 | 2026-02-25 |  | 2026-04-20 | sprint-Edouard | 1.5 | 2 | FILTER
QA | FILTER-12267 | QA- JS (All Extensions): Securly Filter Dashboard YT videos thumbnails are blurred | FILTER-12265 | Defect | Ayesha Kamde | Done |  | P2 | 2026-02-26 |  | 2026-04-06 | sprint-Edouard | 2 | 2 | FILTER
QA | FILTER-12274 | JS (All Extensions) Image Blur. Amazon.com is accessible but links/logo/dropdowns not clickable | FILTER-12272 | Defect | Ayesha Kamde | Done |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Edouard | 2 | 2 | FILTER
QA | FILTER-12280 | QA- JS (All Extensions) Image Blur on Search sites is bluring non blurred images on click | FILTER-12278 | Defect | Ayesha Kamde | Closed without action |  | P1 | 2026-02-26 |  | 2026-03-24 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-12286 | QA- JS (All Extensions) image blur on GDrive. blurred images can be accessed by accessing unblurred images | FILTER-12284 | Defect | Ayesha Kamde | Done |  | P1 | 2026-02-26 |  | 2026-04-21 | sprint-Edouard | 1 | 2 | FILTER
QA | FILTER-12288 | Verify all Image Blur test cases for JS | FILTER-11974 | Story | Ayesha Kamde | Done |  | P3 | 2026-02-27 |  | 2026-03-03 | sprint-Edouard | 25 | 5 | FILTER
QA | FILTER-12403 | QA task for testing P0 Escalation-[Edge Extn mainly + KS Chrome Extn] Youtube keyword blocking is not working | FILTER-12389 | Task | Ayesha Kamde | Done |  | P0 | 2026-03-10 |  | 2026-03-10 | sprint-Edouard | 5 | 5 | FILTER
QA | FILTER-12419 | QA task to test reopen issue for FILTER-10034 | FILTER-10034 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2026-03-12 |  | 2026-03-13 | sprint-Edouard | 6 | 6 | FILTER
Task | FILTER-12291 | Helping classroom team for PR review and Technical discussions |  |  | Harsh Verma | Resolved |  | P3 | 2026-02-27 |  | 2026-03-18 | sprint-Edouard | 8 | 4 | FILTER | unplanned-sprint
Task | FILTER-12292 | Helping Home Team for the overall architecture of Parent Portal design Revamp and and AI Chat for their dashobard requirement |  |  | Harsh Verma | Resolved |  | P3 | 2026-02-27 |  | 2026-03-18 | sprint-Edouard | 32 | 24 | FILTER | unplanned-sprint
QA | FILTER-12501 | QA- Tracking card for Accessibilty related work | FILTER-12499 | Debug | Harsh Verma | Closed without action |  | P3 | 2026-03-16 |  | 2026-03-16 | sprint-Edouard | 0 | 0 | FILTER
Dev | FILTER-11990 | Phase 2: Fixing Dependabot Issues for Filter | FILTER-11742 | Task | Harshada Kude | Done |  | P3 | 2026-02-09 |  | 2026-03-03 | sprint-Edouard | 5 | 6 | FILTER
Dev | FILTER-12101 | Dev changes needed to migrate the code for Dashboard page | FILTER-12100 | Story | Harshada Kude | Closed without action |  | P3 | 2026-02-19 |  | 2026-03-18 | sprint-Edouard | 0 | 24 | FILTER
Dev | FILTER-12294 | Translations for Spanish & French - Json Creation & Verify | FILTER-12293 | Story | Harshada Kude | Done |  | P3 | 2026-02-27 |  | 2026-04-06 | sprint-Edouard | 18 | 16 | FILTER
Dev | FILTER-12306 | [Filter] Creation & Consumption of json Translations in Settings | FILTER-12305 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Edouard | 10 | 8 | FILTER
Dev | FILTER-12308 | [Filter] Creation & Consumption of json Translations in Remaining portion of Policy Map | FILTER-12307 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Edouard | 12 | 10 | FILTER
Dev | FILTER-12310 | [Filter] Cross check Filter Application Other Remaining instances of ¦ translate or instant - Part 2 | FILTER-12311 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Edouard | 12 | 10 | FILTER
Dev | FILTER-12312 | [Filter] Cross check Filter Application Other Remaining instances of ¦ translate or instant | FILTER-12311 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Edouard | 6 | 6 | FILTER
Dev | FILTER-11533 | New Feature ¦ Implement UserToken Retrieval for Signed-In Users | FILTER-11532 | Story | Prateek Fotedar | Done |  | P3 | 2025-12-19 |  | 2026-04-14 | sprint-Edouard | 15 | 15 | FILTER | Capitalized-Feature
Dev | FILTER-11535 | New Feature ¦ Tokenization Error Recovery & Fallback Logic | FILTER-11532 | Story | Prateek Fotedar | Done |  | P3 | 2025-12-19 |  | 2026-04-14 | sprint-Edouard | 35 | 35 | FILTER | Capitalized-Feature
Dev | FILTER-11659 | Phase 3 - Implement FluentD Changes for Tokenization (UserToken) | FILTER-11631 | Story | Prateek Fotedar | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Edouard | 12 | 12 | FILTER | Capitalized-Feature
Dev | FILTER-11824 | Dev task for JS Extension changes | FILTER-10034 | Escape Defect | Prateek Fotedar | Closed without action |  | P1 | 2026-01-29 |  | 2026-03-11 | sprint-Edouard | 8 | 8 | FILTER
Dev | FILTER-11863 | SafetyConsole Custom List API - Sanitize HTML/XSS in List Notes (POST & PUT) | FILTER-11734 | Defect | Prateek Fotedar | Done |  | P2 | 2026-01-29 |  | 2026-03-11 | sprint-Edouard | 4 | 4 | FILTER
Dev | FILTER-11866 | SafetyConsole Custom List API - Sanitize ListName input for XSS prevention (POST/PUT) | FILTER-11732 | Defect | Prateek Fotedar | Done |  | P2 | 2026-01-29 |  | 2026-03-11 | sprint-Edouard | 2 | 2 | FILTER
Dev | FILTER-11869 | Sanitize Resource Notes field in Custom List API (POST/PUT) to prevent XSS | FILTER-11731 | Defect | Prateek Fotedar | Done |  | P3 | 2026-01-29 |  | 2026-03-11 | sprint-Edouard | 5 | 5 | FILTER
Dev | FILTER-11875 | Fix XSS vulnerability in SafetyConsole Get CustomList API parameters | FILTER-11767 | Defect | Prateek Fotedar | Done |  | P3 | 2026-01-29 |  | 2026-03-11 | sprint-Edouard | 2 | 2 | FILTER
Dev | FILTER-11954 | New Feature ¦ DNS and SPAC changes for Tokenization | FILTER-11532 | Story | Prateek Fotedar | Done |  | P3 | 2026-02-03 |  | 2026-04-14 | sprint-Edouard | 16 | 16 | FILTER | Capitalized-Feature
Dev | FILTER-12116 | BE Task for Publish/Unpublish API for Custom List | FILTER-11827 | Story | Prateek Fotedar | Done |  | P3 | 2026-02-20 |  | 2026-04-14 | sprint-Edouard | 14 | 14 | FILTER | Capitalized-Feature
Dev | FILTER-12195 | [BugCrowd] Remove unauthenticated beta FID management API (betaFids.php) to fix arbitrary add/remove of beta FIDs | FILTER-12003 | Defect | Prateek Fotedar | Done |  | P3 | 2026-02-25 |  | 2026-03-18 | sprint-Edouard | 2 | 2 | FILTER
Dev | FILTER-12255 | BE Task Add note in the create and update API | FILTER-11827 | Story | Prateek Fotedar | Done |  | P3 | 2026-02-26 |  | 2026-04-14 | sprint-Edouard | 8 | 8 | FILTER | Capitalized-Feature
Dev | FILTER-12301 | POST /api/custom-list allows Admin to create custom list with usage "GLOBAL" - should be rejected | FILTER-11776 | Defect | Prateek Fotedar | Closed without action |  | P3 | 2026-03-01 |  | 2026-04-24 | sprint-Edouard | 0.5 | 6 | FILTER | Capitalized-Feature
Dev | FILTER-12319 | BE task to create a Custom List Support Tool - Custom List Detail API | FILTER-11827 | Story | Prateek Fotedar | Done |  | P3 | 2026-03-02 |  | 2026-04-14 | sprint-Edouard | 5 | 5 | FILTER | Capitalized-Feature
Dev | FILTER-12401 | www-support-tool build failing | FILTER-11827 | Story | Prateek Fotedar | Done |  | P3 | 2026-03-10 |  | 2026-04-14 | sprint-Edouard | 2 | 2 | FILTER | Capitalized-Feature
Dev | FILTER-12475 | customlist should be false for www-support-tool | FILTER-11827 | Story | Prateek Fotedar | Closed without action |  | P3 | 2026-03-13 |  | 2026-04-24 | sprint-Edouard | 0 | 5 | FILTER | Capitalized-Feature
Dev | FILTER-12701 | BE - DA Filter >> Activities. DA is able to see activities of kids from other OU as well | FILTER-12393 | Defect | Prateek Fotedar | Code Review |  | P1 | 2026-03-26 |  | 2026-04-21 | sprint-Edouard | 0 | 7 | FILTER
Defect | FILTER-10458 | NewFeaturBug: geography-quiz-2.org not getting categorized |  |  | Pratik Tiwari | Resolved | Fixed | P3 | 2025-10-17 | 2025-11-19 | 2026-03-03 | sprint-Edouard | 8 | 8 | FILTER | unplanned-sprint
Dev | FILTER-11896 | Vector Expansion - Add http://kiddle.co/ to search scanning | FILTER-11895 | Story | Pratik Tiwari | Done |  | P2 | 2026-01-29 |  | 2026-04-06 | sprint-Edouard | 10 | 10 | FILTER
Dev | FILTER-11995 | Fix bypass: URLs with /?scrlcbp=. open blocked sites | FILTER-11985 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-02-09 |  | 2026-03-03 | sprint-Edouard | 12 | 12 | FILTER
Dev | FILTER-12074 | [sprox] Bench-marking of Sprox request - Time, CPU and Memory | FILTER-12071 | Story | Pratik Tiwari | Done |  | P3 | 2026-02-17 |  | 2026-03-18 | sprint-Edouard | 24 | 10 | FILTER
Dev | FILTER-12165 | Block W3Schools (and similar) HTML sandbox bypass via CDN/third-party iframe loading (e.g. jsdelivr, Vercel, W3Spaces) | FILTER-12093 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-02-24 |  | 2026-04-06 | sprint-Edouard | 16 | 13 | FILTER
Dev | FILTER-12144 | [sprox] Check requirement of populating msg wth NULL in processSocialMediaMsg | FILTER-12143 | Task | Ravi Raj | Closed without action |  | P3 | 2026-02-23 |  | 2026-04-27 | sprint-Edouard | 4 | 6 | FILTER
Story | FILTER-12332 | [sprox] Logging module integration | FILTER-8230 | Epic | Ravi Raj | Ready For Release |  | P3 | 2026-03-02 |  | 2026-03-29 | sprint-Edouard | 16 | 0 | FILTER
Story | FILTER-12333 | [sprox] RTQA5 testing for DNS & SPAC | FILTER-8230 | Epic | Ravi Raj | Closed without action |  | P3 | 2026-03-02 |  | 2026-04-14 | sprint-Edouard | 16 | 0 | FILTER
Story | FILTER-12334 | [sprox] Captcha analysis and logging integration | FILTER-8230 | Epic | Ravi Raj | Closed without action |  | P3 | 2026-03-02 |  | 2026-03-30 | sprint-Edouard | 16 | 0 | FILTER
Dev | FILTER-12335 | Captcha analysis and logging integration | FILTER-12334 | Story | Ravi Raj | Done |  | P3 | 2026-03-02 |  | 2026-03-30 | sprint-Edouard | 16 | 16 | FILTER
Dev | FILTER-12336 | [sprox] RTQA5 testing for DNS & SPAC | FILTER-12333 | Story | Ravi Raj | Closed without action |  | P3 | 2026-03-03 |  | 2026-04-14 | sprint-Edouard | 16 | 16 | FILTER
Dev | FILTER-12337 | [sprox] Logging module integration | FILTER-12332 | Story | Ravi Raj | Done |  | P3 | 2026-03-03 |  | 2026-03-18 | sprint-Edouard | 16 | 16 | FILTER
Dev | FILTER-11857 | Clone CustomList API accepts invalid values for "usage" field | FILTER-11789 | Defect | Sagar Satpute | Closed without action |  | P2 | 2026-01-29 |  | 2026-03-06 | sprint-Edouard | 4 | 4 | FILTER
Dev | FILTER-11885 | BUGCROWD - Fix Open Redirect Vulnerability in Logout Endpoint (uk-www.securly.com) | FILTER-11806 | Defect | Sagar Satpute | Done |  | P3 | 2026-01-29 |  | 2026-04-16 | sprint-Edouard | 4 | 4 | FILTER
Dev | FILTER-11887 | BUGCROWD - Fix Open Redirect Vulnerability in smart.pac Endpoint via Base64-Encoded redirect Parameter | FILTER-11802 | Defect | Sagar Satpute | Done |  | P3 | 2026-01-29 |  | 2026-03-03 | sprint-Edouard | 8 | 8 | FILTER
Dev | FILTER-11889 | BUGCROWD - Fix Open Redirect Vulnerability in clean-cookies API Endpoint | FILTER-11782 | Defect | Sagar Satpute | Done |  | P3 | 2026-01-29 |  | 2026-04-16 | sprint-Edouard | 8 | 8 | FILTER
Dev | FILTER-11891 | BUGCROWD - Fix Open Redirect Vulnerability in /geo Endpoint via Encoded URL Parameter | FILTER-11778 | Defect | Sagar Satpute | Done |  | P3 | 2026-01-29 |  | 2026-04-16 | sprint-Edouard | 13 | 8 | FILTER
Dev | FILTER-12013 | [Extension] Block drive.google.com.108.181.32.77.sslip.io – not blocked by extension filtering | FILTER-12012 | Escape Defect | Sagar Satpute | Done |  | P1 | 2026-02-10 |  | 2026-03-05 | sprint-Edouard | 10 | 12 | FILTER
Dev | FILTER-12028 | BE - Fix Unhandled Backend Error When Deleting Filter Account via Support Tool | FILTER-10728 | Escape Defect | Sagar Satpute | Closed without action |  | P3 | 2026-02-11 |  | 2026-03-03 | sprint-Edouard | 5 | 5 | FILTER
Dev | FILTER-12087 | DEV - Policy Editor: When multiple custom lists are linked, deleting a URL from one custom list does not copy remaining URLs to the policy after unlink | FILTER-12086 | Defect | Sagar Satpute | Done |  | P3 | 2026-02-18 |  | 2026-04-16 | sprint-Edouard | 4 | 4 | FILTER | Capitalized-Feature
Dev | FILTER-12185 | Fix SSO access-token SameSite cookie and JWT secret for GO broker | FILTER-12048 | Escape Defect | Sagar Satpute | Done |  | P2 | 2026-02-25 |  | 2026-04-14 | sprint-Edouard | 13 | 13 | FILTER
Dev | FILTER-12346 | Include sub-domains in Support Tool API getSchoolAccounts response | FILTER-4949 | Task | Sagar Satpute | Done |  | P2 | 2026-03-03 |  | 2026-03-10 | sprint-Edouard | 6 | 6 | FILTER
Dev | FILTER-12349 | Support Tool: Improve search and display of FIDs (include FIDs without primary/sub domain) | FILTER-5401 | Task | Sagar Satpute | Done |  | P3 | 2026-03-03 |  | 2026-04-21 | sprint-Edouard | 5 | 5 | FILTER
Dev | FILTER-12352 | Support Tool: Include FIDs with no domain/sub-domain in search results | FILTER-5679 | Task | Sagar Satpute | Done |  | P3 | 2026-03-03 |  | 2026-04-21 | sprint-Edouard | 5 | 5 | FILTER
Dev | FILTER-12362 | Fix IP add failure for school FID and root cause in Support Tool | FILTER-11913 | Escape Defect | Sagar Satpute | Done |  | P1 | 2026-03-04 |  | 2026-03-17 | sprint-Edouard | 8 | 8 | FILTER
Dev | FILTER-12370 | DEV - Unable to add domains to Filter via Filter UI or Support Tool | FILTER-12369 | Escape Defect | Sagar Satpute | Done |  | P1 | 2026-03-06 |  | 2026-03-12 | sprint-Edouard | 16 | 8 | FILTER
Dev | FILTER-12373 | Dev task to Update Query to consider the current quarter only, instead of the last 90 days, when deleting the data | FILTER-12372 | Task | Sagar Satpute | Done |  | P3 | 2026-03-06 |  | 2026-03-06 | sprint-Edouard | 5 | 5 | FILTER
Dev | PTGM-664 | Fix linter errors in www-support-tool repo | PTGM-666 | Story | Sagar Satpute | Done |  | P2 | 2026-01-05 |  | 2026-04-14 | sprint-Edouard | 18 | 21 | PTGM
Dev | FILTER-11828 | Add 'Manage Custom List' option under hamburger menu in Support Tool | FILTER-11827 | Story | Shailendra Singh | Done |  | P3 | 2026-01-29 |  | 2026-04-14 | sprint-Edouard | 6 | 6 | FILTER | Capitalized-Feature
Dev | FILTER-11829 | Screen for List of Custom List | FILTER-11827 | Story | Shailendra Singh | Done |  | P3 | 2026-01-29 |  | 2026-04-14 | sprint-Edouard | 22 | 22 | FILTER | Capitalized-Feature
Dev | FILTER-11830 | Screen for 'Create Custom List' | FILTER-11827 | Story | Shailendra Singh | Done |  | P3 | 2026-01-29 |  | 2026-04-14 | sprint-Edouard | 33 | 33 | FILTER | Capitalized-Feature
Dev | FILTER-11831 | View and Edit Existing Custom List | FILTER-11827 | Story | Shailendra Singh | Done |  | P3 | 2026-01-29 |  | 2026-04-14 | sprint-Edouard | 16 | 16 | FILTER | Capitalized-Feature
Dev | FILTER-11833 | Publish/Un-publish Custom List | FILTER-11827 | Story | Shailendra Singh | Done |  | P3 | 2026-01-29 |  | 2026-04-14 | sprint-Edouard | 16 | 16 | FILTER | Capitalized-Feature
Dev | FILTER-11834 | Delete Custom List | FILTER-11827 | Story | Shailendra Singh | Done |  | P3 | 2026-01-29 |  | 2026-04-14 | sprint-Edouard | 12 | 12 | FILTER | Capitalized-Feature
Dev | FILTER-12537 | BE - Search api for support tool | FILTER-11827 | Story | Shailendra Singh | Done |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Edouard | 10 | 10 | FILTER | Capitalized-Feature
Dev | FILTER-12538 | BE - Update list api handling for data over and above paginated values | FILTER-11827 | Story | Shailendra Singh | Done |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Edouard | 6 | 6 | FILTER | Capitalized-Feature
Dev | FILTER-12539 | FE - Integration of search and update list api's to handle the respective changes in support tool | FILTER-11827 | Story | Shailendra Singh | Done |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Edouard | 10 | 10 | FILTER | Capitalized-Feature
QA | FILTER-11536 | Manual Testing Tokenization service for SPAC / DNS | FILTER-11532 | Story | Surabhi Choudhary | Done |  | P3 | 2025-12-19 |  | 2026-04-15 | sprint-Edouard | 16 | 16 | FILTER | Capitalized-Feature
QA | FILTER-11661 | Manual Testing Tokenization service for Extension | FILTER-11631 | Story | Surabhi Choudhary | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Edouard | 24 | 24 | FILTER | Capitalized-Feature
QA | FILTER-11666 | Test Complete URL Path in Categorized Queue from Crextn | FILTER-11637 | Task | Surabhi Choudhary | Done |  | P2 | 2026-01-15 |  | 2026-04-09 | sprint-Edouard | 3 | 3 | FILTER
Test Case Creation | FILTER-11748 | Create test cases for Tokenization feature | FILTER-11532 | Story | Surabhi Choudhary | Done |  | P3 | 2026-01-21 |  | 2026-04-14 | sprint-Edouard | 8 | 8 | FILTER | Capitalized-Feature
QA | FILTER-12078 | Basic sanity & testing related to PDF download is required | FILTER-11742 | Task | Surabhi Choudhary | Done |  | P3 | 2026-02-17 |  | 2026-03-12 | sprint-Edouard | 3 | 3 | FILTER
QA | FILTER-12186 | Verify SSO access-token SameSite and JWT secret fixes for GO broker | FILTER-12048 | Escape Defect | Surabhi Choudhary | Done |  | P2 | 2026-02-25 |  | 2026-04-24 | sprint-Edouard | 1 | 1 | FILTER
QA | FILTER-12194 | Verify Category Lookup respects "Enable Filter Admin Console API traffic switching to Go (BETA)" and does not 404 when toggle is OFF | FILTER-12045 | Defect | Surabhi Choudhary | Done |  | P3 | 2026-02-25 |  | 2026-03-11 | sprint-Edouard | 2 | 2 | FILTER
QA | FILTER-12261 | QA- http/2 protocol could exceed allowed header size | FILTER-12259 | Escape Defect | Surabhi Choudhary | Done |  | P1 | 2026-02-26 |  | 2026-03-10 | sprint-Edouard | 5 | 3 | FILTER
QA | FILTER-12383 | Verify OU gets logged correctly | FILTER-12017 | Escape Defect | Surabhi Choudhary | Done |  | P3 | 2026-03-09 |  | 2026-03-11 | sprint-Edouard | 2 | 2 | FILTER
QA | FILTER-13078 | SPROX Manual Testing Phase 1 | FILTER-12200 | Task | Surabhi Choudhary | Done |  | P2 | 2026-04-01 |  | 2026-04-25 | sprint-Edouard | 24 | 24 | FILTER
QA | FILTER-13079 | Manual Testing Tokenization service for GO Extension | FILTER-11631 | Story | Surabhi Choudhary | Done |  | P2 | 2026-04-01 |  | 2026-04-14 | sprint-Edouard | 24 | 24 | FILTER | Capitalized-Feature
Dev | FILTER-11665 | [PageScan] Send Complete URL Path in Categorized Queue from Crextn | FILTER-11637 | Task | Vaibhav Kumbhar | Done |  | P2 | 2026-01-15 |  | 2026-04-06 | sprint-Edouard | 15 | 12 | FILTER
Dev | FILTER-11883 | HACKERONE - Implement Server-Side Authorization for Policy Editor and Advanced Report Features | FILTER-10347 | Defect | Vaibhav Kumbhar | Done |  | P3 | 2026-01-29 |  | 2026-03-03 | sprint-Edouard | 14 | 18 | FILTER
Defect | FILTER-12045 | InProd:No, Category lookup tool throws error when Enable Filter Admin Console API traffic switching to Go (BETA) is OFF |  |  | Vaibhav Kumbhar | RELEASED TO PROD | Duplicate | P2 | 2026-02-12 | 2026-03-10 | 2026-04-16 | sprint-Edouard | 0 | 0 | FILTER
Dev | FILTER-12056 | Dev- Category Look up drawer gives Error on URL check | FILTER-12055 | Defect | Vaibhav Kumbhar | Done |  | P3 | 2026-02-13 |  | 2026-03-09 | sprint-Edouard | 4 | 4 | FILTER
Dev | FILTER-12168 | Deny list not applied when Google Docs/Slides URL contains scrlybrkr parameter (Downingtown) | FILTER-11893 | Escape Defect | Vaibhav Kumbhar | Done |  | P2 | 2026-02-24 |  | 2026-03-17 | sprint-Edouard | 16 | 16 | FILTER
Dev | FILTER-12193 | Fix Category Lookup tool to respect "Enable Filter Admin Console API traffic switching to Go (BETA)" and avoid 404 when toggle is OFF | FILTER-12045 | Defect | Vaibhav Kumbhar | Done |  | P3 | 2026-02-25 |  | 2026-03-10 | sprint-Edouard | 4 | 8 | FILTER
Dev | FILTER-12260 | DEV - http/2 protocol could exceed allowed header size | FILTER-12259 | Escape Defect | Vaibhav Kumbhar | Done |  | P1 | 2026-02-26 |  | 2026-03-01 | sprint-Edouard | 4 | 4 | FILTER
Dev | FILTER-12338 | Extension logs show traffic for deactivated GAC user (tfisher@d84.org); user should not appear once removed from GAC | FILTER-12300 | Escape Defect | Vaibhav Kumbhar | Closed without action |  | P2 | 2026-03-03 |  | 2026-03-18 | sprint-Edouard | 8 | 16 | FILTER
Dev | FILTER-12536 | Dev Task to Add authentication for proxy apis | FILTER-11637 | Task | Vaibhav Kumbhar | Done |  | P2 | 2026-03-17 |  | 2026-04-06 | sprint-Edouard | 20 | 16 | FILTER

## Not Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Defect | FILTER-12153 | JS (All Extensions): Esc Button is circumventing image blur |  |  | Arun Thakur | Open |  | P1 | 2026-02-24 |  | 2026-03-29 | sprint-Edouard | 1 | 2 | FILTER | unplanned-sprint |  | YES
QA | FILTER-11844 | Verify fix for SafetyConsole CustomList API - Token invalidation on re-authentication | FILTER-11687 | Defect | Amit Shete | Open |  | P2 | 2026-01-29 |  | 2026-04-27 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-11873 | Verify CustomList API returns 401 when Filter Product is disabled | FILTER-11688 | Escape Defect | Amit Shete | Ready for QA |  | P3 | 2026-01-29 |  | 2026-04-27 | sprint-Edouard | 0 | 2 | FILTER
Automation | FILTER-11882 | [Phase-4] Automated Tests for UserToken Read Queries and Detokenization | FILTER-11632 | Story | Amit Shete | Open |  | P3 | 2026-01-29 |  | 2026-03-18 | sprint-Edouard | 0 | 0 | FILTER | Capitalized-Feature
Dev | FILTER-11354 | Fix JS Extension Bypass: Blurred YouTube Shorts/Videos Remain Clickable | FILTER-10631 | Defect | Arun Thakur | Open |  | P2 | 2025-12-08 |  | 2026-03-18 | sprint-Edouard | 0 | 12 | FILTER
Dev | FILTER-11483 | Fix Canva.com NSFW Video Classification Timeout and Safe Image Click Blockers | FILTER-11418 | Defect | Arun Thakur | In Progress |  | P2 | 2025-12-19 |  | 2026-04-27 | sprint-Edouard | 6 | 6 | FILTER
Dev | FILTER-12217 | DEV -JS (All Extensions): Youtube blurred videos are viewable on hover | FILTER-12216 | Defect | Arun Thakur | Reopened |  | P2 | 2026-02-25 |  | 2026-03-23 | sprint-Edouard | 6 | 6 | FILTER
Dev | FILTER-12223 | DEV - JS (All Extensions): Youtube blurred videos can be clicked and played without blur | FILTER-12222 | Defect | Arun Thakur | Reopened |  | P2 | 2026-02-25 |  | 2026-03-18 | sprint-Edouard | 4 | 4 | FILTER
Dev | FILTER-12226 | DEV - JS (Windows+ Edge) Extensions. Youtube. Blurring does not work on Embedded videos | FILTER-12225 | Defect | Arun Thakur | Open |  | P3 | 2026-02-25 |  | 2026-03-18 | sprint-Edouard | 0 | 0 | FILTER
Dev | FILTER-12232 | DEV - JS (All Extensions): Youtube. YT shorts reload the whole page when we scroll to the next video | FILTER-12231 | Defect | Arun Thakur | Open |  | P2 | 2026-02-25 |  | 2026-03-18 | sprint-Edouard | 0 | 0 | FILTER
Dev | FILTER-12282 | DE- JS (ALL Extensions) Image Blur model behaves differently on GSheet, Drive, Gslide, Email, PDF, GDoc | FILTER-12281 | Defect | Arun Thakur | In Progress |  | P2 | 2026-02-26 |  | 2026-04-27 | sprint-Edouard | 12 | 12 | FILTER
Dev | FILTER-11499 | [Triage] Off-CPU flame graph generation on dev cluster | FILTER-10748 | Task | Ashish Temurnikar | Open |  | P2 | 2025-12-19 |  | 2026-04-14 | sprint-Edouard | 0 | 8 | FILTER
Dev | FILTER-12197 | Wrap private-IP check in PAC with IP-only regex to avoid hostname DNS resolution | FILTER-11364 | Support Request | Ashish Temurnikar | Open |  | P3 | 2026-02-25 |  | 2026-04-06 | sprint-Edouard | 0 | 0 | FILTER
QA | FILTER-11147 | Manual QA Validation for Blurred YouTube Thumbnail Click Bypass (Shorts & Videos) | FILTER-10631 | Defect | Ayesha Kamde | Open |  | P2 | 2025-12-02 |  | 2026-03-18 | sprint-Edouard | 0 | 6 | FILTER
QA | FILTER-11485 | Fix Canva.com NSFW Video Classification Timeout and Safe Image Click Blockers | FILTER-11418 | Defect | Ayesha Kamde | Open |  | P2 | 2025-12-19 |  | 2026-04-16 | sprint-Edouard | 2 | 2 | FILTER
QA | FILTER-12155 | QA- JS (All Extensions): Esc Button is circumventing image blur | FILTER-12153 | Defect | Ayesha Kamde | QA in Progress |  | P1 | 2026-02-24 |  | 2026-03-24 | sprint-Edouard | 1 | 2 | FILTER
QA | FILTER-12218 | QA- JS (All Extensions): Youtube blurred videos are viewable on hover | FILTER-12216 | Defect | Ayesha Kamde | Open |  | P2 | 2026-02-25 |  | 2026-03-23 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-12224 | QA- JS (All Extensions): Youtube blurred videos can be clicked and played without blur | FILTER-12222 | Defect | Ayesha Kamde | Open |  | P2 | 2026-02-25 |  | 2026-03-18 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-12227 | QA- JS (Windows+ Edge) Extensions. Youtube. Blurring does not work on Embedded videos | FILTER-12225 | Defect | Ayesha Kamde | Open |  | P3 | 2026-02-25 |  | 2026-03-18 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-12233 | QA- JS (All Extensions): Youtube. YT shorts reload the whole page when we scroll to the next video | FILTER-12231 | Defect | Ayesha Kamde | Open |  | P2 | 2026-02-25 |  | 2026-03-18 | sprint-Edouard | 0 | 2 | FILTER
QA | FILTER-12283 | QA- JS (ALL Extensions) Image Blur model behaves differently on GSheet, Drive, Gslide, Email, PDF, GDoc | FILTER-12281 | Defect | Ayesha Kamde | Open |  | P2 | 2026-02-26 |  | 2026-04-16 | sprint-Edouard | 3 | 2 | FILTER
QA | FILTER-12395 | QA- DA Filter >> Activities. DA is able to see activities of kids from other OU as well | FILTER-12393 | Defect | Ayesha Kamde | Open |  | P1 | 2026-03-09 |  | 2026-04-14 | sprint-Edouard | 0 | 2 | FILTER
Dev | FILTER-11843 | SafetyConsole CustomList API - Old access tokens remain valid after new token generation | FILTER-11687 | Defect | Prateek Fotedar | Reopened |  | P2 | 2026-01-29 |  | 2026-04-28 | sprint-Edouard | 12 | 12 | FILTER
Dev | FILTER-11872 | SafetyConsole CustomList API - Token should be invalidated when Filter Product is disabled | FILTER-11688 | Escape Defect | Prateek Fotedar | Reopened |  | P3 | 2026-01-29 |  | 2026-04-28 | sprint-Edouard | 1 | 8 | FILTER
Dev | FILTER-11880 | FILTER - [Phase-4] Update Read Queries and Implement UserToken Detokenization for UI Consumption | FILTER-11632 | Story | Prateek Fotedar | Open |  | P3 | 2026-01-29 |  | 2026-03-18 | sprint-Edouard | 0 | 12 | FILTER | Capitalized-Feature
Dev | PTGM-663 | Fix linter errors in www-filter repo | PTGM-666 | Story | Sagar Satpute | Open |  | P2 | 2026-01-05 |  | 2026-04-14 | sprint-Edouard | 0 | 0 | PTGM
QA | FILTER-11881 | [Phase-4] Validate UserToken Read Queries and Detokenization for UI Portals | FILTER-11632 | Story | Surabhi Choudhary | Open |  | P3 | 2026-01-29 |  | 2026-03-18 | sprint-Edouard | 0 | 20 | FILTER | Capitalized-Feature
QA | FILTER-12198 | Verify internal-traffic PAC change (IP-only regex) and hostname-heavy page performance | FILTER-11364 | Support Request | Surabhi Choudhary | Open |  | P3 | 2026-02-25 |  | 2026-04-06 | sprint-Edouard | 0 | 0 | FILTER

## Removed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Defect | FILTER-12150 | JS (All Extensions) Some sites opened from search link from Google AI mode does not start image blurring right away |  |  | Arun Thakur | Open |  | P2 | 2026-02-24 |  | 2026-04-02 | sprint-Edouard | 0 | 2 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12304 | Go broker server: Make fasthttp ReadBufferSize and WriteBufferSize configurable |  |  | Vaibhav Kumbhar | Closed | Done | P3 | 2026-03-02 | 2026-03-27 | 2026-04-21 | sprint-Edouard | 4 | 4 | FILTER |  |  | YES
Task | FILTER-12342 | POC - Check from last 1 month, all QA tasks can be verified with Cursor browser or playwright | FILTER-12341 | Epic | Vaibhav Kumbhar | Resolved |  | P2 | 2026-03-03 |  | 2026-03-31 | sprint-Edouard | 20 | 0 | FILTER | unplanned-sprint |  | YES
Escape Defect | FILTER-9853 | Filter >> Activities and Emails for Blocked search terms on Yandex, Baidu and DuckDuckGo, do not have search query in external links |  |  | Arun Thakur | Open |  | P3 | 2025-08-31 |  | 2026-04-10 | sprint-Edouard | 6.5 | 2 | FILTER
Task | FILTER-10604 | Placeholder task to track the efforts used for Vanta tool task completion |  |  | Harsh Verma | In Progress |  | P3 | 2025-11-03 |  | 2026-04-27 | sprint-Edouard | 0 | 8 | FILTER | unplanned-sprint
Task | FILTER-11697 | Extension of FILTER-11605 |  |  | Harsh Verma | In Progress |  | P3 | 2026-01-19 |  | 2026-04-27 | sprint-Edouard | 0 | 24 | FILTER | unplanned-sprint
Escape Defect | FILTER-12010 | P1 Escalation-Extension Bypass - Bookmark + stop page |  |  | Pratik Tiwari | Confirmation | Fixed | P1 | 2026-02-10 | 2026-04-06 | 2026-04-28 | sprint-Edouard | 20 | 0 | FILTER | jira_added, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_p1, jira_qa_verified, zendesk_enterprise, zendesk_org_at_risk
Task | FDSE-155 | Implementation for timepicker component | FDSE-136 | Epic | Swaroop Chavhan | Open |  | P3 | 2026-01-29 |  | 2026-04-28 | sprint-Edouard | 0 | 32 | FDSE | product-filter
Task | FDSE-164 | Search with auto-complete component enhancement | FDSE-174 | Epic | Swaroop Chavhan | Open |  | P3 | 2026-02-26 |  | 2026-04-28 | sprint-Edouard | 0 | 20 | FDSE | Capitalized-Feature, product-filter

## P1 Escalation
P1 Escalation — FILTER · sprint-Edouard (2026-03-03 → 2026-03-16)
sprint-Edouard tickets where Issue Type = Escape Defect AND Priority = P1 AND summary contains 'P1 Escalation' (regardless of bucket). Total = 11.
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Bucket
Escape Defect | FILTER-11610 | P1 Escalation-CORs Errors at BlueBeam and Boomerang S3 Amazon domains ¦ St. Vrain |  |  | Ramani Cheruvu | In Progress | Fixed | P1 | 2026-01-08 | 2026-01-27 | 2026-04-27 | sprint-Edouard | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_reopened, p1escalation, unplanned-sprint, zendesk_enterprise |  | Removed
Escape Defect | FILTER-12119 | P1 Escalation-Investigate and address the use of about:blank pages as a filter loophole |  |  | Shashank Tiwari | In Progress |  | P1 | 2026-02-20 |  | 2026-04-28 | sprint-Edouard | 20 | 0 | FILTER | jira_added, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_p2, p1escalation, zendesk_enterprise, zendesk_org_at_risk |  | Removed
Escape Defect | FILTER-12010 | P1 Escalation-Extension Bypass - Bookmark + stop page |  |  | Pratik Tiwari | Confirmation | Fixed | P1 | 2026-02-10 | 2026-04-06 | 2026-04-28 | sprint-Edouard | 20 | 0 | FILTER | jira_added, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_p1, jira_qa_verified, zendesk_enterprise, zendesk_org_at_risk |  | Removed
Escape Defect | FILTER-10034 | P1 Escalation-YouTube blocked while doing a Google Search |  |  | Shashank Tiwari | Done | Fixed | P1 | 2025-09-12 | 2025-11-24 | 2026-04-16 | sprint-Edouard | 5 | 5 | FILTER | jira_added, jira_closed_notify, jira_confirmation, jira_done, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_p3, jira_qa_verified, jira_reopened, p1escalation, unplanned-sprint, zendesk_org_at_risk |  | Completed
Escape Defect | FILTER-11913 | P1 Escalation-Cannot Add IP address for school |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-01-30 | 2026-01-30 | 2026-04-16 | sprint-Edouard | 0.2 | 0 | FILTER | Reverified-2026, p1escalation, unplanned-sprint |  | Completed
Escape Defect | FILTER-11985 | P1 Escalation-Extension bypass by adding a string at the end of the site |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-02-06 | 2026-02-25 | 2026-04-16 | sprint-Edouard | 27 | 12 | FILTER | jira_added, jira_closed_notify, jira_done, jira_escalated, jira_p1, jira_qa_verified, zendesk_enterprise |  | Completed
Escape Defect | FILTER-12012 | P1 Escalation-drive.google.com.108.181.32.77.sslip.io is not blocking for extension filtering |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-02-10 | 2026-03-05 | 2026-04-16 | sprint-Edouard | 0.2 | 0 | FILTER | jira_added, jira_done, jira_escalated, jira_p1, zendesk_enterprise |  | Completed
Escape Defect | FILTER-12093 | P1 Escalation-Students bypass Filter via W3Schools HTML sandbox using CDN / third-party iframe loading (GitHub content proxy) |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-02-18 | 2026-03-13 | 2026-04-16 | sprint-Edouard | 21 | 0 | FILTER | jira_added, jira_closed_notify, jira_confirmation, jira_done, jira_escalated, jira_open, jira_p1, jira_qa_verified, jira_reopened, unplanned-sprint, zendesk_enterprise |  | Removed
Escape Defect | FILTER-12247 | P1 Escalation-Appending allowed site to the blocked URL breaks CRXTN |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-02-26 | 2026-03-24 | 2026-04-17 | sprint-Edouard | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_closed_notify, jira_confirmation, jira_done, jira_done_notified, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_p2, jira_qa_verified, p1escalation |  | Removed
Escape Defect | FILTER-12369 | P1 Escalation-Unable to add domains to Filter via Filter UI or Support Tool |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-03-06 | 2026-03-11 | 2026-04-16 | sprint-Edouard | 0.2 | 0 | FILTER | jira_added, jira_backlog, jira_done, jira_escalated, jira_in_progress, jira_p1, jira_qa_verified, p1escalation, unplanned-sprint |  | Completed
Escape Defect | FILTER-7666 | P1 Escalation-File downloading in Image Google Search |  |  | Shashank Tiwari | Confirmation | Cannot Reproduce | P1 | 2025-03-26 | 2025-09-04 | 2026-04-28 | sprint-Edouard | 2 | 12 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_closed_notify, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_reopened, jira_resolved, zendesk_org_at_risk |  | Removed