## Capacity vs Delivery
Capacity vs Delivery — FILTER · sprint-Fay (Tue 17 Mar → Mon 30 Mar 2026)
Team Composition (per Securly-PjM-Skills.md Part 2 — Filter India roster). Inactive members for this sprint window are shaded grey with a roster note.
Name | Role | Function / Split | Allocation (FTE) | Seniority | Employment | Notes
Shashank Tiwari | Project Manager | PM / Delivery | 0 | Lead | FTE | Not counted in delivery capacity
Harsh Verma | FE | FrontEnd Architect (Angular) | 1 | Senior | FTE
Arun Thakur | FE + Ext | Angular / Extension | 1 | Medium | FTE
Harshada Kude | FE | Angular | 1 | Junior | FTE
Shailendra Singh | FE | Angular | 1 | Medium | FTE
Swaroop Chavhan | FE + Ext | Angular / Extension | 1 | Medium | FTE
Ashish Modak | BE Architect | Extension / Go / PHP | 1 | Senior | FTE
Prateek Fotedar | BE (www) | Go / PHP | 1 | Senior | FTE
Sagar Satpute | BE (www) | Go / PHP | 1 | Medium | FTE
Vaibhav Kumbhar | BE | Go / PHP | 1 | Medium | FTE
Ashish Temurnikar | BE | DNS / SPAC / Squid / Rust | 1 | Senior | FTE
Ravi Raj | BE | DNS / SPAC / Squid / Rust | 1 | Medium | FTE
Pratik Tiwari | BE + Ext | Extension / Go / Rust | 1 | Senior | FTE
Altamash Heroli | QA | Pri. Manual QA | 1 | Senior | FTE
Surabhi Choudhary | QA | Sr. Manual QA | 1 | Senior | FTE
Ayesha Kamde | QA | Manual QA | 1 | Junior | FTE
Amol Mithari | Auto QA Lead | Team Lead — Auto QA / SDET | 1 | Lead | FTE
Amit Shete | Auto QA | Pri. SDET | 1 | Senior | FTE
Rachit Mishra | Auto QA | SDET | 0 | Junior | FTE | Left team on 20-Feb-2026 — not part of this sprint
Total FILTER allocation |  |  |  | FTE-equivalent heads available to FILTER
Capacity Parameters (yellow cells are inputs — re-run the script after edits)
Parameter | Value | Description
Sprint length (working days) | 10 | FILTER 15-day sprint Tue → Mon. sprint-Fay = 2026-03-17 → 2026-03-30.
Company holidays in sprint | 1 | India calendar 2026 — 19-Mar: Gudi Padwa
Effective working days (sprint − company holidays) |  | Used as the per-person calendar for availability
Hours per working day (nominal) | 8 | Standard working day
Focus factor (productive fraction) | 0.9 | 90% — what SLT expects (sprint-analysis default)
Misc buffer (meetings, scrums, code review, …) | 20% | 20% blanket reservation deducted from Available to get Net Available
Effective hours per FTE per sprint
Allocated FTE on FILTER (active this sprint) | 17 | Headcount actually working this sprint (excludes joiners/leavers outside window)
Ideal capacity for the sprint (hrs)
Issue scope (Jira projects) | FILTER, PTGM, FDSE | Tickets pulled with `project in (FILTER, PTGM, FDSE) AND sprint = …` — FILTER: 240 · PTGM: 5
Capacity vs Actual Delivery — sprint-Fay
Metric | Hours | % of Ideal | Rating | Notes
Actual Availability |  |  |  | Sum of per-person availability (Ideal − leaves)
Misc Buffer (20%) |  |  |  | Reserved for meetings, scrums, code reviews
Net Available (Available − Misc Buffer) |  |  |  | Realistic delivery capacity — used as the denominator for Completed %
Completed |  |  |  | Sum of in-sprint timeSpent (Completed bucket)
Not Completed (Spillover) |  |  |  | Original estimate for spillover (carried into next sprint)
Removed |  |  |  | Original estimate for issues removed mid-sprint
Completed by Priority
Tickets (parents) = unique parent items (Story / Task / Defect / Escape Defect) — subtasks roll up to their parent so 1 parent + 3 subtasks = 1 ticket. Tickets (incl. subtasks) = raw record count incl. every Dev / QA / Automation / Review / Test Case Creation / Debug subtask. Hours = sum across parents and subtasks; matches the core-team Completed hours on the Per-person Delivery sheet.
Priority | Tickets (parents) | Tickets (incl. subtasks) | Hours (incl. subtasks) | % of Completed Hrs | % of Tickets (parents) | Notes
P0 | 1 | 4 | 24 |  |  | Critical / production halting
P1 | 8 | 20 | 53 |  |  | P1 — high priority (see P1 Escalation tab for escalations)
P2 | 13 | 31 | 245.5 |  |  | Major
P3 | 35 | 83 | 632.5 |  |  | Standard
TOTAL | 57 | 138 | 955 | 100% | 100% | Sum of Completed bucket (core roster)
Sprint Completion (spillover = Not Completed)
Metric | Tickets | Planned Hrs (OE) | % by Tickets | % by Hrs | Notes
Completed (closed in sprint) | 138 | 858.5 |  |  | In-sprint deliverables
Spillover (not completed → carry-over) | 11 | 30 |  |  | Original estimate carried to next sprint
Removed (mid-sprint scope cut) | 8 | 38 | — | — | Excluded from completion ratio (out of scope)
Mid-sprint additions (core) | 27 |  | — | — | Late-arriving work (Jira issueKeysAddedDuringSprint)
Sprint completion rate (tickets) | 92.62% | On Target | Completed ÷ (Completed + Spillover)
Sprint completion rate (planned hrs) | 96.62% | On Target | Σ OE Completed ÷ Σ OE (Completed + Spillover)
Planned completion rate (tickets, excludes mid-sprint adds) | 92.19% | On Target | Originally-committed tickets only
Planned completion rate (planned hrs, excludes mid-sprint adds) | 96.42% | On Target | Originally-committed planned hours only
P1 Escalation snapshot
7 ticket(s) in sprint-Fay match 'P1 Escalation' in the title — 5 closed, 2 still open. See the 'P1 Escalation' tab.
Mid-sprint additions snapshot
27 ticket(s) were added to sprint-Fay after it started (issueKeysAddedDuringSprint) — Completed 20, Spillover 1, Removed 6. Highlighted in amber on every detail sheet (Added Mid-Sprint = YES).
Assumptions & caveats
• Sprint window from Jira (/rest/agile/1.0/sprint/5500): 2026-03-17 → 2026-03-30 (10 Mon–Fri working days). Refresh with fetch_filter_sprint_meta.py + fetch_filter_sprint_issues.py.
• Issues pulled from FILTER + PTGM + FDSE (project-scope expanded for the India scrum team's split across the three products).
• Date-aware roster: Amol Mithari joined 20-Feb-2026; Rachit Mishra's last day was 20-Feb-2026. Inactive members for this sprint window are shaded grey in the Team Composition table and excluded from per-person availability + delivery.
• Available (hrs) = (effective working days − leave days) × 8 × focus factor, where effective working days = sprint working days − company holidays falling inside the sprint − days outside the person's employment window. Per-person Delivery shows leave days in Column G to explain the delta from a full sprint.
• Net Available = Available − 20% Misc Buffer for meetings, scrums, code review, etc. Completed/Not Completed/Removed % of capacity use Net Available as the denominator.
• Time Spent on Completed sheet uses the in-sprint hybrid worklog rule (sprint-analysis.md): single-sprint = timespent; multi-sprint = SUM of worklogs whose started ∈ [sprintStart, sprintEnd].
• Not Completed and Removed totals use Original Estimate.
• Removed list comes from the Sprint Report puntedIssues (greenhopper API).
• Core roster only: assignees outside Securly-PjM-Skills.md Part 2 are dropped from per-person + detail sheets.
• P1 Escalation tab is filtered to Issue Type = Escape Defect AND Priority = P1 AND title contains 'P1 Escalation'.
• Completed by Priority — Tickets (parents) rolls subtasks up to their parent (each work item counted once at its parent priority); Tickets (incl. subtasks) shows the raw record count for comparison. The Hours column sums every record (parent + subtasks) and matches the core-team Completed total.
• Spillover = Not Completed bucket (tickets carried into the next sprint).
• Sprint completion rate uses Completed ÷ (Completed + Spillover); Removed tickets are excluded (treated as scope cut). 'Planned' rate also excludes mid-sprint additions.
• All detail sheets (Completed, Not Completed, Removed) highlight tickets added after sprint start (Jira sprint-report issueKeysAddedDuringSprint) in amber, with an 'Added Mid-Sprint = YES' tag column.
• Ratings: ≥85% On Target (green), 70–85% Below Target (amber), <70% Significantly Below (red).

## Per-person Delivery
Assignee | Completed (hrs) | Not Completed (hrs) | Removed (hrs) | Efficiency | Available (hrs) | Leave Days (sprint) | Misc Buffer 20% (hrs) | Net Available (hrs)
Harsh Verma | 48 | 0 | 32 |  | 64.8 | 0
Arun Thakur | 28 | 6 | 6 |  | 64.8 | 0
Harshada Kude | 126.5 | 0 | 0 |  | 64.8 | 0
Shailendra Singh | 0 | 0 | 0 |  | 57.6 | 1
Swaroop Chavhan | 144 | 0 | 0 |  | 64.8 | 0
Ashish Modak | 8 | 0 | 0 |  | 57.6 | 1
Prateek Fotedar | 23.5 | 12 | 0 |  | 64.8 | 0
Sagar Satpute | 70 | 0 | 0 |  | 64.8 | 0
Vaibhav Kumbhar | 81 | 0 | 0 |  | 64.8 | 0
Ashish Temurnikar | 10 | 0 | 0 |  | 57.6 | 1
Ravi Raj | 88 | 0 | 0 |  | 43.2 | 3
Pratik Tiwari | 66 | 4 | 0 |  | 64.8 | 0
Altamash Heroli | 132 | 0 | 0 |  | 57.6 | 1
Surabhi Choudhary | 53.5 | 0 | 0 |  | 36 | 4
Ayesha Kamde | 55.5 | 6 | 0 |  | 50.4 | 2
Amol Mithari | 4 | 0 | 0 |  | 64.8 | 0
Amit Shete | 17 | 2 | 0 |  | 64.8 | 0
TOTAL

## Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Task | FILTER-12693 | Removed NSFW image blur feature code and related files from the securly-extensions repository |  |  | Arun Thakur | Closed |  | P3 | 2026-03-26 |  | 2026-04-21 | sprint-Fay | 1 | 0 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-12543 | Need to setup Cursor Skills and Rules as per our code architecture in FDSE project |  |  | Harsh Verma | Resolved |  | P3 | 2026-03-17 |  | 2026-03-31 | sprint-Fay | 20 | 20 | FILTER | unplanned-sprint |  | YES
Story | FILTER-12293 | [Filter] Translations for Spanish & French - Json Creation & Verify | FILTER-12099 | Epic | Harshada Kude | RELEASED TO PROD |  | P3 | 2026-02-27 |  | 2026-04-27 | sprint-Fay | 24 | 0 | FILTER | unplanned-sprint |  | YES
Story | FILTER-12305 | [Filter] Consumption of json Translations in Settings | FILTER-12099 | Epic | Harshada Kude | RELEASED TO PROD |  | P3 | 2026-03-02 |  | 2026-04-27 | sprint-Fay | 10.5 | 0 | FILTER |  |  | YES
Story | FILTER-12311 | [Filter] Cross check Filter Application Other Remaining instances of ¦ translate or instant | FILTER-12099 | Epic | Harshada Kude | RELEASED TO PROD |  | P3 | 2026-03-02 |  | 2026-04-27 | sprint-Fay | 18.5 | 0 | FILTER |  |  | YES
Story | FILTER-12474 | [Filter] Accessibility Fix - 3.1.2 | FILTER-12099 | Epic | Harshada Kude | RELEASED TO PROD |  | P3 | 2026-03-13 |  | 2026-04-27 | sprint-Fay | 0 | 0 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12681 | Fix New Translation Strategy Related Issues |  |  | Harshada Kude | RELEASED TO PROD | Fixed | P3 | 2026-03-25 | 2026-03-29 | 2026-04-15 | sprint-Fay | 1 | 0 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12677 | Update if condition for scru cookie |  |  | Prateek Fotedar | Closed |  | P3 | 2026-03-25 |  | 2026-04-21 | sprint-Fay | 1 | 1 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12796 | Update Cron Job for tokenization |  |  | Prateek Fotedar | QA Verified | Fixed | P3 | 2026-03-27 | 2026-03-29 | 2026-04-27 | sprint-Fay | 1 | 0 | FILTER | unplanned-sprint |  | YES
Story | FILTER-12332 | [sprox] Logging module integration | FILTER-8230 | Epic | Ravi Raj | Ready For Release |  | P3 | 2026-03-02 |  | 2026-03-29 | sprint-Fay | 16 | 0 | FILTER |  |  | YES
Story | FILTER-12334 | [sprox] Captcha analysis and logging integration | FILTER-8230 | Epic | Ravi Raj | Closed without action |  | P3 | 2026-03-02 |  | 2026-03-30 | sprint-Fay | 16 | 0 | FILTER |  |  | YES
Debug | FILTER-12970 | [sprox] Duckduckgo Keyword not logging |  |  | Ravi Raj | Resolved |  | P3 | 2026-03-30 |  | 2026-03-30 | sprint-Fay | 6 | 6 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-12971 | [sprox] Disable off campus filtering not working |  |  | Ravi Raj | Resolved |  | P3 | 2026-03-30 |  | 2026-03-30 | sprint-Fay | 4 | 4 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-12972 | [sprox] Keyword block shows wrong reason for blocking |  |  | Ravi Raj | Resolved |  | P3 | 2026-03-30 |  | 2026-03-30 | sprint-Fay | 6 | 6 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-13024 | [sprox] Migrate IsReduceTraffic function to Rust |  |  | Ravi Raj | Resolved |  | P3 | 2026-03-31 |  | 2026-03-31 | sprint-Fay | 8 | 8 | FILTER | unplanned-sprint |  | YES
Support Request | FILTER-10777 | Remove play.google.com from perm whitelist for FID securly@mhat.org.uk |  |  | Sagar Satpute | Closed without action |  | P3 | 2025-11-13 |  | 2026-03-30 | sprint-Fay | 3 | 5 | FILTER | jira_added, jira_backlog, jira_escalated, unplanned-sprint |  | YES
Task | FILTER-12697 | Investigate and fix case generation for On-Call demo data |  |  | Sagar Satpute | Closed |  | P3 | 2026-03-26 |  | 2026-04-21 | sprint-Fay | 4 | 0 | FILTER | unplanned-sprint |  | YES
Story | FILTER-12467 | Filter Accessibility - 4.1.2 (Name, role and value) |  |  | Swaroop Chavhan | RELEASED TO PROD |  | P3 | 2026-03-13 |  | 2026-04-27 | sprint-Fay | 48 | 0 | FILTER |  |  | YES
Story | FILTER-12472 | Filter Accessibility - other variations of 4.1.2, 1.4.13 |  |  | Swaroop Chavhan | RELEASED TO PROD |  | P3 | 2026-03-13 |  | 2026-04-27 | sprint-Fay | 24 | 0 | FILTER |  |  | YES
Task | FILTER-12342 | POC - Check from last 1 month, all QA tasks can be verified with Cursor browser or playwright | FILTER-12341 | Epic | Vaibhav Kumbhar | Resolved |  | P2 | 2026-03-03 |  | 2026-03-31 | sprint-Fay | 20 | 0 | FILTER | unplanned-sprint |  | YES
QA | FILTER-11569 | Manual QA Validation: Safety Resource Accessibility on SmartPAC (US-West) | FILTER-11539 | Escape Defect | Altamash Heroli | Closed without action |  | P2 | 2026-01-02 |  | 2026-03-30 | sprint-Fay | 0 | 2 | FILTER
Story | FILTER-11974 | Verify all Image Blur test cases for JS | FILTER-11972 | Epic | Altamash Heroli | Done |  | P2 | 2026-02-05 |  | 2026-04-15 | sprint-Fay | 55 | 65 | FILTER
QA | FILTER-12166 | Filter blocks W3Schools-style sandbox bypass via CDN/iframe (jsdelivr, Vercel, W3Spaces) | FILTER-12093 | Escape Defect | Altamash Heroli | Done |  | P1 | 2026-02-24 |  | 2026-04-06 | sprint-Fay | 5 | 6 | FILTER
QA | FILTER-12196 | [BugCrowd] Verify unauthenticated beta FID API is removed and beta FID controls are secure | FILTER-12003 | Defect | Altamash Heroli | Done |  | P3 | 2026-02-25 |  | 2026-04-14 | sprint-Fay | 1.5 | 4 | FILTER
QA | FILTER-12287 | Verify all Image Blur test cases for JS | FILTER-11974 | Story | Altamash Heroli | Done |  | P3 | 2026-02-27 |  | 2026-04-12 | sprint-Fay | 55 | 65 | FILTER
QA | FILTER-12339 | Verify deactivated GAC user (tfisher@d84.org) no longer appears in extension logs/reports | FILTER-12300 | Escape Defect | Altamash Heroli | Closed without action |  | P2 | 2026-03-03 |  | 2026-03-23 | sprint-Fay | 0 | 0 | FILTER
QA | FILTER-12350 | Verify Support Tool FID search and display (all FIDs, including no-domain) | FILTER-5401 | Task | Altamash Heroli | Done |  | P3 | 2026-03-03 |  | 2026-04-14 | sprint-Fay | 1 | 2 | FILTER
QA | FILTER-12353 | Verify Support Tool search includes FIDs with no domain/sub-domain | FILTER-5679 | Task | Altamash Heroli | Done |  | P3 | 2026-03-03 |  | 2026-04-21 | sprint-Fay | 2 | 2 | FILTER
QA | FILTER-12528 | Verify Translations for Spanish & French | FILTER-12293 | Story | Altamash Heroli | Done |  | P3 | 2026-03-17 |  | 2026-04-21 | sprint-Fay | 6 | 6 | FILTER
QA | FILTER-12529 | Verify Consumption of json Translations in Settings | FILTER-12305 | Story | Altamash Heroli | QA Verified |  | P3 | 2026-03-17 |  | 2026-04-09 | sprint-Fay | 0.5 | 3 | FILTER
QA | FILTER-12530 | Verify Consumption of json Translations in Policy Map | FILTER-12307 | Story | Altamash Heroli | QA Verified |  | P3 | 2026-03-17 |  | 2026-04-09 | sprint-Fay | 0.5 | 6 | FILTER
QA | FILTER-12531 | Cross check Filter Application Other Remaining instances of ¦ translate or instant | FILTER-12311 | Story | Altamash Heroli | QA Verified |  | P3 | 2026-03-17 |  | 2026-04-09 | sprint-Fay | 0.5 | 10 | FILTER
QA | FILTER-12599 | QA - FilterByPass - Malicious Application | FILTER-12572 | Support Request | Altamash Heroli | Closed without action |  | P1 | 2026-03-20 |  | 2026-03-23 | sprint-Fay | 0 | 0 | FILTER
QA | FILTER-12654 | Verify Activities report download (CSV/PDF) on Filter Console after fix | FILTER-12644 | Escape Defect | Altamash Heroli | Closed without action |  | P1 | 2026-03-24 |  | 2026-03-26 | sprint-Fay | 0 | 0 | FILTER
QA | FILTER-12683 | QA- Fix New Translation Strategy Related Issues | FILTER-12681 | Task | Altamash Heroli | Done |  | P3 | 2026-03-25 |  | 2026-04-14 | sprint-Fay | 5 | 5 | FILTER
Automation | FILTER-11660 | Create Automated Tests for FluentD Tokenization Phase 3 (UserToken) | FILTER-11631 | Story | Amit Shete | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Fay | 6 | 6 | FILTER | Capitalized-Feature
Automation | FILTER-11845 | Add test cases for SafetyConsole CustomList API token invalidation | FILTER-11687 | Defect | Amit Shete | Done |  | P2 | 2026-01-29 |  | 2026-04-14 | sprint-Fay | 4 | 4 | FILTER
Automation | FILTER-11975 | Run all automated Image Blur test cases and confirm results to support release readiness decision for the new NSFW model (MobileNetV2). | FILTER-11974 | Story | Amit Shete | Done |  | P2 | 2026-02-05 |  | 2026-03-02 | sprint-Fay | 2 | 3 | FILTER
Automation | FILTER-12023 | Re-run and validate Delegated Admin Custom List tests after JWT role fix | FILTER-12018 | Task | Amit Shete | Done |  | P3 | 2026-02-11 |  | 2026-03-18 | sprint-Fay | 1 | 1 | FILTER
Automation | FILTER-12167 | Sandbox bypass prevention – iframe/CDN block (W3Schools-style) | FILTER-12093 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-02-24 |  | 2026-04-06 | sprint-Fay | 0 | 5 | FILTER
Automation | FILTER-12340 | Scripting for “deactivated GAC user not in extension logs” verification | FILTER-12300 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-03-03 |  | 2026-03-23 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12351 | Scripting for Support Tool FID search and display (all FIDs, no-domain included) | FILTER-5401 | Task | Amit Shete | Done |  | P3 | 2026-03-03 |  | 2026-03-31 | sprint-Fay | 4 | 5 | FILTER
Automation | FILTER-12354 | Scripting for Support Tool search including FIDs with no domain/sub-domain | FILTER-5679 | Task | Amit Shete | Closed without action |  | P3 | 2026-03-03 |  | 2026-03-31 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12434 | QA- CLONE - Helping classroom team for PR review and Technical discussions | FILTER-12431 | Task | Amit Shete | Closed without action |  | P3 | 2026-03-12 |  | 2026-03-18 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12438 | QA- CLONE - Helping Home Team for the overall architecture of Parent Portal design Revamp and and AI Chat for their dashobard requirement | FILTER-12435 | Task | Amit Shete | Closed without action |  | P3 | 2026-03-12 |  | 2026-03-18 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12484 | QA- etld.securly.com.surf.surfnet.ca is not blocking for extension filtering | FILTER-12481 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-03-13 |  | 2026-03-30 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12600 | Automation - FilterByPass - Malicious Application | FILTER-12572 | Support Request | Amit Shete | Closed without action |  | P1 | 2026-03-20 |  | 2026-03-23 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12605 | QA- (Intermediate issue): Google domains added to allow/block list during simultaneous CSV uploads across policies | FILTER-12602 | Defect | Amit Shete | Closed without action |  | P2 | 2026-03-20 |  | 2026-03-23 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12609 | QA- Restricted Google domain can be added when DNS Allow List toggle is OFF | FILTER-12606 | Defect | Amit Shete | Closed without action |  | P2 | 2026-03-20 |  | 2026-03-23 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12655 | Cover Activities report download (CSV/PDF) on Filter Console | FILTER-12644 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-03-24 |  | 2026-03-26 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12680 | QA- Update if condition for scru cookie | FILTER-12677 | Task | Amit Shete | Closed without action |  | P3 | 2026-03-25 |  | 2026-03-26 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12684 | QA- Fix New Translation Strategy Related Issues | FILTER-12681 | Task | Amit Shete | Closed without action |  | P3 | 2026-03-25 |  | 2026-03-30 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12696 | QA- Removed NSFW image blur feature code and related files from the securly-extensions repository | FILTER-12693 | Task | Amit Shete | Closed without action |  | P3 | 2026-03-26 |  | 2026-03-26 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12700 | QA- Investigate and fix case generation for On-Call demo data | FILTER-12697 | Task | Amit Shete | Closed without action |  | P3 | 2026-03-26 |  | 2026-03-26 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-12799 | QA- Update Cron Job for tokenization | FILTER-12796 | Task | Amit Shete | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-28 | sprint-Fay | 0 | 0 | FILTER
Automation | FILTER-11568 | Validate Categorization Parity (SmartPAC vs Extension) | FILTER-11539 | Escape Defect | Amol Mithari | Done |  | P2 | 2026-01-02 |  | 2026-03-26 | sprint-Fay | 2.5 | 4 | FILTER
Automation | FILTER-12006 | [PageScan] QA – Verify blocking of twitter.gmsgroup.app for UK school (FID: securly@shaw-education.org.uk) | FILTER-12004 | Task | Amol Mithari | Done |  | P2 | 2026-02-10 |  | 2026-03-26 | sprint-Fay | 1.5 | 2 | FILTER
Automation | FILTER-12458 | QA- Filter bypass by taping on a link from Google Search - Crxtn | FILTER-12455 | Escape Defect | Amol Mithari | Closed without action |  | P1 | 2026-03-12 |  | 2026-04-14 | sprint-Fay | 0 | 3 | FILTER
Dev | FILTER-12140 | DEV - JS Extn (Chromebook) : Debug Info Not Displayed for Certain Domain Images When Opened Directly (setNSFWDebugAllTabs(true)) | FILTER-12139 | Defect | Arun Thakur | Done |  | P3 | 2026-02-23 |  | 2026-03-24 | sprint-Fay | 10 | 12 | FILTER
Dev | FILTER-12229 | DEV - JS (All Extensions): Youtube.YT logo on YT page, YT search page, YT video page and YT shorts is not clickable | FILTER-12228 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-02-25 |  | 2026-04-15 | sprint-Fay | 0 | 0 | FILTER
Dev | FILTER-12266 | DEV - JS (All Extensions): Securly Filter Dashboard YT videos thumbnails are blurred | FILTER-12265 | Defect | Arun Thakur | Closed without action |  | P2 | 2026-02-26 |  | 2026-04-06 | sprint-Fay | 0 | 0 | FILTER
Dev | FILTER-12270 | DEV - CLONE - JS (Windows+ Edge) Extensions. Securly Filter Dashboard YT videos thumbnails are blurred | FILTER-12265 | Defect | Arun Thakur | Done |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Fay | 4 | 4 | FILTER
Dev | FILTER-12273 | DEV - CLONE - JS (Windows+ Edge) Extensions. SFW images are also getting blurred by the model | FILTER-12272 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Fay | 0 | 0 | FILTER
Dev | FILTER-12276 | DEV - CLONE - JS (Windows+ Edge) Extensions. Image Blur. Amazon.com is accessible but links/logo/dropdowns not clickable | FILTER-12272 | Defect | Arun Thakur | Done |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Fay | 6 | 6 | FILTER
Dev | FILTER-12279 | DEV -JS (All Extensions) Image Blur on Search sites is bluring non blurred images on click | FILTER-12278 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-02-26 |  | 2026-03-23 | sprint-Fay | 0 | 0 | FILTER
Dev | FILTER-12595 | Restrict adding google.com from filter-Admin Allow list UI | FILTER-12573 | Escape Defect | Arun Thakur | Done |  | P0 | 2026-03-20 |  | 2026-03-20 | sprint-Fay | 6 | 6 | FILTER
Dev | FILTER-12653 | Fix Activities report download failure (CSV/PDF) on Filter Console | FILTER-12644 | Escape Defect | Arun Thakur | Closed without action |  | P1 | 2026-03-24 |  | 2026-03-25 | sprint-Fay | 0 | 4 | FILTER
Dev | FILTER-12694 | DEV - Removed NSFW image blur feature code and related files from the securly-extensions repository | FILTER-12693 | Task | Arun Thakur | Done |  | P3 | 2026-03-26 |  | 2026-03-26 | sprint-Fay | 1 | 1 | FILTER
QA | FILTER-12695 | QA- Removed NSFW image blur feature code and related files from the securly-extensions repository | FILTER-12693 | Task | Arun Thakur | Closed without action |  | P3 | 2026-03-26 |  | 2026-03-26 | sprint-Fay | 0 | 0 | FILTER
Dev | FILTER-12482 | DEV - etld.securly.com.surf.surfnet.ca is not blocking for extension filtering | FILTER-12481 | Escape Defect | Ashish Modak | Done |  | P2 | 2026-03-13 |  | 2026-03-18 | sprint-Fay | 8 | 8 | FILTER
Dev | FILTER-11567 | Align SmartPAC Categorization with Global Database (Self-Harm) | FILTER-11539 | Escape Defect | Ashish Temurnikar | Done |  | P2 | 2026-01-02 |  | 2026-03-23 | sprint-Fay | 4 | 4 | FILTER
Dev | FILTER-12005 | [PageScan] Investigate and fix blocking of twitter.gmsgroup.app for UK school (FID: securly@shaw-education.org.uk) | FILTER-12004 | Task | Ashish Temurnikar | Done |  | P2 | 2026-02-10 |  | 2026-03-23 | sprint-Fay | 6 | 5 | FILTER
QA | FILTER-11897 | Vector Expansion - Verify if http://kiddle/co/ is added to search scanning | FILTER-11895 | Story | Ayesha Kamde | Done |  | P2 | 2026-01-29 |  | 2026-04-06 | sprint-Fay | 5 | 6 | FILTER
QA | FILTER-12102 | Regression and translation checking for Dashboard page only for all 3 languages English, French and Spanish | FILTER-12100 | Story | Ayesha Kamde | Closed without action |  | P3 | 2026-02-19 |  | 2026-03-29 | sprint-Fay | 0 | 2 | FILTER
QA | FILTER-12141 | QA- JS Extn (Chromebook) : Debug Info Not Displayed for Certain Domain Images When Opened Directly (setNSFWDebugAllTabs(true)) | FILTER-12139 | Defect | Ayesha Kamde | Done |  | P3 | 2026-02-23 |  | 2026-03-25 | sprint-Fay | 2 | 2 | FILTER
QA | FILTER-12230 | QA- JS (All Extensions): Youtube.YT logo on YT page, YT search page, YT video page and YT shorts is not clickable | FILTER-12228 | Defect | Ayesha Kamde | Done |  | P1 | 2026-02-25 |  | 2026-04-20 | sprint-Fay | 1.5 | 2 | FILTER
QA | FILTER-12249 | QA- Games sites, sometimes shows Accessed for no reason when games category is blocked | FILTER-12247 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2026-02-26 |  | 2026-03-26 | sprint-Fay | 4 | 4 | FILTER
QA | FILTER-12267 | QA- JS (All Extensions): Securly Filter Dashboard YT videos thumbnails are blurred | FILTER-12265 | Defect | Ayesha Kamde | Done |  | P2 | 2026-02-26 |  | 2026-04-06 | sprint-Fay | 2 | 2 | FILTER
QA | FILTER-12274 | JS (All Extensions) Image Blur. Amazon.com is accessible but links/logo/dropdowns not clickable | FILTER-12272 | Defect | Ayesha Kamde | Done |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Fay | 2 | 2 | FILTER
QA | FILTER-12280 | QA- JS (All Extensions) Image Blur on Search sites is bluring non blurred images on click | FILTER-12278 | Defect | Ayesha Kamde | Closed without action |  | P1 | 2026-02-26 |  | 2026-03-24 | sprint-Fay | 0 | 2 | FILTER
QA | FILTER-12288 | Verify all Image Blur test cases for JS | FILTER-11974 | Story | Ayesha Kamde | Done |  | P3 | 2026-02-27 |  | 2026-03-03 | sprint-Fay | 25 | 5 | FILTER
QA | FILTER-12368 | QA- In prod: No, Global Navigation Labels and Profile Menu Labels Missing in RTQA4 and RTQA1 | FILTER-12366 | Defect | Ayesha Kamde | Closed without action |  | P2 | 2026-03-05 |  | 2026-03-24 | sprint-Fay | 0 | 0 | FILTER
QA | FILTER-12483 | QA- etld.securly.com.surf.surfnet.ca is not blocking for extension filtering | FILTER-12481 | Escape Defect | Ayesha Kamde | Done |  | P2 | 2026-03-13 |  | 2026-03-23 | sprint-Fay | 5 | 5 | FILTER
QA | FILTER-12597 | Verify that google.com is not added to allow list through any medium | FILTER-12573 | Escape Defect | Ayesha Kamde | Done |  | P0 | 2026-03-20 |  | 2026-03-20 | sprint-Fay | 5 | 5 | FILTER
QA | FILTER-12604 | QA- (Intermediate issue): Google domains added to allow/block list during simultaneous CSV uploads across policies | FILTER-12602 | Defect | Ayesha Kamde | Done |  | P2 | 2026-03-20 |  | 2026-03-26 | sprint-Fay | 2 | 2 | FILTER
QA | FILTER-12608 | QA- Restricted Google domain can be added when DNS Allow List toggle is OFF | FILTER-12606 | Defect | Ayesha Kamde | Done |  | P2 | 2026-03-20 |  | 2026-03-26 | sprint-Fay | 2 | 2 | FILTER
Task | FILTER-12431 | [Effort Tracking] Helping classroom team for PR review and Technical discussions |  |  | Harsh Verma | Closed |  | P3 | 2026-03-12 |  | 2026-03-31 | sprint-Fay | 4 | 4 | FILTER | unplanned-sprint
Dev | FILTER-12432 | DEV - CLONE - Helping classroom team for PR review and Technical discussions | FILTER-12431 | Task | Harsh Verma | Closed without action |  | P3 | 2026-03-12 |  | 2026-03-31 | sprint-Fay | 0 | 0 | FILTER
QA | FILTER-12433 | QA- CLONE - Helping classroom team for PR review and Technical discussions | FILTER-12431 | Task | Harsh Verma | Closed without action |  | P3 | 2026-03-12 |  | 2026-03-18 | sprint-Fay | 0 | 0 | FILTER
Task | FILTER-12435 | [Effort Tracking] - Helping Home Team for the overall architecture of Parent Portal design Revamp and and AI Chat for their dashobard requirement |  |  | Harsh Verma | Closed |  | P3 | 2026-03-12 |  | 2026-03-31 | sprint-Fay | 24 | 24 | FILTER | unplanned-sprint
Dev | FILTER-12436 | DEV - CLONE - Helping Home Team for the overall architecture of Parent Portal design Revamp and and AI Chat for their dashobard requirement | FILTER-12435 | Task | Harsh Verma | Closed without action |  | P3 | 2026-03-12 |  | 2026-03-31 | sprint-Fay | 0 | 0 | FILTER
QA | FILTER-12437 | QA- CLONE - Helping Home Team for the overall architecture of Parent Portal design Revamp and and AI Chat for their dashobard requirement | FILTER-12435 | Task | Harsh Verma | Closed without action |  | P3 | 2026-03-12 |  | 2026-03-18 | sprint-Fay | 0 | 0 | FILTER
Dev | FILTER-12101 | Dev changes needed to migrate the code for Dashboard page | FILTER-12100 | Story | Harshada Kude | Closed without action |  | P3 | 2026-02-19 |  | 2026-03-18 | sprint-Fay | 0 | 24 | FILTER
Dev | FILTER-12294 | Translations for Spanish & French - Json Creation & Verify | FILTER-12293 | Story | Harshada Kude | Done |  | P3 | 2026-02-27 |  | 2026-04-06 | sprint-Fay | 18 | 16 | FILTER
Dev | FILTER-12306 | [Filter] Creation & Consumption of json Translations in Settings | FILTER-12305 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Fay | 10 | 8 | FILTER
Dev | FILTER-12308 | [Filter] Creation & Consumption of json Translations in Remaining portion of Policy Map | FILTER-12307 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Fay | 12 | 10 | FILTER
Dev | FILTER-12310 | [Filter] Cross check Filter Application Other Remaining instances of ¦ translate or instant - Part 2 | FILTER-12311 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Fay | 12 | 10 | FILTER
Dev | FILTER-12312 | [Filter] Cross check Filter Application Other Remaining instances of ¦ translate or instant | FILTER-12311 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Fay | 6 | 6 | FILTER
Dev | FILTER-12367 | DEV - In prod: No, Global Navigation Labels and Profile Menu Labels Missing in RTQA4 and RTQA1 | FILTER-12366 | Defect | Harshada Kude | Done |  | P2 | 2026-03-05 |  | 2026-03-23 | sprint-Fay | 2.5 | 0.5 | FILTER
Dev | FILTER-12682 | DEV - Fix New Translation Strategy Related Issues | FILTER-12681 | Task | Harshada Kude | Done |  | P3 | 2026-03-25 |  | 2026-03-29 | sprint-Fay | 12 | 12 | FILTER
Dev | FILTER-11659 | Phase 3 - Implement FluentD Changes for Tokenization (UserToken) | FILTER-11631 | Story | Prateek Fotedar | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Fay | 12 | 12 | FILTER | Capitalized-Feature
Dev | FILTER-12195 | [BugCrowd] Remove unauthenticated beta FID management API (betaFids.php) to fix arbitrary add/remove of beta FIDs | FILTER-12003 | Defect | Prateek Fotedar | Done |  | P3 | 2026-02-25 |  | 2026-03-18 | sprint-Fay | 2 | 2 | FILTER
Dev | FILTER-12301 | POST /api/custom-list allows Admin to create custom list with usage "GLOBAL" - should be rejected | FILTER-11776 | Defect | Prateek Fotedar | Closed without action |  | P3 | 2026-03-01 |  | 2026-04-24 | sprint-Fay | 0.5 | 6 | FILTER | Capitalized-Feature
Dev | FILTER-12678 | DEV - Update if condition for scru cookie | FILTER-12677 | Task | Prateek Fotedar | Done |  | P3 | 2026-03-25 |  | 2026-03-25 | sprint-Fay | 1 | 1 | FILTER
QA | FILTER-12679 | QA- Update if condition for scru cookie | FILTER-12677 | Task | Prateek Fotedar | Closed without action |  | P3 | 2026-03-25 |  | 2026-03-26 | sprint-Fay | 0 | 1 | FILTER
Dev | FILTER-12797 | DEV - Update Cron Job for tokenization | FILTER-12796 | Task | Prateek Fotedar | Done |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Fay | 6 | 6 | FILTER
Dev | FILTER-11896 | Vector Expansion - Add http://kiddle.co/ to search scanning | FILTER-11895 | Story | Pratik Tiwari | Done |  | P2 | 2026-01-29 |  | 2026-04-06 | sprint-Fay | 10 | 10 | FILTER
Dev | FILTER-12074 | [sprox] Bench-marking of Sprox request - Time, CPU and Memory | FILTER-12071 | Story | Pratik Tiwari | Done |  | P3 | 2026-02-17 |  | 2026-03-18 | sprint-Fay | 24 | 10 | FILTER
Dev | FILTER-12165 | Block W3Schools (and similar) HTML sandbox bypass via CDN/third-party iframe loading (e.g. jsdelivr, Vercel, W3Spaces) | FILTER-12093 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-02-24 |  | 2026-04-06 | sprint-Fay | 16 | 13 | FILTER
Dev | FILTER-12456 | DEV - Filter bypass by taping on a link from Google Search - Crxtn | FILTER-12455 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-03-12 |  | 2026-04-14 | sprint-Fay | 16 | 16 | FILTER
Dev | FILTER-12335 | Captcha analysis and logging integration | FILTER-12334 | Story | Ravi Raj | Done |  | P3 | 2026-03-02 |  | 2026-03-30 | sprint-Fay | 16 | 16 | FILTER
Dev | FILTER-12337 | [sprox] Logging module integration | FILTER-12332 | Story | Ravi Raj | Done |  | P3 | 2026-03-03 |  | 2026-03-18 | sprint-Fay | 16 | 16 | FILTER
Dev | FILTER-11548 | Reopened - Dev Task -InProd:Yes, Blocked Email Activity is coming twice with crextn | FILTER-8474 | Escape Defect | Sagar Satpute | Closed without action |  | P3 | 2025-12-21 |  | 2026-03-18 | sprint-Fay | 0 | 2 | FILTER
Dev | FILTER-11977 | Implement audit logging for subscriptionType and accountExpiry (Support Tool + cron) | FILTER-11976 | Task | Sagar Satpute | Done |  | P3 | 2026-02-05 |  | 2026-04-16 | sprint-Fay | 13 | 21 | FILTER
Dev | FILTER-12349 | Support Tool: Improve search and display of FIDs (include FIDs without primary/sub domain) | FILTER-5401 | Task | Sagar Satpute | Done |  | P3 | 2026-03-03 |  | 2026-04-21 | sprint-Fay | 5 | 5 | FILTER
Dev | FILTER-12352 | Support Tool: Include FIDs with no domain/sub-domain in search results | FILTER-5679 | Task | Sagar Satpute | Done |  | P3 | 2026-03-03 |  | 2026-04-21 | sprint-Fay | 5 | 5 | FILTER
Dev | FILTER-12594 | Create a script to Remove google.com from existing customer (list shared in ticket) | FILTER-12573 | Escape Defect | Sagar Satpute | Done |  | P0 | 2026-03-20 |  | 2026-03-20 | sprint-Fay | 7 | 5 | FILTER
Dev | FILTER-12596 | Add validation in support tool so that google.com (even through csv upload) | FILTER-12573 | Escape Defect | Sagar Satpute | Done |  | P0 | 2026-03-20 |  | 2026-03-20 | sprint-Fay | 6 | 6 | FILTER
Dev | FILTER-12603 | DEV - (Intermediate issue): Google domains added to allow/block list during simultaneous CSV uploads across policies | FILTER-12602 | Defect | Sagar Satpute | Closed without action |  | P2 | 2026-03-20 |  | 2026-03-23 | sprint-Fay | 3 | 3 | FILTER
Dev | FILTER-12607 | DEV - Restricted Google domain can be added when DNS Allow List toggle is OFF | FILTER-12606 | Defect | Sagar Satpute | Closed without action |  | P2 | 2026-03-20 |  | 2026-03-23 | sprint-Fay | 2 | 2 | FILTER
Dev | FILTER-12698 | DEV - Investigate and fix case generation for On-Call demo data | FILTER-12697 | Task | Sagar Satpute | Done |  | P3 | 2026-03-26 |  | 2026-03-26 | sprint-Fay | 4 | 4 | FILTER
Dev | PTGM-664 | Fix linter errors in www-support-tool repo | PTGM-666 | Story | Sagar Satpute | Done |  | P2 | 2026-01-05 |  | 2026-04-14 | sprint-Fay | 18 | 21 | PTGM
QA | FILTER-11239 | Manual QA Validation for Duplicate Blocked Activity Email Alerts (CRXTN) | FILTER-8474 | Escape Defect | Surabhi Choudhary | Done |  | P3 | 2025-12-03 |  | 2026-03-23 | sprint-Fay | 0.5 | 2 | FILTER
QA | FILTER-11661 | Manual Testing Tokenization service for Extension | FILTER-11631 | Story | Surabhi Choudhary | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Fay | 24 | 24 | FILTER | Capitalized-Feature
QA | FILTER-11978 | Verify audit logging for subscriptionType and accountExpiry (Support Tool + cron) | FILTER-11976 | Task | Surabhi Choudhary | Done |  | P3 | 2026-02-05 |  | 2026-03-24 | sprint-Fay | 3 | 3 | FILTER
QA | FILTER-12798 | QA- Update Cron Job for tokenization | FILTER-12796 | Task | Surabhi Choudhary | Done |  | P3 | 2026-03-27 |  | 2026-04-23 | sprint-Fay | 2 | 2 | FILTER
QA | FILTER-13079 | Manual Testing Tokenization service for GO Extension | FILTER-11631 | Story | Surabhi Choudhary | Done |  | P2 | 2026-04-01 |  | 2026-04-14 | sprint-Fay | 24 | 24 | FILTER | Capitalized-Feature
Dev | FILTER-12468 | Fixing simple input with chips. | FILTER-12467 | Story | Swaroop Chavhan | Done |  | P3 | 2026-03-13 |  | 2026-04-06 | sprint-Fay | 12 | 16 | FILTER
Dev | FILTER-12469 | Fixing search with chips | FILTER-12467 | Story | Swaroop Chavhan | Done |  | P3 | 2026-03-13 |  | 2026-04-06 | sprint-Fay | 12 | 16 | FILTER
Dev | FILTER-12470 | Fixing search with autocomplete with chips | FILTER-12467 | Story | Swaroop Chavhan | Done |  | P3 | 2026-03-13 |  | 2026-04-06 | sprint-Fay | 12 | 16 | FILTER
Dev | FILTER-12471 | Fixing dropdown with chips (search inside) | FILTER-12467 | Story | Swaroop Chavhan | Done |  | P3 | 2026-03-13 |  | 2026-04-06 | sprint-Fay | 12 | 16 | FILTER
Dev | FILTER-12561 | Find and fix pending minor accessibility issues in Filter | FILTER-12472 | Story | Swaroop Chavhan | Done |  | P3 | 2026-03-18 |  | 2026-04-06 | sprint-Fay | 24 | 24 | FILTER
Dev | FILTER-12022 | Fix automation JWT token to use actual user role instead of hardcoded 'Admin' | FILTER-12018 | Task | Vaibhav Kumbhar | Done |  | P3 | 2026-02-11 |  | 2026-03-18 | sprint-Fay | 8 | 8 | FILTER
Dev | FILTER-12248 | DEV - Games sites, sometimes shows Accessed for no reason when games category is blocked | FILTER-12247 | Escape Defect | Vaibhav Kumbhar | Done |  | P1 | 2026-02-26 |  | 2026-03-24 | sprint-Fay | 16 | 16 | FILTER
Task | FILTER-12304 | Go broker server: Make fasthttp ReadBufferSize and WriteBufferSize configurable |  |  | Vaibhav Kumbhar | Closed | Done | P3 | 2026-03-02 | 2026-03-27 | 2026-04-21 | sprint-Fay | 4 | 4 | FILTER
Dev | FILTER-12338 | Extension logs show traffic for deactivated GAC user (tfisher@d84.org); user should not appear once removed from GAC | FILTER-12300 | Escape Defect | Vaibhav Kumbhar | Closed without action |  | P2 | 2026-03-03 |  | 2026-03-18 | sprint-Fay | 8 | 16 | FILTER
Dev | FILTER-12598 | DEV - FilterByPass - Malicious Application | FILTER-12572 | Support Request | Vaibhav Kumbhar | Closed without action |  | P1 | 2026-03-20 |  | 2026-03-23 | sprint-Fay | 0 | 0 | FILTER
Dev | PTGM-652 | Update www-support-tool repo | PTGM-684 | Story | Vaibhav Kumbhar | Done |  | P2 | 2025-12-10 |  | 2026-03-24 | sprint-Fay | 25 | 24 | PTGM

## Not Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Story | FILTER-12473 | Filter + Aware Accessibility - Mat tree |  |  | Swaroop Chavhan | Backlog |  | P3 | 2026-03-13 |  | 2026-04-21 | sprint-Fay | 0 | 0 | FILTER |  |  | YES
QA | FILTER-11844 | Verify fix for SafetyConsole CustomList API - Token invalidation on re-authentication | FILTER-11687 | Defect | Amit Shete | Open |  | P2 | 2026-01-29 |  | 2026-04-27 | sprint-Fay | 0 | 2 | FILTER
Dev | FILTER-11483 | Fix Canva.com NSFW Video Classification Timeout and Safe Image Click Blockers | FILTER-11418 | Defect | Arun Thakur | In Progress |  | P2 | 2025-12-19 |  | 2026-04-27 | sprint-Fay | 6 | 6 | FILTER
QA | FILTER-11485 | Fix Canva.com NSFW Video Classification Timeout and Safe Image Click Blockers | FILTER-11418 | Defect | Ayesha Kamde | Open |  | P2 | 2025-12-19 |  | 2026-04-16 | sprint-Fay | 2 | 2 | FILTER
QA | FILTER-12423 | [TS Extension] - QA task to reverify 'Google search results appear while typing in the bar' on TS | FILTER-7955 | Defect | Ayesha Kamde | Open |  | P2 | 2026-03-12 |  | 2026-04-14 | sprint-Fay | 0 | 2 | FILTER
QA | FILTER-12429 | [TS Extension] QA task to reverify issue - crextn - initial broker skips iframes | FILTER-12427 | Task | Ayesha Kamde | Open |  | P2 | 2026-03-12 |  | 2026-04-21 | sprint-Fay | 1 | 2 | FILTER
Dev | FILTER-11843 | SafetyConsole CustomList API - Old access tokens remain valid after new token generation | FILTER-11687 | Defect | Prateek Fotedar | Reopened |  | P2 | 2026-01-29 |  | 2026-04-28 | sprint-Fay | 12 | 12 | FILTER
Dev | FILTER-12420 | [TS Extension] Dev Task to fix 'Google search results appear while typing in the bar' on JS | FILTER-7955 | Defect | Pratik Tiwari | Open |  | P2 | 2026-03-12 |  | 2026-04-14 | sprint-Fay | 0 | 0 | FILTER
Dev | FILTER-12428 | [TS Extension]DEV - CLONE - crextn - initial broker skips iframes | FILTER-12427 | Task | Pratik Tiwari | Reopened |  | P2 | 2026-03-12 |  | 2026-04-21 | sprint-Fay | 3 | 4 | FILTER
Defect | FILTER-7955 | [TS Extension]Google search results appear while typing in the bar |  |  | Pratik Tiwari | Open |  | P2 | 2025-04-18 |  | 2026-04-27 | sprint-Fay | 0 | 0 | FILTER | EXTN, MV3
Dev | PTGM-663 | Fix linter errors in www-filter repo | PTGM-666 | Story | Sagar Satpute | Open |  | P2 | 2026-01-05 |  | 2026-04-14 | sprint-Fay | 0 | 0 | PTGM

## Removed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Defect | FILTER-12150 | JS (All Extensions) Some sites opened from search link from Google AI mode does not start image blurring right away |  |  | Arun Thakur | Open |  | P2 | 2026-02-24 |  | 2026-04-02 | sprint-Fay | 0 | 2 | FILTER | unplanned-sprint |  | YES
Defect | FILTER-12153 | JS (All Extensions): Esc Button is circumventing image blur |  |  | Arun Thakur | Open |  | P1 | 2026-02-24 |  | 2026-03-29 | sprint-Fay | 1 | 2 | FILTER | unplanned-sprint |  | YES
Escape Defect | FILTER-9853 | Filter >> Activities and Emails for Blocked search terms on Yandex, Baidu and DuckDuckGo, do not have search query in external links |  |  | Arun Thakur | Open |  | P3 | 2025-08-31 |  | 2026-04-10 | sprint-Fay | 6.5 | 2 | FILTER |  |  | YES
Story | FILTER-12400 | P1 Escalation - Extension API Fortification |  |  | Ashish Modak | Open |  | P1 | 2026-03-10 |  | 2026-04-28 | sprint-Fay | 0 | 0 | FILTER | p1escalation, unplanned-sprint |  | YES
Escape Defect | FILTER-12010 | P1 Escalation-Extension Bypass - Bookmark + stop page |  |  | Pratik Tiwari | Confirmation | Fixed | P1 | 2026-02-10 | 2026-04-06 | 2026-04-28 | sprint-Fay | 20 | 0 | FILTER | jira_added, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_p1, jira_qa_verified, zendesk_enterprise, zendesk_org_at_risk |  | YES
Story | FILTER-12333 | [sprox] RTQA5 testing for DNS & SPAC | FILTER-8230 | Epic | Ravi Raj | Closed without action |  | P3 | 2026-03-02 |  | 2026-04-14 | sprint-Fay | 16 | 0 | FILTER |  |  | YES
Task | FILTER-10604 | Placeholder task to track the efforts used for Vanta tool task completion |  |  | Harsh Verma | In Progress |  | P3 | 2025-11-03 |  | 2026-04-27 | sprint-Fay | 0 | 8 | FILTER | unplanned-sprint
Task | FILTER-11697 | Extension of FILTER-11605 |  |  | Harsh Verma | In Progress |  | P3 | 2026-01-19 |  | 2026-04-27 | sprint-Fay | 0 | 24 | FILTER | unplanned-sprint

## P1 Escalation
P1 Escalation — FILTER · sprint-Fay (2026-03-17 → 2026-03-30)
sprint-Fay tickets where Issue Type = Escape Defect AND Priority = P1 AND summary contains 'P1 Escalation' (regardless of bucket). Total = 7.
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Bucket
Escape Defect | FILTER-11610 | P1 Escalation-CORs Errors at BlueBeam and Boomerang S3 Amazon domains ¦ St. Vrain |  |  | Ramani Cheruvu | In Progress | Fixed | P1 | 2026-01-08 | 2026-01-27 | 2026-04-27 | sprint-Fay | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_reopened, p1escalation, unplanned-sprint, zendesk_enterprise |  | Removed
Escape Defect | FILTER-12476 | P1 Escalation-Extension Bypass - Opening new tab |  |  | Shashank Tiwari | QA READY | Fixed | P1 | 2026-03-13 | 2026-04-28 | 2026-04-28 | sprint-Fay | 1 | 0 | FILTER | jira_added, jira_escalated, jira_in_progress, jira_open, jira_p1, zendesk_enterprise |  | Removed
Escape Defect | FILTER-12010 | P1 Escalation-Extension Bypass - Bookmark + stop page |  |  | Pratik Tiwari | Confirmation | Fixed | P1 | 2026-02-10 | 2026-04-06 | 2026-04-28 | sprint-Fay | 20 | 0 | FILTER | jira_added, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_p1, jira_qa_verified, zendesk_enterprise, zendesk_org_at_risk |  | Removed
Escape Defect | FILTER-12093 | P1 Escalation-Students bypass Filter via W3Schools HTML sandbox using CDN / third-party iframe loading (GitHub content proxy) |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-02-18 | 2026-03-13 | 2026-04-16 | sprint-Fay | 21 | 0 | FILTER | jira_added, jira_closed_notify, jira_confirmation, jira_done, jira_escalated, jira_open, jira_p1, jira_qa_verified, jira_reopened, unplanned-sprint, zendesk_enterprise |  | Removed
Escape Defect | FILTER-12247 | P1 Escalation-Appending allowed site to the blocked URL breaks CRXTN |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-02-26 | 2026-03-24 | 2026-04-17 | sprint-Fay | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_closed_notify, jira_confirmation, jira_done, jira_done_notified, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_p2, jira_qa_verified, p1escalation |  | Completed
Escape Defect | FILTER-12644 | P1 Escalation-Unable to download reports on Activities tab - Filter |  |  | Shashank Tiwari | Closed | Configuration Issue | P1 | 2026-03-24 | 2026-03-26 | 2026-04-21 | sprint-Fay | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_closed_notify, jira_escalated, jira_open, jira_p1, p1escalation, unplanned-sprint, zendesk_enterprise, zendesk_org_at_risk |  | Completed
Escape Defect | FILTER-7666 | P1 Escalation-File downloading in Image Google Search |  |  | Shashank Tiwari | Confirmation | Cannot Reproduce | P1 | 2025-03-26 | 2025-09-04 | 2026-04-28 | sprint-Fay | 2 | 12 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_closed_notify, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_reopened, jira_resolved, zendesk_org_at_risk |  | Removed