## Capacity vs Delivery
Capacity vs Delivery — FILTER · sprint-Gonzalo (Tue 31 Mar → Mon 13 Apr 2026)
Team Composition (per Securly-PjM-Skills.md Part 2 — Filter India roster). Inactive members for this sprint window are shaded grey with a roster note.
Name | Role | Function / Split | Allocation (FTE) | Seniority | Employment | Notes
Shashank Tiwari | Project Manager | PM / Delivery | 0 | Lead | FTE | Not counted in delivery capacity
Harsh Verma | FE | FrontEnd Architect (Angular) | 1 | Senior | FTE
Arun Thakur | FE + Ext | Angular / Extension | 1 | Medium | FTE
Harshada Kude | FE | Angular | 1 | Junior | FTE
Shailendra Singh | FE | Angular | 1 | Medium | FTE
Swaroop Chavhan | FE + Ext | Angular / Extension | 1 | Medium | FTE
Ashish Modak | BE Architect | Extension / Go / PHP | 1 | Senior | FTE
Prateek Fotedar | BE (www) | Go / PHP | 1 | Senior | FTE
Sagar Satpute | BE (www) | Go / PHP | 1 | Medium | FTE
Vaibhav Kumbhar | BE | Go / PHP | 1 | Medium | FTE
Ashish Temurnikar | BE | DNS / SPAC / Squid / Rust | 1 | Senior | FTE
Ravi Raj | BE | DNS / SPAC / Squid / Rust | 1 | Medium | FTE
Pratik Tiwari | BE + Ext | Extension / Go / Rust | 1 | Senior | FTE
Altamash Heroli | QA | Pri. Manual QA | 1 | Senior | FTE
Surabhi Choudhary | QA | Sr. Manual QA | 1 | Senior | FTE
Ayesha Kamde | QA | Manual QA | 1 | Junior | FTE
Amol Mithari | Auto QA Lead | Team Lead — Auto QA / SDET | 1 | Lead | FTE
Amit Shete | Auto QA | Pri. SDET | 1 | Senior | FTE
Rachit Mishra | Auto QA | SDET | 0 | Junior | FTE | Left team on 20-Feb-2026 — not part of this sprint
Total FILTER allocation |  |  |  | FTE-equivalent heads available to FILTER
Capacity Parameters (yellow cells are inputs — re-run the script after edits)
Parameter | Value | Description
Sprint length (working days) | 10 | FILTER 15-day sprint Tue → Mon. sprint-Gonzalo = 2026-03-31 → 2026-04-13.
Company holidays in sprint | 0 | India calendar 2026 — none in window
Effective working days (sprint − company holidays) |  | Used as the per-person calendar for availability
Hours per working day (nominal) | 8 | Standard working day
Focus factor (productive fraction) | 0.9 | 90% — what SLT expects (sprint-analysis default)
Misc buffer (meetings, scrums, code review, …) | 20% | 20% blanket reservation deducted from Available to get Net Available
Effective hours per FTE per sprint
Allocated FTE on FILTER (active this sprint) | 17 | Headcount actually working this sprint (excludes joiners/leavers outside window)
Ideal capacity for the sprint (hrs)
Issue scope (Jira projects) | FILTER, PTGM, FDSE | Tickets pulled with `project in (FILTER, PTGM, FDSE) AND sprint = …` — FDSE: 3 · FILTER: 344 · PTGM: 5
Capacity vs Actual Delivery — sprint-Gonzalo
Metric | Hours | % of Ideal | Rating | Notes
Actual Availability |  |  |  | Sum of per-person availability (Ideal − leaves)
Misc Buffer (20%) |  |  |  | Reserved for meetings, scrums, code reviews
Net Available (Available − Misc Buffer) |  |  |  | Realistic delivery capacity — used as the denominator for Completed %
Completed |  |  |  | Sum of in-sprint timeSpent (Completed bucket)
Not Completed (Spillover) |  |  |  | Original estimate for spillover (carried into next sprint)
Removed |  |  |  | Original estimate for issues removed mid-sprint
Completed by Priority
Tickets (parents) = unique parent items (Story / Task / Defect / Escape Defect) — subtasks roll up to their parent so 1 parent + 3 subtasks = 1 ticket. Tickets (incl. subtasks) = raw record count incl. every Dev / QA / Automation / Review / Test Case Creation / Debug subtask. Hours = sum across parents and subtasks; matches the core-team Completed hours on the Per-person Delivery sheet.
Priority | Tickets (parents) | Tickets (incl. subtasks) | Hours (incl. subtasks) | % of Completed Hrs | % of Tickets (parents) | Notes
P0 | 9 | 27 | 59 |  |  | Critical / production halting
P1 | 20 | 53 | 164.5 |  |  | P1 — high priority (see P1 Escalation tab for escalations)
P2 | 23 | 50 | 394.68 |  |  | Major
P3 | 27 | 52 | 530 |  |  | Standard
P4 | 1 | 2 | 25 |  |  | Minor / nice-to-have
TOTAL | 80 | 184 | 1173.18 | 100% | 100% | Sum of Completed bucket (core roster)
Sprint Completion (spillover = Not Completed)
Metric | Tickets | Planned Hrs (OE) | % by Tickets | % by Hrs | Notes
Completed (closed in sprint) | 184 | 1065.52 |  |  | In-sprint deliverables
Spillover (not completed → carry-over) | 36 | 189 |  |  | Original estimate carried to next sprint
Removed (mid-sprint scope cut) | 6 | 2 | — | — | Excluded from completion ratio (out of scope)
Mid-sprint additions (core) | 10 |  | — | — | Late-arriving work (Jira issueKeysAddedDuringSprint)
Sprint completion rate (tickets) | 83.64% | Below Target | Completed ÷ (Completed + Spillover)
Sprint completion rate (planned hrs) | 84.93% | Below Target | Σ OE Completed ÷ Σ OE (Completed + Spillover)
Planned completion rate (tickets, excludes mid-sprint adds) | 83.41% | Below Target | Originally-committed tickets only
Planned completion rate (planned hrs, excludes mid-sprint adds) | 84.38% | Below Target | Originally-committed planned hours only
P1 Escalation snapshot
9 ticket(s) in sprint-Gonzalo match 'P1 Escalation' in the title — 5 closed, 4 still open. See the 'P1 Escalation' tab.
Mid-sprint additions snapshot
10 ticket(s) were added to sprint-Gonzalo after it started (issueKeysAddedDuringSprint) — Completed 8, Spillover 1, Removed 1. Highlighted in amber on every detail sheet (Added Mid-Sprint = YES).
Assumptions & caveats
• Sprint window from Jira (/rest/agile/1.0/sprint/5708): 2026-03-31 → 2026-04-13 (10 Mon–Fri working days). Refresh with fetch_filter_sprint_meta.py + fetch_filter_sprint_issues.py.
• Issues pulled from FILTER + PTGM + FDSE (project-scope expanded for the India scrum team's split across the three products).
• Date-aware roster: Amol Mithari joined 20-Feb-2026; Rachit Mishra's last day was 20-Feb-2026. Inactive members for this sprint window are shaded grey in the Team Composition table and excluded from per-person availability + delivery.
• Available (hrs) = (effective working days − leave days) × 8 × focus factor, where effective working days = sprint working days − company holidays falling inside the sprint − days outside the person's employment window. Per-person Delivery shows leave days in Column G to explain the delta from a full sprint.
• Net Available = Available − 20% Misc Buffer for meetings, scrums, code review, etc. Completed/Not Completed/Removed % of capacity use Net Available as the denominator.
• Time Spent on Completed sheet uses the in-sprint hybrid worklog rule (sprint-analysis.md): single-sprint = timespent; multi-sprint = SUM of worklogs whose started ∈ [sprintStart, sprintEnd].
• Not Completed and Removed totals use Original Estimate.
• Removed list comes from the Sprint Report puntedIssues (greenhopper API).
• Core roster only: assignees outside Securly-PjM-Skills.md Part 2 are dropped from per-person + detail sheets.
• P1 Escalation tab is filtered to Issue Type = Escape Defect AND Priority = P1 AND title contains 'P1 Escalation'.
• Completed by Priority — Tickets (parents) rolls subtasks up to their parent (each work item counted once at its parent priority); Tickets (incl. subtasks) shows the raw record count for comparison. The Hours column sums every record (parent + subtasks) and matches the core-team Completed total.
• Spillover = Not Completed bucket (tickets carried into the next sprint).
• Sprint completion rate uses Completed ÷ (Completed + Spillover); Removed tickets are excluded (treated as scope cut). 'Planned' rate also excludes mid-sprint additions.
• All detail sheets (Completed, Not Completed, Removed) highlight tickets added after sprint start (Jira sprint-report issueKeysAddedDuringSprint) in amber, with an 'Added Mid-Sprint = YES' tag column.
• Ratings: ≥85% On Target (green), 70–85% Below Target (amber), <70% Significantly Below (red).

## Per-person Delivery
Assignee | Completed (hrs) | Not Completed (hrs) | Removed (hrs) | Efficiency | Available (hrs) | Leave Days (sprint) | Misc Buffer 20% (hrs) | Net Available (hrs)
Harsh Verma | 94 | 48 | 0 |  | 72 | 0
Arun Thakur | 69 | 0 | 2 |  | 72 | 0
Harshada Kude | 131.5 | 0 | 0 |  | 64.8 | 1
Shailendra Singh | 0 | 0 | 0 |  | 72 | 0
Swaroop Chavhan | 144 | 52 | 0 |  | 72 | 0
Ashish Modak | 2 | 0 | 0 |  | 64.8 | 1
Prateek Fotedar | 30.5 | 20 | 0 |  | 72 | 0
Sagar Satpute | 77 | 0 | 0 |  | 72 | 0
Vaibhav Kumbhar | 83 | 0 | 0 |  | 72 | 0
Ashish Temurnikar | 24 | 0 | 0 |  | 72 | 0
Ravi Raj | 91 | 0 | 0 |  | 72 | 0
Pratik Tiwari | 50 | 6 | 0 |  | 72 | 0
Altamash Heroli | 159.68 | 0 | 0 |  | 64.8 | 1
Surabhi Choudhary | 115 | 0 | 0 |  | 72 | 0
Ayesha Kamde | 56.5 | 7 | 0 |  | 57.6 | 2
Amol Mithari | 16 | 45 | 0 |  | 72 | 0
Amit Shete | 30 | 11 | 0 |  | 64.8 | 1
TOTAL

## Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Story | FILTER-11974 | Verify all Image Blur test cases for JS | FILTER-11972 | Epic | Altamash Heroli | Done |  | P2 | 2026-02-05 |  | 2026-04-15 | sprint-Gonzalo | 55 | 65 | FILTER |  |  | YES
Debug | FILTER-13090 | POC for Aware TAS flow for DNS |  |  | Ashish Temurnikar | Resolved |  | P2 | 2026-04-01 |  | 2026-04-13 | sprint-Gonzalo | 8 | 8 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-13022 | [Effort Tracking] - Helping Home Team for the overall architecture of Parent Portal design Revamp and and AI Chat for their dashobard requirement and Accessibility requirements |  |  | Harsh Verma | Resolved |  | P3 | 2026-03-31 |  | 2026-04-13 | sprint-Gonzalo | 30 | 32 | FILTER |  |  | YES
Debug | FILTER-13023 | [Effort Tracking] Helping classroom team for PR review and Technical discussions |  |  | Harsh Verma | Resolved |  | P3 | 2026-03-31 |  | 2026-04-13 | sprint-Gonzalo | 4 | 4 | FILTER |  |  | YES
Debug | FILTER-13502 | [Effort tracking] - Add Cusror implementation and visual regression in Desisgn System component |  |  | Harsh Verma | Resolved |  | P2 | 2026-04-13 |  | 2026-04-13 | sprint-Gonzalo | 24 | 20 | FILTER | unplanned-sprint |  | YES
Task | FILTER-13339 | When Policy Name is empty, UI breaks as key is undefined |  |  | Harshada Kude | Closed | Fixed | P2 | 2026-04-08 | 2026-04-08 | 2026-04-21 | sprint-Gonzalo | 2 | 2 | FILTER | unplanned-sprint |  | YES
Escape Defect | FILTER-13360 | P0 Escalation- Investigate and fix 'identifier at index 0 is empty' errors from tokenization-service |  |  | Prateek Fotedar | RELEASED TO PROD | Fixed | P0 | 2026-04-08 | 2026-04-09 | 2026-04-15 | sprint-Gonzalo | 1 | 0 | FILTER | p0escalation, unplanned-sprint |  | YES
Task | FILTER-13080 | Generate context for filter | FILTER-12341 | Epic | Vaibhav Kumbhar | Code Review | Fixed | P3 | 2026-04-01 | 2026-04-27 | 2026-04-27 | sprint-Gonzalo | 2 | 0 | FILTER | unplanned-sprint |  | YES
QA | FILTER-12166 | Filter blocks W3Schools-style sandbox bypass via CDN/iframe (jsdelivr, Vercel, W3Spaces) | FILTER-12093 | Escape Defect | Altamash Heroli | Done |  | P1 | 2026-02-24 |  | 2026-04-06 | sprint-Gonzalo | 5 | 6 | FILTER
QA | FILTER-12287 | Verify all Image Blur test cases for JS | FILTER-11974 | Story | Altamash Heroli | Done |  | P3 | 2026-02-27 |  | 2026-04-12 | sprint-Gonzalo | 55 | 65 | FILTER
QA | FILTER-12325 | QA- BugCrowd-850af9c1-f86b-4c74-91ac-94ea808c8e9b-Deleted User to Continue Performing Privileged Actions (Account Deletion Bypass) | FILTER-12323 | Defect | Altamash Heroli | QA Verified |  | P3 | 2026-03-02 |  | 2026-04-24 | sprint-Gonzalo | 12 | 4 | FILTER
QA | FILTER-12407 | QA- Duplicate policies appearing in Policy editor. | FILTER-12405 | Escape Defect | Altamash Heroli | Closed without action |  | P3 | 2026-03-10 |  | 2026-04-06 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-12528 | Verify Translations for Spanish & French | FILTER-12293 | Story | Altamash Heroli | Done |  | P3 | 2026-03-17 |  | 2026-04-21 | sprint-Gonzalo | 6 | 6 | FILTER
QA | FILTER-12529 | Verify Consumption of json Translations in Settings | FILTER-12305 | Story | Altamash Heroli | QA Verified |  | P3 | 2026-03-17 |  | 2026-04-09 | sprint-Gonzalo | 0.5 | 3 | FILTER
QA | FILTER-12530 | Verify Consumption of json Translations in Policy Map | FILTER-12307 | Story | Altamash Heroli | QA Verified |  | P3 | 2026-03-17 |  | 2026-04-09 | sprint-Gonzalo | 0.5 | 6 | FILTER
QA | FILTER-12531 | Cross check Filter Application Other Remaining instances of ¦ translate or instant | FILTER-12311 | Story | Altamash Heroli | QA Verified |  | P3 | 2026-03-17 |  | 2026-04-09 | sprint-Gonzalo | 0.5 | 10 | FILTER
QA | FILTER-12535 | QA - Build IP lookup tool to make queries across all clusters. | FILTER-12396 | Task | Altamash Heroli | Done |  | P1 | 2026-03-17 |  | 2026-04-21 | sprint-Gonzalo | 4 | 6 | FILTER
QA | FILTER-12782 | QA- Safety Console. Image blur. Confirmation popup does not have text in it and is not functional | FILTER-12780 | Defect | Altamash Heroli | QA Verified |  | P3 | 2026-03-27 |  | 2026-04-09 | sprint-Gonzalo | 1 | 1 | FILTER
QA | FILTER-12790 | QA- Safety Console. Allow/Block Search terms. Even terms added as contains are getting added as Exact | FILTER-12788 | Defect | Altamash Heroli | Done |  | P1 | 2026-03-27 |  | 2026-04-21 | sprint-Gonzalo | 1 | 1 | FILTER
QA | FILTER-12866 | QA- Support Tool >> Custom list UI. Custom List table >> "Last updated by" field is not showing value for every list | FILTER-12864 | Defect | Altamash Heroli | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-28 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-12870 | QA- Support Tool >> Custom list UI. Custom List table >> we are able to see global lists which are created by non support tool users as well | FILTER-12868 | Defect | Altamash Heroli | QA Verified |  | P1 | 2026-03-27 |  | 2026-04-22 | sprint-Gonzalo | 0.5 | 1 | FILTER
QA | FILTER-12894 | QA- Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for more than 255 character length | FILTER-12892 | Defect | Altamash Heroli | QA Verified |  | P2 | 2026-03-27 |  | 2026-04-20 | sprint-Gonzalo | 0.33 | 1 | FILTER
QA | FILTER-12898 | QA- Support Tool >> Custom list UI. Create custom list Resource and Update custom list Resource, drawer should validated for comment length on Save of that drawer | FILTER-12896 | Defect | Altamash Heroli | QA Verified |  | P2 | 2026-03-27 |  | 2026-04-20 | sprint-Gonzalo | 0.33 | 1 | FILTER
QA | FILTER-12902 | QA- Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for duplicate Custom list name | FILTER-12900 | Defect | Altamash Heroli | QA Verified |  | P2 | 2026-03-27 |  | 2026-04-21 | sprint-Gonzalo | 0.5 | 1 | FILTER
QA | FILTER-12914 | QA- Safety Console >> Allow/Block URL. Weird wildcards are not showing ! mark | FILTER-12912 | Defect | Altamash Heroli | Closed without action |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-12975 | QA- Safety Console >> Activities. More more info Popup does not have Search, Site, Public IP, Block and Allow buttons translated | FILTER-12973 | Escape Defect | Altamash Heroli | Done |  | P2 | 2026-03-30 |  | 2026-04-21 | sprint-Gonzalo | 1 | 1 | FILTER
QA | FILTER-13101 | QA- (Not in Pkg 41) Support Tool >> Custom list UI. Not able to create Custom list | FILTER-13099 | Defect | Altamash Heroli | Done |  | P1 | 2026-04-02 |  | 2026-04-21 | sprint-Gonzalo | 1 | 1 | FILTER
QA | FILTER-13292 | QA - P1 Escalation-Searches and Sites not generating Cases ¦ Comal ISD for pkg 40 | FILTER-13286 | Escape Defect | Altamash Heroli | Done |  | P0 | 2026-04-07 |  | 2026-04-14 | sprint-Gonzalo | 6 | 4 | FILTER
QA | FILTER-13375 | QA- Safety Console >> Policy Editor. Delete policy popup has translation key instead of message. | FILTER-13373 | Defect | Altamash Heroli | Done |  | P1 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 1 | 1 | FILTER
QA | FILTER-13383 | QA- Safety Console >> Policy Map >> Custom Group. Delete CG popup has translation key instead of message. | FILTER-13381 | Defect | Altamash Heroli | QA Verified |  | P1 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 1 | 1 | FILTER
QA | FILTER-13417 | QA- MT User >> Filter >> Policy Editor. After making any changes to any policy, MT user is taken to Global policy. | FILTER-13415 | Defect | Altamash Heroli | QA Verified |  | P2 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 1 | 1 | FILTER
QA | FILTER-13421 | QA- MT User >> Filter >> Policy Editor. MT not able to Create or Clone policies | FILTER-13419 | Defect | Altamash Heroli | QA Verified |  | P1 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 1 | 1 | FILTER
QA | FILTER-13425 | QA- MT User >> Filter >> Users. Clicking on Users redirects MT user to Policy Editor by auto reload | FILTER-13423 | Defect | Altamash Heroli | QA Verified |  | P2 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 1 | 1 | FILTER
QA | FILTER-13436 | QA- Safety Console >> Filter. Extension. Dual Provision Kid with SG policy higher than OU/SSU, does not generate cases | FILTER-13434 | Escape Defect | Altamash Heroli | QA Verified |  | P0 | 2026-04-10 |  | 2026-04-14 | sprint-Gonzalo | 1 | 1 | FILTER
QA | FILTER-13452 | QA- Support Tool. Even if the user selects another FID from the FID Detail page's FID name dropdown, the new FID details are not updated on the Detail Page. | FILTER-13450 | Escape Defect | Altamash Heroli | Done |  | P1 | 2026-04-11 |  | 2026-04-16 | sprint-Gonzalo | 1.5 | 1.5 | FILTER
QA | FILTER-13472 | QA- Safety Console >> Filter. Custom Groups page is blank for Dual Provision FID. | FILTER-13470 | Escape Defect | Altamash Heroli | Done |  | P0 | 2026-04-11 |  | 2026-04-14 | sprint-Gonzalo | 2 | 1 | FILTER
QA | FILTER-13496 | QA- Custom groups are not displayed | FILTER-13494 | Escape Defect | Altamash Heroli | Done |  | P2 | 2026-04-12 |  | 2026-04-14 | sprint-Gonzalo | 0.02 | 0.02 | FILTER
Automation | FILTER-11382 | Automated E2E Regression Test: Validate Complete YouTube URL Logging from Embedded Clicks | FILTER-11181 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2025-12-09 |  | 2026-04-14 | sprint-Gonzalo | 0 | 6 | FILTER
Automation | FILTER-11660 | Create Automated Tests for FluentD Tokenization Phase 3 (UserToken) | FILTER-11631 | Story | Amit Shete | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Gonzalo | 6 | 6 | FILTER | Capitalized-Feature
Automation | FILTER-11845 | Add test cases for SafetyConsole CustomList API token invalidation | FILTER-11687 | Defect | Amit Shete | Done |  | P2 | 2026-01-29 |  | 2026-04-14 | sprint-Gonzalo | 4 | 4 | FILTER
Automation | FILTER-11874 | Add tests for CustomList API token invalidation on Filter Product disable | FILTER-11688 | Escape Defect | Amit Shete | Done |  | P3 | 2026-01-29 |  | 2026-04-14 | sprint-Gonzalo | 4 | 4 | FILTER
Automation | FILTER-11975 | Run all automated Image Blur test cases and confirm results to support release readiness decision for the new NSFW model (MobileNetV2). | FILTER-11974 | Story | Amit Shete | Done |  | P2 | 2026-02-05 |  | 2026-03-02 | sprint-Gonzalo | 2 | 3 | FILTER
Automation | FILTER-12167 | Sandbox bypass prevention – iframe/CDN block (W3Schools-style) | FILTER-12093 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-02-24 |  | 2026-04-06 | sprint-Gonzalo | 0 | 5 | FILTER
Automation | FILTER-12201 | SPROX Testing with P0 suite | FILTER-12199 | Task | Amit Shete | Done |  | P2 | 2026-02-25 |  | 2026-04-14 | sprint-Gonzalo | 4.5 | 8 | FILTER
Automation | FILTER-12444 | Automation - Duplicate policies appearing in Policy editor | FILTER-12405 | Escape Defect | Amit Shete | Closed without action |  | P3 | 2026-03-12 |  | 2026-04-06 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12562 | Re-run SPROX Testing with P0 suite post Dev Fixes | FILTER-12199 | Task | Amit Shete | Done |  | P2 | 2026-03-18 |  | 2026-04-14 | sprint-Gonzalo | 6 | 6 | FILTER
QA | FILTER-12565 | QA- [sprox] Keyword scanning is not working for all search engines except google.com | FILTER-12563 | Defect | Amit Shete | Done |  | P1 | 2026-03-18 |  | 2026-04-08 | sprint-Gonzalo | 0.5 | 0.5 | FILTER
Automation | FILTER-12566 | QA- [sprox] Keyword scanning is not working for all search engines except google.com | FILTER-12563 | Defect | Amit Shete | Done |  | P1 | 2026-03-18 |  | 2026-04-06 | sprint-Gonzalo | 1 | 1 | FILTER
Automation | FILTER-12660 | QA- Policy Map does not display OU names when searching or filtering | FILTER-12657 | Escape Defect | Amit Shete | Closed without action |  | P3 | 2026-03-24 |  | 2026-03-26 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12688 | QA- [Edge] Overlay gets stuck in an infinite loading loop on YouTube thumbnails | FILTER-12685 | Defect | Amit Shete | Closed without action |  | P1 | 2026-03-25 |  | 2026-04-07 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12783 | QA- Safety Console. Image blur. Confirmation popup does not have text in it and is not functional | FILTER-12780 | Defect | Amit Shete | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12791 | QA- Safety Console. Allow/Block Search terms. Even terms added as contains are getting added as Exact | FILTER-12788 | Defect | Amit Shete | Done |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 2 | 2 | FILTER
Automation | FILTER-12867 | QA- Support Tool >> Custom list UI. Custom List table >> "Last updated by" field is not showing value for every list | FILTER-12864 | Defect | Amit Shete | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12871 | QA- Support Tool >> Custom list UI. Custom List table >> we are able to see global lists which are created by non support tool users as well | FILTER-12868 | Defect | Amit Shete | Closed without action |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12895 | QA- Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for more than 255 character length | FILTER-12892 | Defect | Amit Shete | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12899 | QA- Support Tool >> Custom list UI. Create custom list Resource and Update custom list Resource, drawer should validated for comment length on Save of that drawer | FILTER-12896 | Defect | Amit Shete | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12903 | QA- Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for duplicate Custom list name | FILTER-12900 | Defect | Amit Shete | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12915 | QA- Safety Console >> Allow/Block URL. Weird wildcards are not showing ! mark | FILTER-12912 | Defect | Amit Shete | Closed without action |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12976 | QA- Safety Console >> Activities. More more info Popup does not have Search, Site, Public IP, Block and Allow buttons translated | FILTER-12973 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-03-30 |  | 2026-04-06 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13102 | QA- (Not in Pkg 41) Support Tool >> Custom list UI. Not able to create Custom list | FILTER-13099 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-02 |  | 2026-04-07 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13108 | QA- Looking for solution for HTML Editor vulnerabilities | FILTER-13105 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-04-02 |  | 2026-04-16 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13132 | QA- CA & UK DNS filtering not working as expected. | FILTER-13129 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-04-02 |  | 2026-04-06 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13321 | QA- Security issues with SSO access token and JWT created for GO broker - Part 1 | FILTER-13318 | Task | Amit Shete | Closed without action |  | P3 | 2026-04-08 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13329 | QA- Users receiving {"success":0,"message":"Internal Server Error"} when trying to use Google search and browse sites. | FILTER-13326 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-04-08 |  | 2026-04-12 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13363 | QA- Investigate and fix 'identifier at index 0 is empty' errors in tokenization-service | FILTER-13360 | Escape Defect | Amit Shete | Closed without action |  | P0 | 2026-04-08 |  | 2026-04-12 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13376 | QA- Safety Console >> Policy Editor. Delete policy popup has translation key instead of message. | FILTER-13373 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13384 | QA- Safety Console >> Policy Map >> Custom Group. Delete CG popup has translation key instead of message. | FILTER-13381 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13418 | QA- MT User >> Filter >> Policy Editor. After making any changes to any policy, MT user is taken to Global policy. | FILTER-13415 | Defect | Amit Shete | Closed without action |  | P2 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13422 | QA- MT User >> Filter >> Policy Editor. MT not able to Create or Clone policies | FILTER-13419 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13426 | QA- MT User >> Filter >> Users. Clicking on Users redirects MT user to Policy Editor by auto reload | FILTER-13423 | Defect | Amit Shete | Closed without action |  | P2 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13437 | QA- Safety Console >> Filter. Extension. Dual Provision Kid with SG policy higher than OU/SSU, does not generate cases | FILTER-13434 | Escape Defect | Amit Shete | Closed without action |  | P0 | 2026-04-10 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13453 | QA- Support Tool. Even if the user selects another FID from the FID Detail page's FID name dropdown, the new FID details are not updated on the Detail Page. | FILTER-13450 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-04-11 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13473 | QA- Safety Console >> Filter. Custom Groups page is blank for Dual Provision FID. | FILTER-13470 | Escape Defect | Amit Shete | Closed without action |  | P0 | 2026-04-11 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13497 | QA- Custom groups are not displayed | FILTER-13494 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-04-12 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12450 | QA- Site not loading correctly with extension | FILTER-12447 | Escape Defect | Amol Mithari | Done |  | P3 | 2026-03-12 |  | 2026-04-26 | sprint-Gonzalo | 2 | 2 | FILTER
Automation | FILTER-12851 | QA- [Edge] - Bing allow p o r n search | FILTER-12848 | Defect | Amol Mithari | Done |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 2 | 2 | FILTER
Automation | FILTER-13012 | QA- CLONE - [Edge-TS] - Blocked Google search triggers an infinite window.alert popup loop, locking the entire browser | FILTER-13009 | Defect | Amol Mithari | Closed without action |  | P0 | 2026-03-30 |  | 2026-04-06 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-13034 | QA- Automate performance testing for tokenization cron job | FILTER-13031 | Task | Amol Mithari | Done |  | P3 | 2026-03-31 |  | 2026-04-14 | sprint-Gonzalo | 10 | 5 | FILTER
Automation | FILTER-13042 | QA- Win Ext : TS, Repeated searches on bing.com is not brokering | FILTER-13039 | Defect | Amol Mithari | Done |  | P2 | 2026-03-31 |  | 2026-04-14 | sprint-Gonzalo | 2 | 2 | FILTER
Dev | FILTER-11381 | Fix CRXTN Logging Failure: Incomplete YouTube URL Captured from Embedded Video Clicks | FILTER-11181 | Escape Defect | Arun Thakur | Done |  | P2 | 2025-12-09 |  | 2026-04-17 | sprint-Gonzalo | 6 | 4 | FILTER
Dev | FILTER-11846 | GIF on Mouse Hover Becomes Visible and Clickable When Blur is Applied | FILTER-11033 | Defect | Arun Thakur | Closed without action |  | P2 | 2026-01-29 |  | 2026-04-06 | sprint-Gonzalo | 10 | 8 | FILTER
Dev | FILTER-12157 | DEV - JS (All Extensions) Images which behave as "show more" links are not blurred | FILTER-12156 | Defect | Arun Thakur | Done |  | P3 | 2026-02-24 |  | 2026-04-06 | sprint-Gonzalo | 8 | 8 | FILTER
Dev | FILTER-12229 | DEV - JS (All Extensions): Youtube.YT logo on YT page, YT search page, YT video page and YT shorts is not clickable | FILTER-12228 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-02-25 |  | 2026-04-15 | sprint-Gonzalo | 0 | 0 | FILTER
Dev | FILTER-12266 | DEV - JS (All Extensions): Securly Filter Dashboard YT videos thumbnails are blurred | FILTER-12265 | Defect | Arun Thakur | Closed without action |  | P2 | 2026-02-26 |  | 2026-04-06 | sprint-Gonzalo | 0 | 0 | FILTER
Dev | FILTER-12270 | DEV - CLONE - JS (Windows+ Edge) Extensions. Securly Filter Dashboard YT videos thumbnails are blurred | FILTER-12265 | Defect | Arun Thakur | Done |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Gonzalo | 4 | 4 | FILTER
Dev | FILTER-12273 | DEV - CLONE - JS (Windows+ Edge) Extensions. SFW images are also getting blurred by the model | FILTER-12272 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Gonzalo | 0 | 0 | FILTER
Dev | FILTER-12276 | DEV - CLONE - JS (Windows+ Edge) Extensions. Image Blur. Amazon.com is accessible but links/logo/dropdowns not clickable | FILTER-12272 | Defect | Arun Thakur | Done |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Gonzalo | 6 | 6 | FILTER
Dev | FILTER-12285 | DEV - JS (All Extensions) image blur on GDrive. blurred images can be accessed by accessing unblurred images | FILTER-12284 | Defect | Arun Thakur | Done |  | P1 | 2026-02-26 |  | 2026-04-08 | sprint-Gonzalo | 10 | 10 | FILTER
Dev | FILTER-12533 | DEV - JS (All Extensions) Image Blur. Images created by AI are not getting blurred on AI screen but if the links are accessed they are getting blurred in other tab | FILTER-12275 | Defect | Arun Thakur | Done |  | P1 | 2026-03-17 |  | 2026-04-08 | sprint-Gonzalo | 10 | 10 | FILTER
Dev | FILTER-13416 | DEV - MT User >> Filter >> Policy Editor. After making any changes to any policy, MT user is taken to Global policy. | FILTER-13415 | Defect | Arun Thakur | Done |  | P2 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 2 | 2 | FILTER
Dev | FILTER-13420 | DEV - MT User >> Filter >> Policy Editor. MT not able to Create or Clone policies | FILTER-13419 | Defect | Arun Thakur | Done |  | P1 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 2 | 2 | FILTER
Dev | FILTER-13424 | DEV - MT User >> Filter >> Users. Clicking on Users redirects MT user to Policy Editor by auto reload | FILTER-13423 | Defect | Arun Thakur | Done |  | P2 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 6 | 6 | FILTER
Dev | FILTER-13451 | DEV - Support Tool. Even if the user selects another FID from the FID Detail page's FID name dropdown, the new FID details are not updated on the Detail Page. | FILTER-13450 | Escape Defect | Arun Thakur | Done |  | P1 | 2026-04-11 |  | 2026-04-13 | sprint-Gonzalo | 5 | 4 | FILTER
Dev | FILTER-12686 | DEV - [Edge] Overlay gets stuck in an infinite loading loop on YouTube thumbnails | FILTER-12685 | Defect | Ashish Modak | Closed without action |  | P1 | 2026-03-25 |  | 2026-04-06 | sprint-Gonzalo | 0 | 1 | FILTER
Dev | FILTER-12849 | DEV - [Edge] - Bing allow p o r n search | FILTER-12848 | Defect | Ashish Modak | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 2 | 8 | FILTER
Dev | FILTER-12564 | DEV - [sprox] Keyword scanning is not working for all search engines except google.com | FILTER-12563 | Defect | Ashish Temurnikar | Done |  | P1 | 2026-03-18 |  | 2026-04-06 | sprint-Gonzalo | 16 | 16 | FILTER
QA | FILTER-11383 | Manual QA Validation for Incomplete YouTube URL Logging from Embedded Clicks | FILTER-11181 | Escape Defect | Ayesha Kamde | Done |  | P2 | 2025-12-09 |  | 2026-04-24 | sprint-Gonzalo | 6 | 6 | FILTER
QA | FILTER-11847 | Verify Fix for GIF Hover Visibility and Clickability Issue on Blurred Content | FILTER-11033 | Defect | Ayesha Kamde | Done |  | P2 | 2026-01-29 |  | 2026-04-08 | sprint-Gonzalo | 2 | 2 | FILTER
QA | FILTER-11897 | Vector Expansion - Verify if http://kiddle/co/ is added to search scanning | FILTER-11895 | Story | Ayesha Kamde | Done |  | P2 | 2026-01-29 |  | 2026-04-06 | sprint-Gonzalo | 5 | 6 | FILTER
QA | FILTER-12158 | QA- JS (All Extensions) Images which behave as "show more" links are not blurred | FILTER-12156 | Defect | Ayesha Kamde | Closed without action |  | P3 | 2026-02-24 |  | 2026-04-08 | sprint-Gonzalo | 1 | 2 | FILTER
QA | FILTER-12230 | QA- JS (All Extensions): Youtube.YT logo on YT page, YT search page, YT video page and YT shorts is not clickable | FILTER-12228 | Defect | Ayesha Kamde | Done |  | P1 | 2026-02-25 |  | 2026-04-20 | sprint-Gonzalo | 1.5 | 2 | FILTER
QA | FILTER-12267 | QA- JS (All Extensions): Securly Filter Dashboard YT videos thumbnails are blurred | FILTER-12265 | Defect | Ayesha Kamde | Done |  | P2 | 2026-02-26 |  | 2026-04-06 | sprint-Gonzalo | 2 | 2 | FILTER
QA | FILTER-12274 | JS (All Extensions) Image Blur. Amazon.com is accessible but links/logo/dropdowns not clickable | FILTER-12272 | Defect | Ayesha Kamde | Done |  | P1 | 2026-02-26 |  | 2026-04-06 | sprint-Gonzalo | 2 | 2 | FILTER
QA | FILTER-12277 | QA- JS (All Extensions) Image Blur. Images created by AI are not getting blurred on AI screen but if the links are accessed they are getting blurred in other tab | FILTER-12275 | Defect | Ayesha Kamde | Done |  | P1 | 2026-02-26 |  | 2026-04-08 | sprint-Gonzalo | 2 | 2 | FILTER
QA | FILTER-12286 | QA- JS (All Extensions) image blur on GDrive. blurred images can be accessed by accessing unblurred images | FILTER-12284 | Defect | Ayesha Kamde | Done |  | P1 | 2026-02-26 |  | 2026-04-21 | sprint-Gonzalo | 1 | 2 | FILTER
QA | FILTER-12288 | Verify all Image Blur test cases for JS | FILTER-11974 | Story | Ayesha Kamde | Done |  | P3 | 2026-02-27 |  | 2026-03-03 | sprint-Gonzalo | 25 | 5 | FILTER
QA | FILTER-13107 | QA- Looking for solution for HTML Editor vulnerabilities | FILTER-13105 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2026-04-02 |  | 2026-04-23 | sprint-Gonzalo | 9 | 12 | FILTER
Dev | FILTER-12242 | Do the required changes in order to achieve the Story's ask | FILTER-12241 | Story | Harsh Verma | Done |  | P3 | 2026-02-26 |  | 2026-04-16 | sprint-Gonzalo | 36 | 32 | FILTER
Story | FILTER-12293 | [Filter] Translations for Spanish & French - Json Creation & Verify | FILTER-12099 | Epic | Harshada Kude | RELEASED TO PROD |  | P3 | 2026-02-27 |  | 2026-04-27 | sprint-Gonzalo | 24 | 0 | FILTER | unplanned-sprint
Dev | FILTER-12294 | Translations for Spanish & French - Json Creation & Verify | FILTER-12293 | Story | Harshada Kude | Done |  | P3 | 2026-02-27 |  | 2026-04-06 | sprint-Gonzalo | 18 | 16 | FILTER
Story | FILTER-12305 | [Filter] Consumption of json Translations in Settings | FILTER-12099 | Epic | Harshada Kude | RELEASED TO PROD |  | P3 | 2026-03-02 |  | 2026-04-27 | sprint-Gonzalo | 10.5 | 0 | FILTER
Dev | FILTER-12306 | [Filter] Creation & Consumption of json Translations in Settings | FILTER-12305 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Gonzalo | 10 | 8 | FILTER
Dev | FILTER-12308 | [Filter] Creation & Consumption of json Translations in Remaining portion of Policy Map | FILTER-12307 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Gonzalo | 12 | 10 | FILTER
Dev | FILTER-12310 | [Filter] Cross check Filter Application Other Remaining instances of ¦ translate or instant - Part 2 | FILTER-12311 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Gonzalo | 12 | 10 | FILTER
Story | FILTER-12311 | [Filter] Cross check Filter Application Other Remaining instances of ¦ translate or instant | FILTER-12099 | Epic | Harshada Kude | RELEASED TO PROD |  | P3 | 2026-03-02 |  | 2026-04-27 | sprint-Gonzalo | 18.5 | 0 | FILTER
Dev | FILTER-12312 | [Filter] Cross check Filter Application Other Remaining instances of ¦ translate or instant | FILTER-12311 | Story | Harshada Kude | Done |  | P3 | 2026-03-02 |  | 2026-04-06 | sprint-Gonzalo | 6 | 6 | FILTER
Story | FILTER-12474 | [Filter] Accessibility Fix - 3.1.2 | FILTER-12099 | Epic | Harshada Kude | RELEASED TO PROD |  | P3 | 2026-03-13 |  | 2026-04-27 | sprint-Gonzalo | 0 | 0 | FILTER | unplanned-sprint
Dev | FILTER-12658 | DEV - Policy Map does not display OU names when searching or filtering | FILTER-12657 | Escape Defect | Harshada Kude | Done |  | P0 | 2026-03-24 |  | 2026-04-10 | sprint-Gonzalo | 6 | 6 | FILTER
Dev | FILTER-12781 | DEV - Safety Console. Image blur. Confirmation popup does not have text in it and is not functional | FILTER-12780 | Defect | Harshada Kude | Done |  | P3 | 2026-03-27 |  | 2026-04-07 | sprint-Gonzalo | 2 | 2 | FILTER
Dev | FILTER-12789 | DEV - Safety Console. Allow/Block Search terms. Even terms added as contains are getting added as Exact | FILTER-12788 | Defect | Harshada Kude | Done |  | P1 | 2026-03-27 |  | 2026-04-07 | sprint-Gonzalo | 3.5 | 2 | FILTER
Dev | FILTER-12913 | DEV - Safety Console >> Allow/Block URL. Weird wildcards are not showing ! mark | FILTER-12912 | Defect | Harshada Kude | Closed without action |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Dev | FILTER-12974 | DEV - Safety Console >> Activities. More more info Popup does not have Search, Site, Public IP, Block and Allow buttons translated | FILTER-12973 | Escape Defect | Harshada Kude | Done |  | P2 | 2026-03-30 |  | 2026-04-07 | sprint-Gonzalo | 1 | 1 | FILTER
Dev | FILTER-13374 | DEV - Safety Console >> Policy Editor. Delete policy popup has translation key instead of message. | FILTER-13373 | Defect | Harshada Kude | Done |  | P1 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 1 | 1 | FILTER
Dev | FILTER-13382 | DEV - Safety Console >> Policy Map >> Custom Group. Delete CG popup has translation key instead of message. | FILTER-13381 | Defect | Harshada Kude | Done |  | P1 | 2026-04-09 |  | 2026-04-14 | sprint-Gonzalo | 1 | 1 | FILTER
Dev | FILTER-13471 | DEV - Safety Console >> Filter. Custom Groups page is blank for Dual Provision FID. | FILTER-13470 | Escape Defect | Harshada Kude | Done |  | P0 | 2026-04-11 |  | 2026-04-13 | sprint-Gonzalo | 4 | 4 | FILTER
Dev | FILTER-13495 | DEV - Custom groups are not displayed | FILTER-13494 | Escape Defect | Harshada Kude | Done |  | P2 | 2026-04-12 |  | 2026-04-13 | sprint-Gonzalo | 0 | 0.5 | FILTER
Dev | FILTER-11659 | Phase 3 - Implement FluentD Changes for Tokenization (UserToken) | FILTER-11631 | Story | Prateek Fotedar | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Gonzalo | 12 | 12 | FILTER | Capitalized-Feature
Dev | FILTER-12301 | POST /api/custom-list allows Admin to create custom list with usage "GLOBAL" - should be rejected | FILTER-11776 | Defect | Prateek Fotedar | Closed without action |  | P3 | 2026-03-01 |  | 2026-04-24 | sprint-Gonzalo | 0.5 | 6 | FILTER | Capitalized-Feature
Dev | FILTER-12865 | DEV - Support Tool >> Custom list UI. Custom List table >> "Last updated by" field is not showing value for every list | FILTER-12864 | Defect | Prateek Fotedar | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 1 | 1 | FILTER
Dev | FILTER-12869 | DEV - Support Tool >> Custom list UI. Custom List table >> we are able to see global lists which are created by non support tool users as well | FILTER-12868 | Defect | Prateek Fotedar | Closed without action |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 1.5 | 1.5 | FILTER
Dev | FILTER-12893 | DEV - Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for more than 255 character length | FILTER-12892 | Defect | Prateek Fotedar | Done |  | P2 | 2026-03-27 |  | 2026-04-17 | sprint-Gonzalo | 2 | 2 | FILTER
Dev | FILTER-12901 | DEV - Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for duplicate Custom list name | FILTER-12900 | Defect | Prateek Fotedar | Done |  | P2 | 2026-03-27 |  | 2026-04-17 | sprint-Gonzalo | 2 | 2 | FILTER
Dev | FILTER-13032 | DEV - Automate performance testing for tokenization cron job | FILTER-13031 | Task | Prateek Fotedar | Closed without action |  | P3 | 2026-03-31 |  | 2026-04-21 | sprint-Gonzalo | 1 | 1 | FILTER
Dev | FILTER-13100 | DEV - (Not in Pkg 41) Support Tool >> Custom list UI. Not able to create Custom list | FILTER-13099 | Defect | Prateek Fotedar | Done |  | P1 | 2026-04-02 |  | 2026-04-06 | sprint-Gonzalo | 2 | 2 | FILTER
Dev | FILTER-13277 | CA & UK DNS filtering not working as expected - Tokenization code change | FILTER-13129 | Escape Defect | Prateek Fotedar | Done |  | P1 | 2026-04-06 |  | 2026-04-06 | sprint-Gonzalo | 3 | 3 | FILTER
Dev | FILTER-13327 | DEV - Users receiving {"success":0,"message":"Internal Server Error"} when trying to use Google search and browse sites. | FILTER-13326 | Escape Defect | Prateek Fotedar | Done |  | P2 | 2026-04-08 |  | 2026-04-08 | sprint-Gonzalo | 1.5 | 1.5 | FILTER
Dev | FILTER-13361 | DEV - Investigate and fix 'identifier at index 0 is empty' errors in tokenization-service | FILTER-13360 | Escape Defect | Prateek Fotedar | Done |  | P0 | 2026-04-08 |  | 2026-04-09 | sprint-Gonzalo | 3 | 3 | FILTER
Dev | FILTER-11896 | Vector Expansion - Add http://kiddle.co/ to search scanning | FILTER-11895 | Story | Pratik Tiwari | Done |  | P2 | 2026-01-29 |  | 2026-04-06 | sprint-Gonzalo | 10 | 10 | FILTER
Dev | FILTER-12165 | Block W3Schools (and similar) HTML sandbox bypass via CDN/third-party iframe loading (e.g. jsdelivr, Vercel, W3Spaces) | FILTER-12093 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-02-24 |  | 2026-04-06 | sprint-Gonzalo | 16 | 13 | FILTER
Dev | FILTER-12540 | DEV -Extension Bypass - Opening new tab | FILTER-12476 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-03-17 |  | 2026-04-28 | sprint-Gonzalo | 12 | 12 | FILTER
Dev | FILTER-12821 | DEV - Windows Extn : TS - Safe search is not getting applied immediately on google search engine(Ensure that api response shows SS enabled) | FILTER-12820 | Defect | Pratik Tiwari | Code Review |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 0 | 6 | FILTER
Dev | FILTER-13010 | DEV - CLONE - [Edge-TS] - Blocked Google search triggers an infinite window.alert popup loop, locking the entire browser | FILTER-13009 | Defect | Pratik Tiwari | Closed without action |  | P0 | 2026-03-30 |  | 2026-04-06 | sprint-Gonzalo | 0 | 0 | FILTER
Dev | FILTER-13106 | DEV - Looking for solution for HTML Editor vulnerabilities | FILTER-13105 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-04-02 |  | 2026-04-24 | sprint-Gonzalo | 12 | 12 | FILTER
Story | FILTER-12333 | [sprox] RTQA5 testing for DNS & SPAC | FILTER-8230 | Epic | Ravi Raj | Closed without action |  | P3 | 2026-03-02 |  | 2026-04-14 | sprint-Gonzalo | 16 | 0 | FILTER
Dev | FILTER-12336 | [sprox] RTQA5 testing for DNS & SPAC | FILTER-12333 | Story | Ravi Raj | Closed without action |  | P3 | 2026-03-03 |  | 2026-04-14 | sprint-Gonzalo | 16 | 16 | FILTER
Debug | FILTER-13013 | [sprox] Cookie & broker performance check for top proxy sites | FILTER-8230 | Epic | Ravi Raj | Resolved |  | P2 | 2026-03-30 |  | 2026-04-14 | sprint-Gonzalo | 16 | 16 | FILTER
Debug | FILTER-13014 | [sprox] Verify securly cookie delete code from C++/Rust integration point | FILTER-8230 | Epic | Ravi Raj | Resolved |  | P3 | 2026-03-30 |  | 2026-04-13 | sprint-Gonzalo | 12 | 12 | FILTER
Debug | FILTER-13015 | [sprox] Handle captcha logic migration to sprox | FILTER-8230 | Epic | Ravi Raj | Resolved | Done | P2 | 2026-03-30 | 2026-04-09 | 2026-04-13 | sprint-Gonzalo | 19 | 16 | FILTER
Debug | FILTER-13016 | [sprox] doRequestTransform & dumpRequest function migration to sprox | FILTER-8230 | Epic | Ravi Raj | Closed | Fixed | P2 | 2026-03-30 | 2026-04-02 | 2026-04-21 | sprint-Gonzalo | 12 | 10 | FILTER
Dev | FILTER-12324 | DEV - BugCrowd-850af9c1-f86b-4c74-91ac-94ea808c8e9b-Deleted User to Continue Performing Privileged Actions (Account Deletion Bypass) | FILTER-12323 | Defect | Sagar Satpute | Done |  | P3 | 2026-03-02 |  | 2026-04-15 | sprint-Gonzalo | 13 | 13 | FILTER
Dev | FILTER-12344 | DEV - Take-home policy settings randomly reset to all allowed/least restrictive on or around 24th Feb 2026 | FILTER-12343 | Escape Defect | Sagar Satpute | Closed without action |  | P3 | 2026-03-03 |  | 2026-04-22 | sprint-Gonzalo | 0 | 5 | FILTER
Dev | FILTER-12406 | DEV - Duplicate policies appearing in Policy editor. | FILTER-12405 | Escape Defect | Sagar Satpute | Closed without action |  | P3 | 2026-03-10 |  | 2026-04-06 | sprint-Gonzalo | 0 | 0 | FILTER
Dev | FILTER-12534 | DEV - Build IP lookup tool to make queries across all clusters. | FILTER-12396 | Task | Sagar Satpute | Done |  | P1 | 2026-03-17 |  | 2026-04-06 | sprint-Gonzalo | 8 | 8 | FILTER
Dev | FILTER-13130 | DEV - CA & UK DNS filtering not working as expected. | FILTER-13129 | Escape Defect | Sagar Satpute | Closed without action |  | P1 | 2026-04-02 |  | 2026-04-06 | sprint-Gonzalo | 6 | 8 | FILTER
Dev | FILTER-13291 | DEV - P1 Escalation-Searches and Sites not generating Cases ¦ Comal ISD | FILTER-13286 | Escape Defect | Sagar Satpute | Done |  | P0 | 2026-04-07 |  | 2026-04-10 | sprint-Gonzalo | 8 | 6 | FILTER
Dev | FILTER-13435 | DEV - Safety Console >> Filter. Extension. Dual Provision Kid with SG policy higher than OU/SSU, does not generate cases | FILTER-13434 | Escape Defect | Sagar Satpute | Done |  | P0 | 2026-04-10 |  | 2026-04-10 | sprint-Gonzalo | 6 | 6 | FILTER
Dev | FILTER-13783 | DEV - Use common sso package - www-support-tool | FILTER-13782 | Story | Sagar Satpute | Done |  | P3 | 2026-03-29 |  | 2026-04-27 | sprint-Gonzalo | 10 | 16 | FILTER
Dev | FILTER-13786 | DEV - Use common sso package - www-filter | FILTER-13785 | Story | Sagar Satpute | Done |  | P3 | 2026-03-29 |  | 2026-04-27 | sprint-Gonzalo | 8 | 16 | FILTER
Dev | PTGM-664 | Fix linter errors in www-support-tool repo | PTGM-666 | Story | Sagar Satpute | Done |  | P2 | 2026-01-05 |  | 2026-04-14 | sprint-Gonzalo | 18 | 21 | PTGM
Dev | FILTER-12897 | DEV - Support Tool >> Custom list UI. Create custom list Resource and Update custom list Resource, drawer should validated for comment length on Save of that drawer | FILTER-12896 | Defect | Shailendra Singh | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-20 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-11661 | Manual Testing Tokenization service for Extension | FILTER-11631 | Story | Surabhi Choudhary | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Gonzalo | 24 | 24 | FILTER | Capitalized-Feature
QA | FILTER-11666 | Test Complete URL Path in Categorized Queue from Crextn | FILTER-11637 | Task | Surabhi Choudhary | Done |  | P2 | 2026-01-15 |  | 2026-04-09 | sprint-Gonzalo | 3 | 3 | FILTER
Task | FILTER-12200 | SPROX Manual Testing | FILTER-8230 | Epic | Surabhi Choudhary | QA Verified |  | P2 | 2026-02-25 |  | 2026-04-25 | sprint-Gonzalo | 24 | 0 | FILTER
QA | FILTER-12659 | QA- Policy Map does not display OU names when searching or filtering | FILTER-12657 | Escape Defect | Surabhi Choudhary | Done |  | P0 | 2026-03-24 |  | 2026-04-10 | sprint-Gonzalo | 1 | 1 | FILTER
QA | FILTER-13078 | SPROX Manual Testing Phase 1 | FILTER-12200 | Task | Surabhi Choudhary | Done |  | P2 | 2026-04-01 |  | 2026-04-25 | sprint-Gonzalo | 24 | 24 | FILTER
QA | FILTER-13079 | Manual Testing Tokenization service for GO Extension | FILTER-11631 | Story | Surabhi Choudhary | Done |  | P2 | 2026-04-01 |  | 2026-04-14 | sprint-Gonzalo | 24 | 24 | FILTER | Capitalized-Feature
QA | FILTER-13131 | QA- CA & UK DNS filtering not working as expected. | FILTER-13129 | Escape Defect | Surabhi Choudhary | Done |  | P1 | 2026-04-02 |  | 2026-04-07 | sprint-Gonzalo | 5 | 5 | FILTER
QA | FILTER-13328 | QA- Users receiving {"success":0,"message":"Internal Server Error"} when trying to use Google search and browse sites. | FILTER-13326 | Escape Defect | Surabhi Choudhary | Done |  | P2 | 2026-04-08 |  | 2026-04-08 | sprint-Gonzalo | 2 | 2 | FILTER
QA | FILTER-13362 | QA- Investigate and fix 'identifier at index 0 is empty' errors in tokenization-service | FILTER-13360 | Escape Defect | Surabhi Choudhary | Done |  | P0 | 2026-04-08 |  | 2026-04-09 | sprint-Gonzalo | 3 | 2 | FILTER
QA | FILTER-13433 | QA - P1 Escalation-Searches and Sites not generating Cases ¦ Comal ISD for pkg 41 | FILTER-13286 | Escape Defect | Surabhi Choudhary | Done |  | P0 | 2026-04-10 |  | 2026-04-14 | sprint-Gonzalo | 5 | 5 | FILTER
Story | FILTER-12467 | Filter Accessibility - 4.1.2 (Name, role and value) |  |  | Swaroop Chavhan | RELEASED TO PROD |  | P3 | 2026-03-13 |  | 2026-04-27 | sprint-Gonzalo | 48 | 0 | FILTER
Dev | FILTER-12468 | Fixing simple input with chips. | FILTER-12467 | Story | Swaroop Chavhan | Done |  | P3 | 2026-03-13 |  | 2026-04-06 | sprint-Gonzalo | 12 | 16 | FILTER
Dev | FILTER-12469 | Fixing search with chips | FILTER-12467 | Story | Swaroop Chavhan | Done |  | P3 | 2026-03-13 |  | 2026-04-06 | sprint-Gonzalo | 12 | 16 | FILTER
Dev | FILTER-12470 | Fixing search with autocomplete with chips | FILTER-12467 | Story | Swaroop Chavhan | Done |  | P3 | 2026-03-13 |  | 2026-04-06 | sprint-Gonzalo | 12 | 16 | FILTER
Dev | FILTER-12471 | Fixing dropdown with chips (search inside) | FILTER-12467 | Story | Swaroop Chavhan | Done |  | P3 | 2026-03-13 |  | 2026-04-06 | sprint-Gonzalo | 12 | 16 | FILTER
Story | FILTER-12472 | Filter Accessibility - other variations of 4.1.2, 1.4.13 |  |  | Swaroop Chavhan | RELEASED TO PROD |  | P3 | 2026-03-13 |  | 2026-04-27 | sprint-Gonzalo | 24 | 0 | FILTER
Dev | FILTER-12561 | Find and fix pending minor accessibility issues in Filter | FILTER-12472 | Story | Swaroop Chavhan | Done |  | P3 | 2026-03-18 |  | 2026-04-06 | sprint-Gonzalo | 24 | 24 | FILTER
Dev | FILTER-11665 | [PageScan] Send Complete URL Path in Categorized Queue from Crextn | FILTER-11637 | Task | Vaibhav Kumbhar | Done |  | P2 | 2026-01-15 |  | 2026-04-06 | sprint-Gonzalo | 15 | 12 | FILTER
Dev | FILTER-12177 | Investigate and close about:blank loophole used to bypass filtering and access competitor content | FILTER-12119 | Escape Defect | Vaibhav Kumbhar | Code Review |  | P1 | 2026-02-25 |  | 2026-04-24 | sprint-Gonzalo | 20 | 13 | FILTER
Dev | FILTER-12448 | DEV - Site not loading correctly with extension | FILTER-12447 | Escape Defect | Vaibhav Kumbhar | Code Review |  | P3 | 2026-03-12 |  | 2026-04-14 | sprint-Gonzalo | 11 | 20 | FILTER
Dev | FILTER-12536 | Dev Task to Add authentication for proxy apis | FILTER-11637 | Task | Vaibhav Kumbhar | Done |  | P2 | 2026-03-17 |  | 2026-04-06 | sprint-Gonzalo | 20 | 16 | FILTER
Dev | FILTER-13081 | DEV - Generate context for filter | FILTER-13080 | Task | Vaibhav Kumbhar | Code Review |  | P3 | 2026-04-01 |  | 2026-04-27 | sprint-Gonzalo | 9 | 14 | FILTER
Task | PTGM-686 | [Support tool] Update context with traceid, sessionid |  |  | Vaibhav Kumbhar | Closed | Done | P3 | 2026-03-30 | 2026-04-27 | 2026-04-28 | sprint-Gonzalo | 6 | 4 | PTGM
Task | PTGM-687 | [www-filter] Update context with traceid and sessionid |  |  | Vaibhav Kumbhar | Resolved | Done | P3 | 2026-03-30 | 2026-04-13 | 2026-04-17 | sprint-Gonzalo | 0 | 6 | PTGM

## Not Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Debug | FILTER-13047 | Need to work on Secrets identified on Filter/Aware repo |  |  | Harsh Verma | Open |  | P3 | 2026-03-31 |  | 2026-04-27 | sprint-Gonzalo | 0 | 16 | FILTER | unplanned-sprint |  | YES
QA | FILTER-12345 | QA- Take-home policy settings randomly reset to all allowed/least restrictive on or around 24th Feb 2026 | FILTER-12343 | Escape Defect | Altamash Heroli | Open |  | P3 | 2026-03-03 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-12621 | QA- Policy Map Import not showing policy names ¦ San Ramon | FILTER-12619 | Escape Defect | Altamash Heroli | Open |  | P1 | 2026-03-23 |  | 2026-04-26 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-13784 | QA- Use common sso package - www-support-tool | FILTER-13782 | Story | Altamash Heroli | Ready for QA |  | P3 | 2026-03-29 |  | 2026-04-27 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-13787 | QA- Use common sso package - www-filter | FILTER-13785 | Story | Altamash Heroli | Ready for QA |  | P3 | 2026-03-29 |  | 2026-04-27 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-11844 | Verify fix for SafetyConsole CustomList API - Token invalidation on re-authentication | FILTER-11687 | Defect | Amit Shete | Open |  | P2 | 2026-01-29 |  | 2026-04-27 | sprint-Gonzalo | 0 | 2 | FILTER
QA | FILTER-11873 | Verify CustomList API returns 401 when Filter Product is disabled | FILTER-11688 | Escape Defect | Amit Shete | Ready for QA |  | P3 | 2026-01-29 |  | 2026-04-27 | sprint-Gonzalo | 0 | 2 | FILTER
Automation | FILTER-12179 | Scripting for about:blank loophole fix – policy and redirect behavior | FILTER-12119 | Escape Defect | Amit Shete | Open |  | P1 | 2026-02-25 |  | 2026-04-14 | sprint-Gonzalo | 0 | 4 | FILTER
Automation | FILTER-12494 | QA- In prod: Yes, (PHP) – Default Securly logo not visible on blocked page when no custom logo is configured via support tool or general settings | FILTER-12491 | Escape Defect | Amit Shete | Open |  | P2 | 2026-03-16 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12622 | QA- Policy Map Import not showing policy names ¦ San Ramon | FILTER-12619 | Escape Defect | Amit Shete | Scripting in progress |  | P1 | 2026-03-23 |  | 2026-04-26 | sprint-Gonzalo | 0 | 3 | FILTER
Automation | FILTER-12823 | QA- Windows Extn : TS - Safe search is not getting applied immediately on google search engine(Ensure that api response shows SS enabled) | FILTER-12820 | Defect | Amit Shete | Open |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Automation | FILTER-12526 | Automation Task for Chrome Browser | FILTER-12207 | Task | Amol Mithari | Scripting in progress |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Gonzalo | 31 | 40 | FILTER
Automation | FILTER-12542 | Automation -Extension Bypass - Opening new tab | FILTER-12476 | Escape Defect | Amol Mithari | Open |  | P1 | 2026-03-17 |  | 2026-04-14 | sprint-Gonzalo | 0 | 2 | FILTER
Automation | FILTER-12984 | QA- Win extn : TS, Internal IP is not getting logged on the UI | FILTER-12981 | Defect | Amol Mithari | Open |  | P3 | 2026-03-30 |  | 2026-04-14 | sprint-Gonzalo | 0 | 3 | FILTER
Dev | FILTER-12620 | DEV - Policy Map Import not showing policy names ¦ San Ramon | FILTER-12619 | Escape Defect | Arun Thakur | Open |  | P1 | 2026-03-23 |  | 2026-04-26 | sprint-Gonzalo | 0 | 0 | FILTER
Dev | FILTER-13826 | Dev Task for Beta flag | FILTER-12119 | Escape Defect | Arun Thakur | Open |  | P1 | 2026-04-28 |  | 2026-04-28 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-12105 | QA- JS/TS (Chromebook) Extension – Blocked Website Loads on First Browser Launch When Opened via Bookmark (Iframe Not Blocked) | FILTER-12103 | Escape Defect | Ayesha Kamde | Open |  | P3 | 2026-02-19 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-12178 | Verify about:blank loophole fix – block/redirect unless opened from allowed site | FILTER-12119 | Escape Defect | Ayesha Kamde | Open |  | P1 | 2026-02-25 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-12449 | QA- Site not loading correctly with extension | FILTER-12447 | Escape Defect | Ayesha Kamde | Open |  | P3 | 2026-03-12 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
QA | FILTER-12493 | QA- In prod: Yes, (PHP) – Default Securly logo not visible on blocked page when no custom logo is configured via support tool or general settings | FILTER-12491 | Escape Defect | Ayesha Kamde | Open |  | P2 | 2026-03-16 |  | 2026-04-14 | sprint-Gonzalo | 0 | 2 | FILTER
QA | FILTER-12541 | QA -Extension Bypass - Opening new tab - Fix Test | FILTER-12476 | Escape Defect | Ayesha Kamde | Ready for QA |  | P1 | 2026-03-17 |  | 2026-04-28 | sprint-Gonzalo | 0 | 5 | FILTER
Task | FILTER-10604 | Placeholder task to track the efforts used for Vanta tool task completion |  |  | Harsh Verma | In Progress |  | P3 | 2025-11-03 |  | 2026-04-27 | sprint-Gonzalo | 0 | 8 | FILTER | unplanned-sprint
Task | FILTER-11697 | Extension of FILTER-11605 |  |  | Harsh Verma | In Progress |  | P3 | 2026-01-19 |  | 2026-04-27 | sprint-Gonzalo | 0 | 24 | FILTER | unplanned-sprint
Dev | FILTER-11843 | SafetyConsole CustomList API - Old access tokens remain valid after new token generation | FILTER-11687 | Defect | Prateek Fotedar | Reopened |  | P2 | 2026-01-29 |  | 2026-04-28 | sprint-Gonzalo | 12 | 12 | FILTER
Dev | FILTER-11872 | SafetyConsole CustomList API - Token should be invalidated when Filter Product is disabled | FILTER-11688 | Escape Defect | Prateek Fotedar | Reopened |  | P3 | 2026-01-29 |  | 2026-04-28 | sprint-Gonzalo | 1 | 8 | FILTER
Dev | FILTER-12492 | DEV - In prod: Yes, (PHP) – Default Securly logo not visible on blocked page when no custom logo is configured via support tool or general settings | FILTER-12491 | Escape Defect | Prateek Fotedar | Open |  | P2 | 2026-03-16 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Dev | FILTER-12104 | DEV - JS/TS (Chromebook) Extension – Blocked Website Loads on First Browser Launch When Opened via Bookmark (Iframe Not Blocked) | FILTER-12103 | Escape Defect | Pratik Tiwari | Open |  | P3 | 2026-02-19 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Dev | FILTER-12982 | DEV - Win extn : TS, Internal IP is not getting logged on the UI | FILTER-12981 | Defect | Pratik Tiwari | Open |  | P3 | 2026-03-30 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Dev | FILTER-13040 | DEV - Win Ext : TS, Repeated searches on bing.com is not brokering | FILTER-13039 | Defect | Pratik Tiwari | Open |  | P2 | 2026-03-31 |  | 2026-04-15 | sprint-Gonzalo | 0 | 6 | FILTER
Dev | FILTER-13319 | DEV - Security issues with SSO access token and JWT created for GO broker - Part 1 | FILTER-13318 | Task | Sagar Satpute | Open |  | P3 | 2026-04-08 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Dev | PTGM-663 | Fix linter errors in www-filter repo | PTGM-666 | Story | Sagar Satpute | Open |  | P2 | 2026-01-05 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | PTGM
QA | FILTER-13320 | QA- Security issues with SSO access token and JWT created for GO broker - Part 1 | FILTER-13318 | Task | Surabhi Choudhary | Open |  | P3 | 2026-04-08 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FILTER
Task | FDSE-155 | Implementation for timepicker component | FDSE-136 | Epic | Swaroop Chavhan | Open |  | P3 | 2026-01-29 |  | 2026-04-28 | sprint-Gonzalo | 0 | 32 | FDSE | product-filter
Sub-task | FDSE-163 | Dev Task - Implementation for timepicker component | FDSE-155 | Task | Swaroop Chavhan | Open |  | P3 | 2026-02-22 |  | 2026-04-14 | sprint-Gonzalo | 0 | 0 | FDSE
Task | FDSE-164 | Search with auto-complete component enhancement | FDSE-174 | Epic | Swaroop Chavhan | Open |  | P3 | 2026-02-26 |  | 2026-04-28 | sprint-Gonzalo | 0 | 20 | FDSE | Capitalized-Feature, product-filter
Story | FILTER-12473 | Filter + Aware Accessibility - Mat tree |  |  | Swaroop Chavhan | Backlog |  | P3 | 2026-03-13 |  | 2026-04-21 | sprint-Gonzalo | 0 | 0 | FILTER

## Removed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Defect | FILTER-12150 | JS (All Extensions) Some sites opened from search link from Google AI mode does not start image blurring right away |  |  | Arun Thakur | Open |  | P2 | 2026-02-24 |  | 2026-04-02 | sprint-Gonzalo | 0 | 2 | FILTER | unplanned-sprint |  | YES
Story | FILTER-12400 | P1 Escalation - Extension API Fortification |  |  | Ashish Modak | Open |  | P1 | 2026-03-10 |  | 2026-04-28 | sprint-Gonzalo | 0 | 0 | FILTER | p1escalation, unplanned-sprint
Escape Defect | FILTER-10780 | SmartPAC on iOS can be broken by changing time on the iPad ¦ St. Vrain |  |  | Ashish Temurnikar | Open |  | P2 | 2025-11-13 |  | 2026-04-27 | sprint-Gonzalo | 5 | 0 | FILTER | jira_added, jira_backlog, jira_escalated, jira_open, jira_p2, zendesk_enterprise
Task | FILTER-12796 | Update Cron Job for tokenization |  |  | Prateek Fotedar | QA Verified | Fixed | P3 | 2026-03-27 | 2026-03-29 | 2026-04-27 | sprint-Gonzalo | 1 | 0 | FILTER | unplanned-sprint
Escape Defect | FILTER-12010 | P1 Escalation-Extension Bypass - Bookmark + stop page |  |  | Pratik Tiwari | Confirmation | Fixed | P1 | 2026-02-10 | 2026-04-06 | 2026-04-28 | sprint-Gonzalo | 20 | 0 | FILTER | jira_added, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_p1, jira_qa_verified, zendesk_enterprise, zendesk_org_at_risk
Defect | FILTER-7955 | [TS Extension]Google search results appear while typing in the bar |  |  | Pratik Tiwari | Open |  | P2 | 2025-04-18 |  | 2026-04-27 | sprint-Gonzalo | 0 | 0 | FILTER | EXTN, MV3

## P1 Escalation
P1 Escalation — FILTER · sprint-Gonzalo (2026-03-31 → 2026-04-13)
sprint-Gonzalo tickets where Issue Type = Escape Defect AND Priority = P1 AND summary contains 'P1 Escalation' (regardless of bucket). Total = 9.
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Bucket
Escape Defect | FILTER-11610 | P1 Escalation-CORs Errors at BlueBeam and Boomerang S3 Amazon domains ¦ St. Vrain |  |  | Ramani Cheruvu | In Progress | Fixed | P1 | 2026-01-08 | 2026-01-27 | 2026-04-27 | sprint-Gonzalo | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_reopened, p1escalation, unplanned-sprint, zendesk_enterprise |  | Removed
Escape Defect | FILTER-12119 | P1 Escalation-Investigate and address the use of about:blank pages as a filter loophole |  |  | Shashank Tiwari | In Progress |  | P1 | 2026-02-20 |  | 2026-04-28 | sprint-Gonzalo | 20 | 0 | FILTER | jira_added, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_p2, p1escalation, zendesk_enterprise, zendesk_org_at_risk |  | Not Completed
Escape Defect | FILTER-12476 | P1 Escalation-Extension Bypass - Opening new tab |  |  | Shashank Tiwari | QA READY | Fixed | P1 | 2026-03-13 | 2026-04-28 | 2026-04-28 | sprint-Gonzalo | 1 | 0 | FILTER | jira_added, jira_escalated, jira_in_progress, jira_open, jira_p1, zendesk_enterprise |  | Not Completed
Escape Defect | FILTER-12619 | P1 Escalation-Policy Map Import not showing policy names ¦ San Ramon |  |  | Shashank Tiwari | Waiting on support |  | P1 | 2026-03-23 |  | 2026-04-28 | sprint-Gonzalo | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_p2, jira_p3, p1escalation, zendesk_enterprise |  | Not Completed
Escape Defect | FILTER-12010 | P1 Escalation-Extension Bypass - Bookmark + stop page |  |  | Pratik Tiwari | Confirmation | Fixed | P1 | 2026-02-10 | 2026-04-06 | 2026-04-28 | sprint-Gonzalo | 20 | 0 | FILTER | jira_added, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_p1, jira_qa_verified, zendesk_enterprise, zendesk_org_at_risk |  | Removed
Escape Defect | FILTER-11654 | P1 Escalation-Crextn blocking issue with Google Workspace apps | FILTER-4326 | Epic | Shashank Tiwari | QA Verified | Done | P1 | 2026-01-15 | 2026-04-06 | 2026-04-28 | sprint-Gonzalo | 0 | 0 | FILTER | jira_added, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_qa_verified, jira_resolved |  | Removed
Escape Defect | FILTER-12093 | P1 Escalation-Students bypass Filter via W3Schools HTML sandbox using CDN / third-party iframe loading (GitHub content proxy) |  |  | Shashank Tiwari | Done | Fixed | P1 | 2026-02-18 | 2026-03-13 | 2026-04-16 | sprint-Gonzalo | 21 | 0 | FILTER | jira_added, jira_closed_notify, jira_confirmation, jira_done, jira_escalated, jira_open, jira_p1, jira_qa_verified, jira_reopened, unplanned-sprint, zendesk_enterprise |  | Completed
Escape Defect | FILTER-13105 | P1 Escalation-Looking for solution for HTML Editor vulnerabilities |  |  | Shashank Tiwari | QA Verified | Configuration Issue | P1 | 2026-04-02 | 2026-04-17 | 2026-04-27 | sprint-Gonzalo | 21 | 0 | FILTER | Reverified-2026, jira_added, jira_closed_notify, jira_done, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_qa_verified, p1escalation, unplanned-sprint, zendesk_enterprise |  | Completed
Escape Defect | FILTER-13129 | P1 Escalation- CA & UK DNS filtering not working as expected. |  |  | Shashank Tiwari | RELEASED TO PROD | Fixed | P1 | 2026-04-02 | 2026-04-06 | 2026-04-15 | sprint-Gonzalo | 1 | 3 | FILTER | Reverified-2026, p1escalation, unplanned-sprint |  | Completed