## Capacity vs Delivery
Capacity vs Delivery — FILTER · sprint-Hanna (Tue 14 Apr → Mon 27 Apr 2026)
Team Composition (per Securly-PjM-Skills.md Part 2 — Filter India roster). Inactive members for this sprint window are shaded grey with a roster note.
Name | Role | Function / Split | Allocation (FTE) | Seniority | Employment | Notes
Shashank Tiwari | Project Manager | PM / Delivery | 0 | Lead | FTE | Not counted in delivery capacity
Harsh Verma | FE | FrontEnd Architect (Angular) | 1 | Senior | FTE
Arun Thakur | FE + Ext | Angular / Extension | 1 | Medium | FTE
Harshada Kude | FE | Angular | 1 | Junior | FTE
Shailendra Singh | FE | Angular | 1 | Medium | FTE
Swaroop Chavhan | FE + Ext | Angular / Extension | 1 | Medium | FTE
Ashish Modak | BE Architect | Extension / Go / PHP | 1 | Senior | FTE
Prateek Fotedar | BE (www) | Go / PHP | 1 | Senior | FTE
Sagar Satpute | BE (www) | Go / PHP | 1 | Medium | FTE
Vaibhav Kumbhar | BE | Go / PHP | 1 | Medium | FTE
Ashish Temurnikar | BE | DNS / SPAC / Squid / Rust | 1 | Senior | FTE
Ravi Raj | BE | DNS / SPAC / Squid / Rust | 1 | Medium | FTE
Pratik Tiwari | BE + Ext | Extension / Go / Rust | 1 | Senior | FTE
Altamash Heroli | QA | Pri. Manual QA | 1 | Senior | FTE
Surabhi Choudhary | QA | Sr. Manual QA | 1 | Senior | FTE
Ayesha Kamde | QA | Manual QA | 1 | Junior | FTE
Amol Mithari | Auto QA Lead | Team Lead — Auto QA / SDET | 1 | Lead | FTE
Amit Shete | Auto QA | Pri. SDET | 1 | Senior | FTE
Rachit Mishra | Auto QA | SDET | 0 | Junior | FTE | Left team on 20-Feb-2026 — not part of this sprint
Total FILTER allocation |  |  |  | FTE-equivalent heads available to FILTER
Capacity Parameters (yellow cells are inputs — re-run the script after edits)
Parameter | Value | Description
Sprint length (working days) | 10 | FILTER 15-day sprint Tue → Mon. sprint-Hanna = 2026-04-14 → 2026-04-27.
Company holidays in sprint | 0 | India calendar 2026 — none in window
Effective working days (sprint − company holidays) |  | Used as the per-person calendar for availability
Hours per working day (nominal) | 8 | Standard working day
Focus factor (productive fraction) | 0.9 | 90% — what SLT expects (sprint-analysis default)
Misc buffer (meetings, scrums, code review, …) | 20% | 20% blanket reservation deducted from Available to get Net Available
Effective hours per FTE per sprint
Allocated FTE on FILTER (active this sprint) | 17 | Headcount actually working this sprint (excludes joiners/leavers outside window)
Ideal capacity for the sprint (hrs)
Issue scope (Jira projects) | FILTER, PTGM, FDSE | Tickets pulled with `project in (FILTER, PTGM, FDSE) AND sprint = …` — FDSE: 5 · FILTER: 471 · PTGM: 7
Capacity vs Actual Delivery — sprint-Hanna
Metric | Hours | % of Ideal | Rating | Notes
Actual Availability |  |  |  | Sum of per-person availability (Ideal − leaves)
Misc Buffer (20%) |  |  |  | Reserved for meetings, scrums, code reviews
Net Available (Available − Misc Buffer) |  |  |  | Realistic delivery capacity — used as the denominator for Completed %
Completed |  |  |  | Sum of in-sprint timeSpent (Completed bucket)
Not Completed (Spillover) |  |  |  | Original estimate for spillover (carried into next sprint)
Removed |  |  |  | Original estimate for issues removed mid-sprint
Completed by Priority
Tickets (parents) = unique parent items (Story / Task / Defect / Escape Defect) — subtasks roll up to their parent so 1 parent + 3 subtasks = 1 ticket. Tickets (incl. subtasks) = raw record count incl. every Dev / QA / Automation / Review / Test Case Creation / Debug subtask. Hours = sum across parents and subtasks; matches the core-team Completed hours on the Per-person Delivery sheet.
Priority | Tickets (parents) | Tickets (incl. subtasks) | Hours (incl. subtasks) | % of Completed Hrs | % of Tickets (parents) | Notes
P0 | 4 | 13 | 28.72 |  |  | Critical / production halting
P1 | 37 | 98 | 271.24 |  |  | P1 — high priority (see P1 Escalation tab for escalations)
P2 | 28 | 67 | 308.74 |  |  | Major
P3 | 26 | 60 | 371.66 |  |  | Standard
P4 | 1 | 2 | 25 |  |  | Minor / nice-to-have
TOTAL | 96 | 240 | 1005.36 | 100% | 100% | Sum of Completed bucket (core roster)
Sprint Completion (spillover = Not Completed)
Metric | Tickets | Planned Hrs (OE) | % by Tickets | % by Hrs | Notes
Completed (closed in sprint) | 240 | 1006 |  |  | In-sprint deliverables
Spillover (not completed → carry-over) | 62 | 211 |  |  | Original estimate carried to next sprint
Removed (mid-sprint scope cut) | 11 | 48 | — | — | Excluded from completion ratio (out of scope)
Mid-sprint additions (core) | 23 |  | — | — | Late-arriving work (Jira issueKeysAddedDuringSprint)
Sprint completion rate (tickets) | 79.47% | Below Target | Completed ÷ (Completed + Spillover)
Sprint completion rate (planned hrs) | 82.66% | Below Target | Σ OE Completed ÷ Σ OE (Completed + Spillover)
Planned completion rate (tickets, excludes mid-sprint adds) | 79.79% | Below Target | Originally-committed tickets only
Planned completion rate (planned hrs, excludes mid-sprint adds) | 89.38% | On Target | Originally-committed planned hours only
P1 Escalation snapshot
9 ticket(s) in sprint-Hanna match 'P1 Escalation' in the title — 4 closed, 5 still open. See the 'P1 Escalation' tab.
Mid-sprint additions snapshot
23 ticket(s) were added to sprint-Hanna after it started (issueKeysAddedDuringSprint) — Completed 11, Spillover 4, Removed 8. Highlighted in amber on every detail sheet (Added Mid-Sprint = YES).
Assumptions & caveats
• Sprint window from Jira (/rest/agile/1.0/sprint/6292): 2026-04-14 → 2026-04-27 (10 Mon–Fri working days). Refresh with fetch_filter_sprint_meta.py + fetch_filter_sprint_issues.py.
• Issues pulled from FILTER + PTGM + FDSE (project-scope expanded for the India scrum team's split across the three products).
• Date-aware roster: Amol Mithari joined 20-Feb-2026; Rachit Mishra's last day was 20-Feb-2026. Inactive members for this sprint window are shaded grey in the Team Composition table and excluded from per-person availability + delivery.
• Available (hrs) = (effective working days − leave days) × 8 × focus factor, where effective working days = sprint working days − company holidays falling inside the sprint − days outside the person's employment window. Per-person Delivery shows leave days in Column G to explain the delta from a full sprint.
• Net Available = Available − 20% Misc Buffer for meetings, scrums, code review, etc. Completed/Not Completed/Removed % of capacity use Net Available as the denominator.
• Time Spent on Completed sheet uses the in-sprint hybrid worklog rule (sprint-analysis.md): single-sprint = timespent; multi-sprint = SUM of worklogs whose started ∈ [sprintStart, sprintEnd].
• Not Completed and Removed totals use Original Estimate.
• Removed list comes from the Sprint Report puntedIssues (greenhopper API).
• Core roster only: assignees outside Securly-PjM-Skills.md Part 2 are dropped from per-person + detail sheets.
• P1 Escalation tab is filtered to Issue Type = Escape Defect AND Priority = P1 AND title contains 'P1 Escalation'.
• Completed by Priority — Tickets (parents) rolls subtasks up to their parent (each work item counted once at its parent priority); Tickets (incl. subtasks) shows the raw record count for comparison. The Hours column sums every record (parent + subtasks) and matches the core-team Completed total.
• Spillover = Not Completed bucket (tickets carried into the next sprint).
• Sprint completion rate uses Completed ÷ (Completed + Spillover); Removed tickets are excluded (treated as scope cut). 'Planned' rate also excludes mid-sprint additions.
• All detail sheets (Completed, Not Completed, Removed) highlight tickets added after sprint start (Jira sprint-report issueKeysAddedDuringSprint) in amber, with an 'Added Mid-Sprint = YES' tag column.
• Ratings: ≥85% On Target (green), 70–85% Below Target (amber), <70% Significantly Below (red).

## Per-person Delivery
Assignee | Completed (hrs) | Not Completed (hrs) | Removed (hrs) | Efficiency | Available (hrs) | Leave Days (sprint) | Misc Buffer 20% (hrs) | Net Available (hrs)
Harsh Verma | 57 | 0 | 48 |  | 72 | 0
Arun Thakur | 9 | 18 | 0 |  | 64.8 | 1
Harshada Kude | 49.5 | 14 | 0 |  | 64.8 | 1
Shailendra Singh | 54 | 10 | 0 |  | 72 | 0
Swaroop Chavhan | 62 | 52 | 0 |  | 72 | 0
Ashish Modak | 18 | 16 | 0 |  | 72 | 0
Prateek Fotedar | 115.5 | 20 | 0 |  | 72 | 0
Sagar Satpute | 81 | 0 | 0 |  | 72 | 0
Vaibhav Kumbhar | 73 | 0 | 0 |  | 57.6 | 2
Ashish Temurnikar | 26.42 | 0 | 0 |  | 64.8 | 1
Ravi Raj | 50 | 0 | 0 |  | 72 | 0
Pratik Tiwari | 81 | 4 | 0 |  | 57.6 | 2
Altamash Heroli | 28.94 | 0 | 0 |  | 72 | 0
Surabhi Choudhary | 201.5 | 0 | 0 |  | 72 | 0
Ayesha Kamde | 46.5 | 13 | 0 |  | 72 | 0
Amol Mithari | 16 | 47 | 0 |  | 72 | 0
Amit Shete | 36 | 17 | 0 |  | 64.8 | 1
TOTAL

## Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Escape Defect | FILTER-13743 | Filter >> Download, Email, and Scheduled reports are not working. |  |  | Altamash Heroli | RELEASED TO PROD | Fixed | P0 | 2026-04-23 | 2026-04-24 | 2026-04-27 | sprint-Hanna | 0.2 | 5 | FILTER |  |  | YES
Debug | FILTER-13801 | Helping team on Accessibility, PR reveiw, Technical discussions and sprint-palnning |  |  | Harsh Verma | Closed |  | P2 | 2026-04-27 |  | 2026-04-27 | sprint-Hanna | 21 | 20 | FILTER | unplanned-sprint |  | YES
Task | FDSE-173 | Mentioned issue fixes on different components |  |  | Harshada Kude | Resolved | Fixed | P2 | 2026-04-13 | 2026-04-23 | 2026-04-23 | sprint-Hanna | 19 | 16 | FDSE |  |  | YES
Task | FILTER-12244 | Need code changes to keep more versions of UI artifacts - Part 2 |  |  | Harshada Kude | Resolved | Fixed | P3 | 2026-02-26 | 2026-04-27 | 2026-04-28 | sprint-Hanna | 13.5 | 10 | FILTER | unplanned-sprint |  | YES
Task | FILTER-13621 | Filter Translation Regression Testing on SM |  |  | Harshada Kude | Closed |  | P2 | 2026-04-17 |  | 2026-04-27 | sprint-Hanna | 4 | 4 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12796 | Update Cron Job for tokenization |  |  | Prateek Fotedar | QA Verified | Fixed | P3 | 2026-03-27 | 2026-03-29 | 2026-04-27 | sprint-Hanna | 1 | 0 | FILTER | unplanned-sprint |  | YES
Task | FILTER-12200 | SPROX Manual Testing | FILTER-8230 | Epic | Surabhi Choudhary | QA Verified |  | P2 | 2026-02-25 |  | 2026-04-25 | sprint-Hanna | 24 | 0 | FILTER |  |  | YES
Task | FDSE-156 | Tooltip variation on options | FDSE-139 | Epic | Swaroop Chavhan | Resolved | Fixed | P3 | 2026-02-01 | 2026-04-27 | 2026-04-28 | sprint-Hanna | 30 | 16 | FDSE |  |  | YES
Story | FILTER-13620 | Filter A11y - Check and fix deque reported issues in Aware. |  |  | Swaroop Chavhan | Ready For Release |  | P2 | 2026-04-17 |  | 2026-04-28 | sprint-Hanna | 16 | 16 | FILTER | unplanned-sprint |  | YES
Task | PTGM-686 | [Support tool] Update context with traceid, sessionid |  |  | Vaibhav Kumbhar | Closed | Done | P3 | 2026-03-30 | 2026-04-27 | 2026-04-28 | sprint-Hanna | 6 | 4 | PTGM |  |  | YES
Task | PTGM-687 | [www-filter] Update context with traceid and sessionid |  |  | Vaibhav Kumbhar | Resolved | Done | P3 | 2026-03-30 | 2026-04-13 | 2026-04-17 | sprint-Hanna | 0 | 6 | PTGM |  |  | YES
QA | FILTER-11167 | Manual QA Validation for Policy Map Security Group Initial Load and Search Failure | FILTER-10462 | Escape Defect | Altamash Heroli | QA Verified |  | P3 | 2025-12-02 |  | 2026-04-27 | sprint-Hanna | 1 | 1 | FILTER
QA | FILTER-12325 | QA- BugCrowd-850af9c1-f86b-4c74-91ac-94ea808c8e9b-Deleted User to Continue Performing Privileged Actions (Account Deletion Bypass) | FILTER-12323 | Defect | Altamash Heroli | QA Verified |  | P3 | 2026-03-02 |  | 2026-04-24 | sprint-Hanna | 12 | 4 | FILTER
QA | FILTER-12705 | QA- Support Tool >> Custom list UI. Custom List table and Custom List Resource table headers are not in bold | FILTER-12702 | Defect | Altamash Heroli | Closed without action |  | P3 | 2026-03-26 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-12706 | QA- Support Tool >> Custom list UI. Custom List table and Custom List Resource table headers are not in bold | FILTER-12702 | Defect | Altamash Heroli | Done |  | P3 | 2026-03-26 |  | 2026-04-21 | sprint-Hanna | 0.33 | 1 | FILTER
QA | FILTER-12770 | QA- Support Tool >> Custom list UI. Custom List table. Listing Order is incorrect. Should be A-Z. | FILTER-12768 | Defect | Altamash Heroli | Done |  | P3 | 2026-03-27 |  | 2026-04-21 | sprint-Hanna | 0.33 | 1 | FILTER
QA | FILTER-12774 | QA- Support Tool >> Custom list UI. Custom List table >> List names become center aligned if the Brower Zoom is 110% or more. | FILTER-12772 | Defect | Altamash Heroli | Done |  | P3 | 2026-03-27 |  | 2026-04-21 | sprint-Hanna | 0.17 | 1 | FILTER
QA | FILTER-12778 | QA- Support Tool >> Custom list UI. Custom List table >> Action icons lose aligned if the Brower Zoom is 110% or more. | FILTER-12776 | Defect | Altamash Heroli | QA Verified |  | P3 | 2026-03-27 |  | 2026-04-20 | sprint-Hanna | 0.33 | 1 | FILTER
QA | FILTER-12858 | QA- Support Tool >> Custom list UI. Custom List table >> "Updated on" field's date format is inconsistent with date format on FID listing page's " Last edited / created" field | FILTER-12856 | Defect | Altamash Heroli | Done |  | P3 | 2026-03-27 |  | 2026-04-21 | sprint-Hanna | 0.08 | 1 | FILTER
QA | FILTER-12866 | QA- Support Tool >> Custom list UI. Custom List table >> "Last updated by" field is not showing value for every list | FILTER-12864 | Defect | Altamash Heroli | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-12870 | QA- Support Tool >> Custom list UI. Custom List table >> we are able to see global lists which are created by non support tool users as well | FILTER-12868 | Defect | Altamash Heroli | QA Verified |  | P1 | 2026-03-27 |  | 2026-04-22 | sprint-Hanna | 0.5 | 1 | FILTER
QA | FILTER-12874 | QA- Support Tool >> Custom list UI. Custom List table, Custom List Resource table >> icons section missing table header | FILTER-12872 | Defect | Altamash Heroli | QA Verified |  | P3 | 2026-03-27 |  | 2026-04-20 | sprint-Hanna | 0.5 | 1 | FILTER
QA | FILTER-12886 | QA- Support Tool >> Custom list UI. Custom List table, Custom List Resource table >> Formatting issues in table if List Name and Comment is big (255 characters each) | FILTER-12884 | Defect | Altamash Heroli | Done |  | P3 | 2026-03-27 |  | 2026-04-21 | sprint-Hanna | 0.5 | 1 | FILTER
QA | FILTER-12890 | QA- Support Tool >> Custom list UI. Create custom list and Edit custom list, pages do not have * mark for Mandatory fields | FILTER-12888 | Defect | Altamash Heroli | Done |  | P3 | 2026-03-27 |  | 2026-04-21 | sprint-Hanna | 0.33 | 1 | FILTER
QA | FILTER-12894 | QA- Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for more than 255 character length | FILTER-12892 | Defect | Altamash Heroli | QA Verified |  | P2 | 2026-03-27 |  | 2026-04-20 | sprint-Hanna | 0.33 | 1 | FILTER
QA | FILTER-12898 | QA- Support Tool >> Custom list UI. Create custom list Resource and Update custom list Resource, drawer should validated for comment length on Save of that drawer | FILTER-12896 | Defect | Altamash Heroli | QA Verified |  | P2 | 2026-03-27 |  | 2026-04-20 | sprint-Hanna | 0.33 | 1 | FILTER
QA | FILTER-12902 | QA- Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for duplicate Custom list name | FILTER-12900 | Defect | Altamash Heroli | QA Verified |  | P2 | 2026-03-27 |  | 2026-04-21 | sprint-Hanna | 0.5 | 1 | FILTER
QA | FILTER-12910 | QA- Support Tool >> Custom list UI. Edit custom list, User can change the Type on Edit. | FILTER-12908 | Defect | Altamash Heroli | QA Verified |  | P1 | 2026-03-27 |  | 2026-04-22 | sprint-Hanna | 0.33 | 1 | FILTER
QA | FILTER-12934 | QA- Support Tool >> Custom list UI. Edit custom list Search terms type, allows changing Match type and saves it. But does not reflect the change. | FILTER-12932 | Defect | Altamash Heroli | QA Verified |  | P1 | 2026-03-27 |  | 2026-04-22 | sprint-Hanna | 0.33 | 1 | FILTER
QA | FILTER-12938 | QA- Support Tool >> Custom list UI. Add custom list Search terms type, does not save for Match type Contains | FILTER-12936 | Defect | Altamash Heroli | QA Verified |  | P1 | 2026-03-27 |  | 2026-04-22 | sprint-Hanna | 0.33 | 1 | FILTER
QA | FILTER-12999 | QA- Support Tool >> Custom list UI. Cross Cluster Create custom lists are not displayed in other clusters | FILTER-12997 | Defect | Altamash Heroli | QA Verified |  | P1 | 2026-03-30 |  | 2026-04-21 | sprint-Hanna | 0.5 | 1 | FILTER
QA | FILTER-13379 | QA- Safety Console >> Policy Editor. Allow/Block Search terms' pop-up does not show value if added text is not as per validations. | FILTER-13377 | Defect | Altamash Heroli | QA Verified |  | P3 | 2026-04-09 |  | 2026-04-21 | sprint-Hanna | 0.67 | 1 | FILTER
QA | FILTER-13401 | QA- Safety Console >> Filter. Activities. Deleted Admin group user is able add activities to Allow/Block list | FILTER-13399 | Defect | Altamash Heroli | Closed without action |  | P2 | 2026-04-09 |  | 2026-04-22 | sprint-Hanna | 0.17 | 2 | FILTER
QA | FILTER-13456 | QA- Support Tool. After searching for FID from FID Detail page's FID name dropdown, the FID name is not cleared | FILTER-13454 | Escape Defect | Altamash Heroli | QA Verified |  | P1 | 2026-04-11 |  | 2026-04-20 | sprint-Hanna | 0.5 | 1 | FILTER
QA | FILTER-13460 | QA- Support Tool. FID search from FID Detail page's FID name dropdown is not able to search when spaces are present at the start or end of the query. | FILTER-13458 | Escape Defect | Altamash Heroli | QA Verified |  | P3 | 2026-04-11 |  | 2026-04-20 | sprint-Hanna | 0.33 | 1 | FILTER
QA | FILTER-13464 | QA- Support Tool. FID search from FID Detail page's FID name dropdown can search and display closed accounts as well | FILTER-13462 | Escape Defect | Altamash Heroli | QA Verified |  | P2 | 2026-04-11 |  | 2026-04-20 | sprint-Hanna | 0.33 | 1 | FILTER
QA | FILTER-13544 | QA- Safety Console >> Filter. Admin Group. Admin user if removed from DA, looses Admin session as well | FILTER-13542 | Defect | Altamash Heroli | QA Verified |  | P0 | 2026-04-14 |  | 2026-04-23 | sprint-Hanna | 2 | 2 | FILTER
QA | FILTER-13584 | QA- Safety Console >> Filter. Translation and Accessibility issues | FILTER-13581 | Escape Defect | Altamash Heroli | Closed without action |  | P1 | 2026-04-16 |  | 2026-04-16 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13585 | QA- Safety Console >> Filter. Translation and Accessibility issues | FILTER-13581 | Escape Defect | Altamash Heroli | QA Verified |  | P1 | 2026-04-16 |  | 2026-04-23 | sprint-Hanna | 3 | 5 | FILTER
QA | FILTER-13741 | QA- P1 Escalation-Filter reports file URLs are easily guessable and the S3 bucket used for downloads is publicly accessible. | FILTER-13739 | Escape Defect | Altamash Heroli | QA Verified |  | P1 | 2026-04-22 |  | 2026-04-24 | sprint-Hanna | 3 | 2 | FILTER
QA | FILTER-13749 | QA- Filter >> Download, Email, and Scheduled reports are not working. | FILTER-13743 | Escape Defect | Altamash Heroli | QA Verified |  | P0 | 2026-04-23 |  | 2026-04-24 | sprint-Hanna | 0.02 | 2 | FILTER
Automation | FILTER-11243 | Automated E2E Regression Test: Fix Unwanted f.txt File Download on Google Image Scroll | FILTER-7666 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2025-12-03 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-11382 | Automated E2E Regression Test: Validate Complete YouTube URL Logging from Embedded Clicks | FILTER-11181 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2025-12-09 |  | 2026-04-14 | sprint-Hanna | 0 | 6 | FILTER
Automation | FILTER-11537 | New Feature ¦ Automation Suite Development (Tokenization & Resilience) | FILTER-11532 | Story | Amit Shete | Closed without action |  | P3 | 2025-12-19 |  | 2026-04-28 | sprint-Hanna | 0 | 6 | FILTER | Capitalized-Feature
Automation | FILTER-11656 | Create Automated Tests for Crextn Google Workspace Blocking | FILTER-11654 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-01-15 |  | 2026-04-28 | sprint-Hanna | 7.5 | 7 | FILTER
Automation | FILTER-11660 | Create Automated Tests for FluentD Tokenization Phase 3 (UserToken) | FILTER-11631 | Story | Amit Shete | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Hanna | 6 | 6 | FILTER | Capitalized-Feature
Automation | FILTER-11845 | Add test cases for SafetyConsole CustomList API token invalidation | FILTER-11687 | Defect | Amit Shete | Done |  | P2 | 2026-01-29 |  | 2026-04-14 | sprint-Hanna | 4 | 4 | FILTER
Automation | FILTER-11874 | Add tests for CustomList API token invalidation on Filter Product disable | FILTER-11688 | Escape Defect | Amit Shete | Done |  | P3 | 2026-01-29 |  | 2026-04-14 | sprint-Hanna | 4 | 4 | FILTER
Automation | FILTER-12040 | Add regression coverage for bookmark + stop-request bypass | FILTER-12010 | Escape Defect | Amit Shete | Done |  | P1 | 2026-02-12 |  | 2026-04-14 | sprint-Hanna | 4 | 4 | FILTER
Automation | FILTER-12187 | Scripting for GO broker SSO cookie and JWT auth regression | FILTER-12048 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-02-25 |  | 2026-04-20 | sprint-Hanna | 0 | 8 | FILTER
Automation | FILTER-12201 | SPROX Testing with P0 suite | FILTER-12199 | Task | Amit Shete | Done |  | P2 | 2026-02-25 |  | 2026-04-14 | sprint-Hanna | 4.5 | 8 | FILTER
Automation | FILTER-12562 | Re-run SPROX Testing with P0 suite post Dev Fixes | FILTER-12199 | Task | Amit Shete | Done |  | P2 | 2026-03-18 |  | 2026-04-14 | sprint-Hanna | 6 | 6 | FILTER
Automation | FILTER-12707 | QA- Support Tool >> Custom list UI. Custom List table and Custom List Resource table headers are not in bold | FILTER-12702 | Defect | Amit Shete | Closed without action |  | P3 | 2026-03-26 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12721 | QA- TS Ext + Go. Site Approved via TWL process, gets logged in Default Policy rather than Global Policy | FILTER-12716 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-03-26 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12771 | QA- Support Tool >> Custom list UI. Custom List table. Listing Order is incorrect. Should be A-Z. | FILTER-12768 | Defect | Amit Shete | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12775 | QA- Support Tool >> Custom list UI. Custom List table >> List names become center aligned if the Brower Zoom is 110% or more. | FILTER-12772 | Defect | Amit Shete | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-21 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12779 | QA- Support Tool >> Custom list UI. Custom List table >> Action icons lose aligned if the Brower Zoom is 110% or more. | FILTER-12776 | Defect | Amit Shete | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12799 | QA- Update Cron Job for tokenization | FILTER-12796 | Task | Amit Shete | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12859 | QA- Support Tool >> Custom list UI. Custom List table >> "Updated on" field's date format is inconsistent with date format on FID listing page's " Last edited / created" field | FILTER-12856 | Defect | Amit Shete | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12867 | QA- Support Tool >> Custom list UI. Custom List table >> "Last updated by" field is not showing value for every list | FILTER-12864 | Defect | Amit Shete | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12871 | QA- Support Tool >> Custom list UI. Custom List table >> we are able to see global lists which are created by non support tool users as well | FILTER-12868 | Defect | Amit Shete | Closed without action |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12875 | QA- Support Tool >> Custom list UI. Custom List table, Custom List Resource table >> icons section missing table header | FILTER-12872 | Defect | Amit Shete | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12887 | QA- Support Tool >> Custom list UI. Custom List table, Custom List Resource table >> Formatting issues in table if List Name and Comment is big (255 characters each) | FILTER-12884 | Defect | Amit Shete | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12891 | QA- Support Tool >> Custom list UI. Create custom list and Edit custom list, pages do not have * mark for Mandatory fields | FILTER-12888 | Defect | Amit Shete | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12895 | QA- Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for more than 255 character length | FILTER-12892 | Defect | Amit Shete | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12899 | QA- Support Tool >> Custom list UI. Create custom list Resource and Update custom list Resource, drawer should validated for comment length on Save of that drawer | FILTER-12896 | Defect | Amit Shete | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12903 | QA- Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for duplicate Custom list name | FILTER-12900 | Defect | Amit Shete | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12907 | QA- Support Tool >> Custom list UI. Create custom list Resource and Edit custom list Resource, drawers donot check for duplicate Custom list resource. | FILTER-12904 | Defect | Amit Shete | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12911 | QA- Support Tool >> Custom list UI. Edit custom list, User can change the Type on Edit. | FILTER-12908 | Defect | Amit Shete | Closed without action |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12935 | QA- Support Tool >> Custom list UI. Edit custom list Search terms type, allows changing Match type and saves it. But does not reflect the change. | FILTER-12932 | Defect | Amit Shete | Closed without action |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12939 | QA- Support Tool >> Custom list UI. Add custom list Search terms type, does not save for Match type Contains | FILTER-12936 | Defect | Amit Shete | Closed without action |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13000 | QA- Support Tool >> Custom list UI. Cross Cluster Create custom lists are not displayed in other clusters | FILTER-12997 | Defect | Amit Shete | Closed without action |  | P1 | 2026-03-30 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13051 | QA- GO extension: proxy call shows success for unauthorized user | FILTER-13048 | Defect | Amit Shete | Closed without action |  | P1 | 2026-03-31 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13108 | QA- Looking for solution for HTML Editor vulnerabilities | FILTER-13105 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-04-02 |  | 2026-04-16 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13301 | QA- NewFeatureBug. GO DNS: Temporary UserToken is generated even when platform service is available | FILTER-13298 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-07 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13313 | QA- NewFeatureBug. GO SPAC: UserToken not present for verbose logs | FILTER-13310 | Defect | Amit Shete | Closed without action |  | P2 | 2026-04-07 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13347 | QA- NewFeatureBug. SPAC: After anonymous user log, activities do not have userToken | FILTER-13344 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-08 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13355 | QA- NewFeatureBug. SPAC: userToken not created when Force logins is ON | FILTER-13352 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-08 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13380 | QA- Safety Console >> Policy Editor. Allow/Block Search terms' pop-up does not show value if added text is not as per validations. | FILTER-13377 | Defect | Amit Shete | Closed without action |  | P3 | 2026-04-09 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13402 | QA- Safety Console >> Filter. Activities. Deleted Admin group user is able add activities to Allow/Block list | FILTER-13399 | Defect | Amit Shete | Closed without action |  | P2 | 2026-04-09 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13445 | QA- SPROX: suicide.org throws Bad Request error | FILTER-13442 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-10 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13457 | QA- Support Tool. After searching for FID from FID Detail page's FID name dropdown, the FID name is not cleared | FILTER-13454 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-04-11 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13461 | QA- Support Tool. FID search from FID Detail page's FID name dropdown is not able to search when spaces are present at the start or end of the query. | FILTER-13458 | Escape Defect | Amit Shete | Closed without action |  | P3 | 2026-04-11 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13465 | QA- Support Tool. FID search from FID Detail page's FID name dropdown can search and display closed accounts as well | FILTER-13462 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-04-11 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13485 | QA- SPROX: baidu.com suspicious searches are not logged | FILTER-13482 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-11 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13489 | QA- SPROX: wikipedia searches are not logged when search is made from bookmark | FILTER-13486 | Defect | Amit Shete | Closed without action |  | P2 | 2026-04-11 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13493 | QA- SPROX: ask.com suspicious & allowed searches are not logged | FILTER-13490 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-11 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13506 | QA- CLONE - SPROX: Wrong category logged | FILTER-13503 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-13 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13510 | QA- SPROX: Incorrect policy logging | FILTER-13507 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-13 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13521 | QA- SPROX: Search engines do not get blocked when category is Other Search Engine | FILTER-13518 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-14 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13529 | QA- SPROX: YT keyword block is not getting logged | FILTER-13526 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-14 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13545 | QA- Safety Console >> Filter. Admin Group. Admin user if removed from DA, looses Admin session as well | FILTER-13542 | Defect | Amit Shete | Closed without action |  | P0 | 2026-04-14 |  | 2026-04-27 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13561 | QA- SPROX: GO DNS. Suspicious and allowed searches on any search engine is not getting logged | FILTER-13556 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-15 |  | 2026-04-23 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13567 | QA- SPROX: GO DNS. YouTube video logging is not happening | FILTER-13562 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-15 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13586 | QA- Safety Console >> Filter. Translation and Accessibility issues | FILTER-13581 | Escape Defect | Amit Shete | Closed without action |  | P1 | 2026-04-16 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13590 | QA- SPROX: GO DNS.Force Logins OFF. New categories are not getting blocked | FILTER-13587 | Defect | Amit Shete | Closed without action |  | P2 | 2026-04-16 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13604 | QA- SPROX: GO DNS. Search terms not getting blocked on google.com | FILTER-13601 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-16 |  | 2026-04-23 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13638 | QA- SPROX & Squid: GO SPAC/DNS. Custom group policy is not applied | FILTER-13635 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-17 |  | 2026-04-20 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13733 | QA- SPROX: Filter leaks within the 10 mins ban | FILTER-13730 | Defect | Amit Shete | Closed without action |  | P2 | 2026-04-22 |  | 2026-04-24 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13742 | QA- P1 Escalation-Filter reports file URLs are easily guessable and the S3 bucket used for downloads is publicly accessible. | FILTER-13739 | Escape Defect | Amit Shete | Closed without action |  | P2 | 2026-04-22 |  | 2026-04-24 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13750 | QA- Filter >> Download, Email, and Scheduled reports are not working. | FILTER-13743 | Escape Defect | Amit Shete | Closed without action |  | P0 | 2026-04-23 |  | 2026-04-24 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13762 | QA- Home SPROX: Pause is not getting applied for a kid with SPROX enabled | FILTER-13759 | Defect | Amit Shete | Closed without action |  | P1 | 2026-04-24 |  | 2026-04-24 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12450 | QA- Site not loading correctly with extension | FILTER-12447 | Escape Defect | Amol Mithari | Done |  | P3 | 2026-03-12 |  | 2026-04-26 | sprint-Hanna | 2 | 2 | FILTER
Automation | FILTER-12458 | QA- Filter bypass by taping on a link from Google Search - Crxtn | FILTER-12455 | Escape Defect | Amol Mithari | Closed without action |  | P1 | 2026-03-12 |  | 2026-04-14 | sprint-Hanna | 0 | 3 | FILTER
Automation | FILTER-12795 | QA- Chrome Extension : Log in page is not shown | FILTER-12792 | Defect | Amol Mithari | Done |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 2 | 2 | FILTER
Automation | FILTER-12851 | QA- [Edge] - Bing allow p o r n search | FILTER-12848 | Defect | Amol Mithari | Done |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 2 | 2 | FILTER
Automation | FILTER-13034 | QA- Automate performance testing for tokenization cron job | FILTER-13031 | Task | Amol Mithari | Done |  | P3 | 2026-03-31 |  | 2026-04-14 | sprint-Hanna | 10 | 5 | FILTER
Dev | FILTER-11355 | Reopened - Fix Unwanted 'Ask for Leaving Page' Popup on Search Sites When Overlay is Enabled | FILTER-10558 | Escape Defect | Arun Thakur | Closed without action |  | P2 | 2025-12-08 |  | 2026-04-14 | sprint-Hanna | 3 | 8 | FILTER
Dev | FILTER-11381 | Fix CRXTN Logging Failure: Incomplete YouTube URL Captured from Embedded Video Clicks | FILTER-11181 | Escape Defect | Arun Thakur | Done |  | P2 | 2025-12-09 |  | 2026-04-17 | sprint-Hanna | 6 | 4 | FILTER
Dev | FILTER-12229 | DEV - JS (All Extensions): Youtube.YT logo on YT page, YT search page, YT video page and YT shorts is not clickable | FILTER-12228 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-02-25 |  | 2026-04-15 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-12394 | DEV - DA Filter >> Activities. DA is able to see activities of kids from other OU as well | FILTER-12393 | Defect | Arun Thakur | Closed without action |  | P1 | 2026-03-09 |  | 2026-04-14 | sprint-Hanna | 0 | 4 | FILTER
Dev | FILTER-13336 | DEV - Image Blur Feature: Google Drive - Download and Copy options available for blurred images | FILTER-13335 | Defect | Arun Thakur | Code Review |  | P1 | 2026-04-08 |  | 2026-04-20 | sprint-Hanna | 0 | 4 | FILTER
Dev | FILTER-12513 | Implement end-to-end integration of the Verified Access API, including required Chromebook-side changes to support the API. | FILTER-12512 | Task | Ashish Modak | Done |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 16 | 16 | FILTER
Dev | FILTER-12849 | DEV - [Edge] - Bing allow p o r n search | FILTER-12848 | Defect | Ashish Modak | Closed without action |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 2 | 8 | FILTER
Dev | FILTER-11994 | New Feature ¦ DNS and SPAC changes for Tokenization | FILTER-11532 | Story | Ashish Temurnikar | Done |  | P3 | 2026-02-09 |  | 2026-04-14 | sprint-Hanna | 20 | 10 | FILTER | Capitalized-Feature
Dev | FILTER-13508 | DEV - SPROX: Incorrect policy logging | FILTER-13507 | Defect | Ashish Temurnikar | Closed without action |  | P1 | 2026-04-13 |  | 2026-04-14 | sprint-Hanna | 1 | 1 | FILTER
Dev | FILTER-13731 | DEV - SPROX: Filter leaks within the 10 mins ban | FILTER-13730 | Defect | Ashish Temurnikar | Done |  | P2 | 2026-04-22 |  | 2026-04-24 | sprint-Hanna | 4 | 4 | FILTER
Review | FILTER-13763 | Review - DEV - SPROX: GO DNS. YouTube video logging is not happening | FILTER-13562 | Defect | Ashish Temurnikar | Done |  | P2 | 2026-04-24 |  | 2026-04-27 | sprint-Hanna | 0.25 | 0 | FILTER
Review | FILTER-13764 | Review - DEV - SPROX: GO DNS.Force Logins OFF. New categories are not getting blocked | FILTER-13587 | Defect | Ashish Temurnikar | Done |  | P2 | 2026-04-24 |  | 2026-04-27 | sprint-Hanna | 1 | 0 | FILTER
Review | FILTER-13771 | Review - DEV - Home SPROX: Pause is not getting applied for a kid with SPROX enabled | FILTER-13759 | Defect | Ashish Temurnikar | Done |  | P2 | 2026-04-24 |  | 2026-04-24 | sprint-Hanna | 0 | 0 | FILTER
Review | FILTER-13800 | Review - DEV - SPROX: YT keyword block is not getting logged | FILTER-13526 | Defect | Ashish Temurnikar | Done |  | P2 | 2026-04-27 |  | 2026-04-27 | sprint-Hanna | 0.17 | 0 | FILTER
QA | FILTER-11149 | Manual QA Validation for "Leaving Page" Popup on Search Engines (Overlay Enabled) | FILTER-10558 | Escape Defect | Ayesha Kamde | Done |  | P2 | 2025-12-02 |  | 2026-04-21 | sprint-Hanna | 3 | 3 | FILTER
QA | FILTER-11383 | Manual QA Validation for Incomplete YouTube URL Logging from Embedded Clicks | FILTER-11181 | Escape Defect | Ayesha Kamde | Done |  | P2 | 2025-12-09 |  | 2026-04-24 | sprint-Hanna | 6 | 6 | FILTER
QA | FILTER-11657 | Test Crextn Google Workspace Blocking Fix | FILTER-11654 | Escape Defect | Ayesha Kamde | QA Verified |  | P1 | 2026-01-15 |  | 2026-04-28 | sprint-Hanna | 13 | 12 | FILTER
QA | FILTER-12230 | QA- JS (All Extensions): Youtube.YT logo on YT page, YT search page, YT video page and YT shorts is not clickable | FILTER-12228 | Defect | Ayesha Kamde | Done |  | P1 | 2026-02-25 |  | 2026-04-20 | sprint-Hanna | 1.5 | 2 | FILTER
QA | FILTER-12719 | QA- TS Ext + Go. Site Approved via TWL process, gets logged in Default Policy rather than Global Policy | FILTER-12716 | Escape Defect | Ayesha Kamde | Done |  | P2 | 2026-03-26 |  | 2026-04-17 | sprint-Hanna | 6 | 3.5 | FILTER
QA | FILTER-12720 | QA- TS Ext + Go. Site Approved via TWL process, gets logged in Default Policy rather than Global Policy | FILTER-12716 | Escape Defect | Ayesha Kamde | Closed without action |  | P1 | 2026-03-26 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13107 | QA- Looking for solution for HTML Editor vulnerabilities | FILTER-13105 | Escape Defect | Ayesha Kamde | Done |  | P1 | 2026-04-02 |  | 2026-04-23 | sprint-Hanna | 9 | 12 | FILTER
QA | FILTER-13647 | QA - [Proxy]: Send fid and userEmail to pagescan | FILTER-13645 | Task | Ayesha Kamde | Done |  | P1 | 2026-04-20 |  | 2026-04-22 | sprint-Hanna | 8 | 8 | FILTER
Dev | FILTER-12242 | Do the required changes in order to achieve the Story's ask | FILTER-12241 | Story | Harsh Verma | Done |  | P3 | 2026-02-26 |  | 2026-04-16 | sprint-Hanna | 36 | 32 | FILTER
Dev | FILTER-13378 | DEV - Safety Console >> Policy Editor. Allow/Block Search terms' pop-up does not show value if added text is not as per validations. | FILTER-13377 | Defect | Harshada Kude | Done |  | P3 | 2026-04-09 |  | 2026-04-21 | sprint-Hanna | 1 | 0.5 | FILTER
Dev | FILTER-13583 | DEV - Safety Console >> Filter. Translation and Accessibility issues | FILTER-13581 | Escape Defect | Harshada Kude | Done |  | P1 | 2026-04-16 |  | 2026-04-20 | sprint-Hanna | 12 | 8 | FILTER
Dev | FILTER-11533 | New Feature ¦ Implement UserToken Retrieval for Signed-In Users | FILTER-11532 | Story | Prateek Fotedar | Done |  | P3 | 2025-12-19 |  | 2026-04-14 | sprint-Hanna | 15 | 15 | FILTER | Capitalized-Feature
Dev | FILTER-11535 | New Feature ¦ Tokenization Error Recovery & Fallback Logic | FILTER-11532 | Story | Prateek Fotedar | Done |  | P3 | 2025-12-19 |  | 2026-04-14 | sprint-Hanna | 35 | 35 | FILTER | Capitalized-Feature
Dev | FILTER-11659 | Phase 3 - Implement FluentD Changes for Tokenization (UserToken) | FILTER-11631 | Story | Prateek Fotedar | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Hanna | 12 | 12 | FILTER | Capitalized-Feature
Dev | FILTER-11954 | New Feature ¦ DNS and SPAC changes for Tokenization | FILTER-11532 | Story | Prateek Fotedar | Done |  | P3 | 2026-02-03 |  | 2026-04-14 | sprint-Hanna | 16 | 16 | FILTER | Capitalized-Feature
Dev | FILTER-12301 | POST /api/custom-list allows Admin to create custom list with usage "GLOBAL" - should be rejected | FILTER-11776 | Defect | Prateek Fotedar | Closed without action |  | P3 | 2026-03-01 |  | 2026-04-24 | sprint-Hanna | 0.5 | 6 | FILTER | Capitalized-Feature
Dev | FILTER-12445 | Dev Task to remove test email id from alert | FILTER-12384 | Task | Prateek Fotedar | Done |  | P3 | 2026-03-12 |  | 2026-04-20 | sprint-Hanna | 3 | 3 | FILTER
Dev | FILTER-12701 | BE - DA Filter >> Activities. DA is able to see activities of kids from other OU as well | FILTER-12393 | Defect | Prateek Fotedar | Code Review |  | P1 | 2026-03-26 |  | 2026-04-21 | sprint-Hanna | 0 | 7 | FILTER
Dev | FILTER-12769 | DEV - Support Tool >> Custom list UI. Custom List table. Listing Order is incorrect. Should be A-Z. | FILTER-12768 | Defect | Prateek Fotedar | Done |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 1.5 | 1.5 | FILTER
Dev | FILTER-12797 | DEV - Update Cron Job for tokenization | FILTER-12796 | Task | Prateek Fotedar | Done |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 6 | 6 | FILTER
Dev | FILTER-12865 | DEV - Support Tool >> Custom list UI. Custom List table >> "Last updated by" field is not showing value for every list | FILTER-12864 | Defect | Prateek Fotedar | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 1 | 1 | FILTER
Dev | FILTER-12869 | DEV - Support Tool >> Custom list UI. Custom List table >> we are able to see global lists which are created by non support tool users as well | FILTER-12868 | Defect | Prateek Fotedar | Closed without action |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 1.5 | 1.5 | FILTER
Dev | FILTER-12893 | DEV - Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for more than 255 character length | FILTER-12892 | Defect | Prateek Fotedar | Done |  | P2 | 2026-03-27 |  | 2026-04-17 | sprint-Hanna | 2 | 2 | FILTER
Dev | FILTER-12901 | DEV - Support Tool >> Custom list UI. Create custom list and Edit custom list, pages error message is not explanatory for duplicate Custom list name | FILTER-12900 | Defect | Prateek Fotedar | Done |  | P2 | 2026-03-27 |  | 2026-04-17 | sprint-Hanna | 2 | 2 | FILTER
Dev | FILTER-12937 | DEV - Support Tool >> Custom list UI. Add custom list Search terms type, does not save for Match type Contains | FILTER-12936 | Defect | Prateek Fotedar | Done |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 3 | 3 | FILTER
Dev | FILTER-12998 | DEV - Support Tool >> Custom list UI. Cross Cluster Create custom lists are not displayed in other clusters | FILTER-12997 | Defect | Prateek Fotedar | Done |  | P1 | 2026-03-30 |  | 2026-04-14 | sprint-Hanna | 4 | 4 | FILTER
Dev | FILTER-13032 | DEV - Automate performance testing for tokenization cron job | FILTER-13031 | Task | Prateek Fotedar | Closed without action |  | P3 | 2026-03-31 |  | 2026-04-21 | sprint-Hanna | 1 | 1 | FILTER
Dev | FILTER-13299 | DEV - NewFeatureBug. GO DNS: Temporary UserToken is generated even when platform service is available | FILTER-13298 | Defect | Prateek Fotedar | Done |  | P1 | 2026-04-07 |  | 2026-04-17 | sprint-Hanna | 1 | 1 | FILTER
Dev | FILTER-13311 | DEV - NewFeatureBug. GO SPAC: UserToken not present for verbose logs | FILTER-13310 | Defect | Prateek Fotedar | Done |  | P1 | 2026-04-07 |  | 2026-04-20 | sprint-Hanna | 4 | 4 | FILTER
Dev | FILTER-13345 | DEV - NewFeatureBug. SPAC: After anonymous user log, activities do not have userToken | FILTER-13344 | Defect | Prateek Fotedar | Done |  | P1 | 2026-04-08 |  | 2026-04-20 | sprint-Hanna | 3 | 3 | FILTER
Dev | FILTER-13353 | DEV - NewFeatureBug. SPAC: userToken not created when Force logins is ON | FILTER-13352 | Defect | Prateek Fotedar | Done |  | P1 | 2026-04-08 |  | 2026-04-20 | sprint-Hanna | 3 | 3 | FILTER
Dev | FILTER-13516 | DEV -BE - Support Tool >> Custom list UI. Create custom list Resource and Edit custom list Resource, drawers donot check for duplicate Custom list resource. | FILTER-12904 | Defect | Prateek Fotedar | Code Review |  | P2 | 2026-04-14 |  | 2026-04-22 | sprint-Hanna | 0 | 5 | FILTER
Dev | FILTER-13712 | DEV - Support Tool >> Custom list UI. Need Validation for Resource and Type Mismatch | FILTER-13711 | Defect | Prateek Fotedar | Code Review |  | P3 | 2026-04-22 |  | 2026-04-23 | sprint-Hanna | 0 | 5 | FILTER
Dev | FILTER-13716 | DEV - Support Tool >> Custom list UI. Audit logs issues | FILTER-13715 | Escape Defect | Prateek Fotedar | Code Review |  | P3 | 2026-04-22 |  | 2026-04-23 | sprint-Hanna | 0 | 3 | FILTER
Dev | FILTER-12038 | Chrome extension bypass via bookmark + stopping request before block page loads | FILTER-12010 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-02-12 |  | 2026-04-14 | sprint-Hanna | 18 | 18 | FILTER
Dev | FILTER-12418 | Dev task for Analysis and Fix - P1 Escalation-File downloading in Image Google Search | FILTER-7666 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-03-12 |  | 2026-04-14 | sprint-Hanna | 16 | 16 | FILTER
Dev | FILTER-12456 | DEV - Filter bypass by taping on a link from Google Search - Crxtn | FILTER-12455 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-03-12 |  | 2026-04-14 | sprint-Hanna | 16 | 16 | FILTER
Dev | FILTER-12540 | DEV -Extension Bypass - Opening new tab | FILTER-12476 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-03-17 |  | 2026-04-28 | sprint-Hanna | 12 | 12 | FILTER
Dev | FILTER-12793 | [TS] DEV - Chrome Extension : Log in page is not shown | FILTER-12792 | Defect | Pratik Tiwari | Done |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 7 | 5 | FILTER
Dev | FILTER-12821 | DEV - Windows Extn : TS - Safe search is not getting applied immediately on google search engine(Ensure that api response shows SS enabled) | FILTER-12820 | Defect | Pratik Tiwari | Code Review |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 6 | FILTER
Dev | FILTER-13106 | DEV - Looking for solution for HTML Editor vulnerabilities | FILTER-13105 | Escape Defect | Pratik Tiwari | Done |  | P1 | 2026-04-02 |  | 2026-04-24 | sprint-Hanna | 12 | 12 | FILTER
Dev | FILTER-12144 | [sprox] Check requirement of populating msg wth NULL in processSocialMediaMsg | FILTER-12143 | Task | Ravi Raj | Closed without action |  | P3 | 2026-02-23 |  | 2026-04-27 | sprint-Hanna | 4 | 6 | FILTER
Dev | FILTER-13443 | DEV - SPROX: suicide.org throws Bad Request error | FILTER-13442 | Defect | Ravi Raj | Done |  | P1 | 2026-04-10 |  | 2026-04-14 | sprint-Hanna | 4 | 4 | FILTER
Dev | FILTER-13483 | DEV - SPROX: baidu.com suspicious searches are not logged | FILTER-13482 | Defect | Ravi Raj | Done |  | P1 | 2026-04-11 |  | 2026-04-16 | sprint-Hanna | 2 | 2 | FILTER
Dev | FILTER-13487 | DEV - SPROX: wikipedia searches are not logged when search is made from bookmark | FILTER-13486 | Defect | Ravi Raj | Done |  | P2 | 2026-04-11 |  | 2026-04-14 | sprint-Hanna | 2 | 2 | FILTER
Dev | FILTER-13491 | DEV - SPROX: ask.com suspicious & allowed searches are not logged | FILTER-13490 | Defect | Ravi Raj | Done |  | P1 | 2026-04-11 |  | 2026-04-16 | sprint-Hanna | 2 | 2 | FILTER
Dev | FILTER-13519 | DEV - SPROX: Search engines do not get blocked when category is Other Search Engine | FILTER-13518 | Defect | Ravi Raj | Done |  | P1 | 2026-04-14 |  | 2026-04-17 | sprint-Hanna | 2 | 2 | FILTER
Dev | FILTER-13527 | DEV - SPROX: YT keyword block is not getting logged | FILTER-13526 | Defect | Ravi Raj | Done |  | P1 | 2026-04-14 |  | 2026-04-27 | sprint-Hanna | 4 | 4 | FILTER
Dev | FILTER-13551 | Dev - SPROX - Changes to Onboard Beta FIDs | FILTER-13550 | Story | Ravi Raj | Done |  | P1 | 2026-04-15 |  | 2026-04-19 | sprint-Hanna | 16 | 16 | FILTER
Dev | FILTER-13558 | DEV - SPROX: GO DNS. Suspicious and allowed searches on any search engine is not getting logged | FILTER-13556 | Defect | Ravi Raj | Closed without action |  | P1 | 2026-04-15 |  | 2026-04-23 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-13564 | DEV - SPROX: GO DNS. YouTube video logging is not happening | FILTER-13562 | Defect | Ravi Raj | Done |  | P1 | 2026-04-15 |  | 2026-04-24 | sprint-Hanna | 4 | 4 | FILTER
Dev | FILTER-13588 | DEV - SPROX: GO DNS.Force Logins OFF. New categories are not getting blocked | FILTER-13587 | Defect | Ravi Raj | Done |  | P2 | 2026-04-16 |  | 2026-04-24 | sprint-Hanna | 2 | 2 | FILTER
Dev | FILTER-13602 | DEV - SPROX: GO DNS. Search terms not getting blocked on google.com | FILTER-13601 | Defect | Ravi Raj | Closed without action |  | P1 | 2026-04-16 |  | 2026-04-23 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-13636 | DEV - SPROX & Squid: GO SPAC/DNS. Custom group policy is not applied | FILTER-13635 | Defect | Ravi Raj | Closed without action |  | P1 | 2026-04-17 |  | 2026-04-20 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-13760 | DEV - Home SPROX: Pause is not getting applied for a kid with SPROX enabled | FILTER-13759 | Defect | Ravi Raj | Done |  | P1 | 2026-04-24 |  | 2026-04-24 | sprint-Hanna | 8 | 8 | FILTER
Dev | FILTER-12185 | Fix SSO access-token SameSite cookie and JWT secret for GO broker | FILTER-12048 | Escape Defect | Sagar Satpute | Done |  | P2 | 2026-02-25 |  | 2026-04-14 | sprint-Hanna | 13 | 13 | FILTER
Dev | FILTER-12324 | DEV - BugCrowd-850af9c1-f86b-4c74-91ac-94ea808c8e9b-Deleted User to Continue Performing Privileged Actions (Account Deletion Bypass) | FILTER-12323 | Defect | Sagar Satpute | Done |  | P3 | 2026-03-02 |  | 2026-04-15 | sprint-Hanna | 13 | 13 | FILTER
Dev | FILTER-13096 | DEV - On Support tool, if we turn on On-Call / Case manager setting along with Case Handled by as Both changes do not get saved | FILTER-13095 | Escape Defect | Sagar Satpute | Done |  | P3 | 2026-04-02 |  | 2026-04-22 | sprint-Hanna | 8 | 8 | FILTER
Dev | FILTER-13400 | DEV - Safety Console >> Filter. Activities. Deleted Admin group user is able add activities to Allow/Block list | FILTER-13399 | Defect | Sagar Satpute | Closed without action |  | P2 | 2026-04-09 |  | 2026-04-16 | sprint-Hanna | 2 | 2 | FILTER
Dev | FILTER-13504 | DEV - CLONE - SPROX: Wrong category logged | FILTER-13503 | Defect | Sagar Satpute | Done |  | P1 | 2026-04-13 |  | 2026-04-16 | sprint-Hanna | 8 | 8 | FILTER
Dev | FILTER-13543 | DEV - Safety Console >> Filter. Admin Group. Admin user if removed from DA, looses Admin session as well | FILTER-13542 | Defect | Sagar Satpute | Done |  | P0 | 2026-04-14 |  | 2026-04-15 | sprint-Hanna | 6 | 6 | FILTER
Dev | FILTER-13740 | DEV - P1 Escalation-Filter reports file URLs are easily guessable and the S3 bucket used for downloads is publicly accessible. | FILTER-13739 | Escape Defect | Sagar Satpute | Done |  | P1 | 2026-04-22 |  | 2026-04-24 | sprint-Hanna | 13 | 8 | FILTER
Dev | FILTER-13748 | DEV - Filter >> Download, Email, and Scheduled reports are not working. | FILTER-13743 | Escape Defect | Sagar Satpute | Closed without action |  | P0 | 2026-04-23 |  | 2026-04-24 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-13783 | DEV - Use common sso package - www-support-tool | FILTER-13782 | Story | Sagar Satpute | Done |  | P3 | 2026-03-29 |  | 2026-04-27 | sprint-Hanna | 10 | 16 | FILTER
Dev | FILTER-13786 | DEV - Use common sso package - www-filter | FILTER-13785 | Story | Sagar Satpute | Done |  | P3 | 2026-03-29 |  | 2026-04-27 | sprint-Hanna | 8 | 16 | FILTER
Escape Defect | FILTER-10462 | Security groups for customer are not able to be searched for, and initially do not show on Policy Map |  |  | Shailendra Singh | QA Verified | Fixed | P3 | 2025-10-17 | 2025-11-24 | 2026-04-27 | sprint-Hanna | 4 | 6 | FILTER | jira_added, jira_escalated, jira_in_progress, jira_p3, jira_reopened, zendesk_org_at_risk
Dev | FILTER-12703 | DEV - Support Tool >> Custom list UI. Custom List table and Custom List Resource table headers are not in bold | FILTER-12702 | Defect | Shailendra Singh | Done |  | P3 | 2026-03-26 |  | 2026-04-14 | sprint-Hanna | 2 | 2 | FILTER
Dev | FILTER-12773 | DEV - Support Tool >> Custom list UI. Custom List table >> List names become center aligned if the Brower Zoom is 110% or more. | FILTER-12772 | Defect | Shailendra Singh | Done |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 3 | 3 | FILTER
Dev | FILTER-12777 | DEV - Support Tool >> Custom list UI. Custom List table >> Action icons lose aligned if the Brower Zoom is 110% or more. | FILTER-12776 | Defect | Shailendra Singh | Done |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 3 | 3 | FILTER
Dev | FILTER-12857 | DEV - Support Tool >> Custom list UI. Custom List table >> "Updated on" field's date format is inconsistent with date format on FID listing page's " Last edited / created" field | FILTER-12856 | Defect | Shailendra Singh | Done |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 3 | 3 | FILTER
Dev | FILTER-12873 | DEV - Support Tool >> Custom list UI. Custom List table, Custom List Resource table >> icons section missing table header | FILTER-12872 | Defect | Shailendra Singh | Done |  | P3 | 2026-03-27 |  | 2026-04-20 | sprint-Hanna | 5 | 3 | FILTER
Dev | FILTER-12885 | DEV - Support Tool >> Custom list UI. Custom List table, Custom List Resource table >> Formatting issues in table if List Name and Comment is big (255 characters each) | FILTER-12884 | Defect | Shailendra Singh | Done |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 5 | 5 | FILTER
Dev | FILTER-12889 | DEV - Support Tool >> Custom list UI. Create custom list and Edit custom list, pages do not have * mark for Mandatory fields | FILTER-12888 | Defect | Shailendra Singh | Done |  | P3 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 4 | 4 | FILTER
Dev | FILTER-12897 | DEV - Support Tool >> Custom list UI. Create custom list Resource and Update custom list Resource, drawer should validated for comment length on Save of that drawer | FILTER-12896 | Defect | Shailendra Singh | Closed without action |  | P2 | 2026-03-27 |  | 2026-04-20 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-12905 | DEV - Support Tool >> Custom list UI. Create custom list Resource and Edit custom list Resource, drawers donot check for duplicate Custom list resource. | FILTER-12904 | Defect | Shailendra Singh | Done |  | P2 | 2026-03-27 |  | 2026-04-24 | sprint-Hanna | 4 | 4 | FILTER
Dev | FILTER-12909 | DEV - Support Tool >> Custom list UI. Edit custom list, User can change the Type on Edit. | FILTER-12908 | Defect | Shailendra Singh | Done |  | P1 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 6 | 6 | FILTER
Dev | FILTER-12933 | DEV - Support Tool >> Custom list UI. Edit custom list Search terms type, allows changing Match type and saves it. But does not reflect the change. | FILTER-12932 | Defect | Shailendra Singh | Closed without action |  | P1 | 2026-03-27 |  | 2026-04-15 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-13455 | DEV - Support Tool. After searching for FID from FID Detail page's FID name dropdown, the FID name is not cleared | FILTER-13454 | Escape Defect | Shailendra Singh | Done |  | P1 | 2026-04-11 |  | 2026-04-20 | sprint-Hanna | 4 | 4 | FILTER
Dev | FILTER-13459 | DEV - Support Tool. FID search from FID Detail page's FID name dropdown is not able to search when spaces are present at the start or end of the query. | FILTER-13458 | Escape Defect | Shailendra Singh | Done |  | P3 | 2026-04-11 |  | 2026-04-20 | sprint-Hanna | 3 | 3 | FILTER
Dev | FILTER-13463 | DEV - Support Tool. FID search from FID Detail page's FID name dropdown can search and display closed accounts as well | FILTER-13462 | Escape Defect | Shailendra Singh | Done |  | P2 | 2026-04-11 |  | 2026-04-20 | sprint-Hanna | 4 | 4 | FILTER
Dev | FILTER-13517 | Fix issue for Report section | FILTER-10462 | Escape Defect | Shailendra Singh | Done |  | P2 | 2026-04-14 |  | 2026-04-16 | sprint-Hanna | 4 | 4 | FILTER
QA | FILTER-11536 | Manual Testing Tokenization service for SPAC / DNS | FILTER-11532 | Story | Surabhi Choudhary | Done |  | P3 | 2025-12-19 |  | 2026-04-15 | sprint-Hanna | 16 | 16 | FILTER | Capitalized-Feature
QA | FILTER-11661 | Manual Testing Tokenization service for Extension | FILTER-11631 | Story | Surabhi Choudhary | Done |  | P3 | 2026-01-15 |  | 2026-04-14 | sprint-Hanna | 24 | 24 | FILTER | Capitalized-Feature
Test Case Creation | FILTER-11748 | Create test cases for Tokenization feature | FILTER-11532 | Story | Surabhi Choudhary | Done |  | P3 | 2026-01-21 |  | 2026-04-14 | sprint-Hanna | 8 | 8 | FILTER | Capitalized-Feature
QA | FILTER-12186 | Verify SSO access-token SameSite and JWT secret fixes for GO broker | FILTER-12048 | Escape Defect | Surabhi Choudhary | Done |  | P2 | 2026-02-25 |  | 2026-04-24 | sprint-Hanna | 1 | 1 | FILTER
QA | FILTER-12798 | QA- Update Cron Job for tokenization | FILTER-12796 | Task | Surabhi Choudhary | Done |  | P3 | 2026-03-27 |  | 2026-04-23 | sprint-Hanna | 2 | 2 | FILTER
QA | FILTER-13050 | QA- GO extension: proxy call shows success for unauthorized user | FILTER-13048 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-03-31 |  | 2026-04-21 | sprint-Hanna | 1 | 1 | FILTER
QA | FILTER-13078 | SPROX Manual Testing Phase 1 | FILTER-12200 | Task | Surabhi Choudhary | Done |  | P2 | 2026-04-01 |  | 2026-04-25 | sprint-Hanna | 24 | 24 | FILTER
QA | FILTER-13079 | Manual Testing Tokenization service for GO Extension | FILTER-11631 | Story | Surabhi Choudhary | Done |  | P2 | 2026-04-01 |  | 2026-04-14 | sprint-Hanna | 24 | 24 | FILTER | Capitalized-Feature
Task | FILTER-13288 | SPROX Manual Testing Phase 2 |  |  | Surabhi Choudhary | QA Verified |  | P2 | 2026-04-07 |  | 2026-04-25 | sprint-Hanna | 32 | 0 | FILTER
QA | FILTER-13289 | SPROX Manual Testing Phase 2 | FILTER-13288 | Task | Surabhi Choudhary | Done |  | P2 | 2026-04-07 |  | 2026-04-24 | sprint-Hanna | 24 | 24 | FILTER
QA | FILTER-13300 | QA- NewFeatureBug. GO DNS: Temporary UserToken is generated even when platform service is available | FILTER-13298 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-04-07 |  | 2026-04-23 | sprint-Hanna | 1 | 1 | FILTER
QA | FILTER-13312 | QA- NewFeatureBug. GO SPAC: UserToken not present for verbose logs | FILTER-13310 | Defect | Surabhi Choudhary | Done |  | P2 | 2026-04-07 |  | 2026-04-23 | sprint-Hanna | 1 | 1 | FILTER
QA | FILTER-13346 | QA- NewFeatureBug. SPAC: After anonymous user log, activities do not have userToken | FILTER-13344 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-04-08 |  | 2026-04-23 | sprint-Hanna | 1 | 1 | FILTER
QA | FILTER-13354 | QA- NewFeatureBug. SPAC: userToken not created when Force logins is ON | FILTER-13352 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-04-08 |  | 2026-04-23 | sprint-Hanna | 1 | 1 | FILTER
QA | FILTER-13444 | QA- SPROX: suicide.org throws Bad Request error | FILTER-13442 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-04-10 |  | 2026-04-16 | sprint-Hanna | 0.5 | 0.5 | FILTER
QA | FILTER-13484 | QA- SPROX: baidu.com suspicious searches are not logged | FILTER-13482 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-04-11 |  | 2026-04-16 | sprint-Hanna | 0.5 | 0.5 | FILTER
QA | FILTER-13488 | QA- SPROX: wikipedia searches are not logged when search is made from bookmark | FILTER-13486 | Defect | Surabhi Choudhary | Done |  | P2 | 2026-04-11 |  | 2026-04-17 | sprint-Hanna | 0.5 | 0.5 | FILTER
QA | FILTER-13492 | QA- SPROX: ask.com suspicious & allowed searches are not logged | FILTER-13490 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-04-11 |  | 2026-04-16 | sprint-Hanna | 0.5 | 0.5 | FILTER
QA | FILTER-13505 | QA- CLONE - SPROX: Wrong category logged | FILTER-13503 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-04-13 |  | 2026-04-17 | sprint-Hanna | 2 | 2 | FILTER
QA | FILTER-13509 | QA- SPROX: Incorrect policy logging | FILTER-13507 | Defect | Surabhi Choudhary | Closed without action |  | P1 | 2026-04-13 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13520 | QA- SPROX: Search engines do not get blocked when category is Other Search Engine | FILTER-13518 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-04-14 |  | 2026-04-17 | sprint-Hanna | 1 | 1 | FILTER
QA | FILTER-13528 | QA- SPROX: YT keyword block is not getting logged | FILTER-13526 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-04-14 |  | 2026-04-24 | sprint-Hanna | 0.5 | 0.5 | FILTER
QA | FILTER-13552 | QA - SPROX - Changes to Onboard Beta FIDs | FILTER-13550 | Story | Surabhi Choudhary | Done |  | P1 | 2026-04-15 |  | 2026-04-22 | sprint-Hanna | 9.5 | 4 | FILTER
QA | FILTER-13559 | QA- SPROX: GO DNS. Suspicious and allowed searches on any search engine is not getting logged | FILTER-13556 | Defect | Surabhi Choudhary | Closed without action |  | P1 | 2026-04-15 |  | 2026-04-23 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13560 | QA- SPROX: GO DNS. Suspicious and allowed searches on any search engine is not getting logged | FILTER-13556 | Defect | Surabhi Choudhary | Closed without action |  | P1 | 2026-04-15 |  | 2026-04-16 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13565 | QA- SPROX: GO DNS. YouTube video logging is not happening | FILTER-13562 | Defect | Surabhi Choudhary | Done |  | P1 | 2026-04-15 |  | 2026-04-24 | sprint-Hanna | 1 | 1 | FILTER
QA | FILTER-13566 | QA- SPROX: GO DNS. YouTube video logging is not happening | FILTER-13562 | Defect | Surabhi Choudhary | Closed without action |  | P2 | 2026-04-15 |  | 2026-04-16 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13589 | QA- SPROX: GO DNS.Force Logins OFF. New categories are not getting blocked | FILTER-13587 | Defect | Surabhi Choudhary | Done |  | P2 | 2026-04-16 |  | 2026-04-24 | sprint-Hanna | 1 | 1 | FILTER
QA | FILTER-13603 | QA- SPROX: GO DNS. Search terms not getting blocked on google.com | FILTER-13601 | Defect | Surabhi Choudhary | Closed without action |  | P1 | 2026-04-16 |  | 2026-04-23 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13637 | QA- SPROX & Squid: GO SPAC/DNS. Custom group policy is not applied | FILTER-13635 | Defect | Surabhi Choudhary | Closed without action |  | P1 | 2026-04-17 |  | 2026-04-20 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13732 | QA- SPROX: Filter leaks within the 10 mins ban | FILTER-13730 | Defect | Surabhi Choudhary | Done |  | P2 | 2026-04-22 |  | 2026-04-23 | sprint-Hanna | 0.5 | 0.5 | FILTER
Dev | FILTER-13626 | Check and fix deque reported issues for Filter | FILTER-13620 | Story | Swaroop Chavhan | Done |  | P2 | 2026-04-17 |  | 2026-04-22 | sprint-Hanna | 16 | 16 | FILTER
Dev | FILTER-11655 | Fix Crextn Not Blocking Google Workspace Apps (Docs, Slides, Meet, Drive, etc. | FILTER-11654 | Escape Defect | Vaibhav Kumbhar | Done |  | P1 | 2026-01-15 |  | 2026-04-14 | sprint-Hanna | 16 | 24 | FILTER
Dev | FILTER-12177 | Investigate and close about:blank loophole used to bypass filtering and access competitor content | FILTER-12119 | Escape Defect | Vaibhav Kumbhar | Code Review |  | P1 | 2026-02-25 |  | 2026-04-24 | sprint-Hanna | 20 | 13 | FILTER
Dev | FILTER-12448 | DEV - Site not loading correctly with extension | FILTER-12447 | Escape Defect | Vaibhav Kumbhar | Code Review |  | P3 | 2026-03-12 |  | 2026-04-14 | sprint-Hanna | 11 | 20 | FILTER
Dev | FILTER-12717 | DEV - TS Ext + Go. Site Approved via TWL process, gets logged in Default Policy rather than Global Policy | FILTER-12716 | Escape Defect | Vaibhav Kumbhar | Done |  | P2 | 2026-03-26 |  | 2026-04-14 | sprint-Hanna | 8 | 6 | FILTER
Dev | FILTER-13049 | DEV - GO extension: proxy call shows success for unauthorized user | FILTER-13048 | Defect | Vaibhav Kumbhar | Done |  | P1 | 2026-03-31 |  | 2026-04-14 | sprint-Hanna | 6 | 6 | FILTER
Dev | FILTER-13646 | DEV - [Proxy]: Send fid and userEmail to pagescan | FILTER-13645 | Task | Vaibhav Kumbhar | Done |  | P1 | 2026-04-20 |  | 2026-04-21 | sprint-Hanna | 6 | 6 | FILTER

## Not Completed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Task | FILTER-13553 | Automation UI script Enhancement: |  |  | Amit Shete | In Progress |  | P2 | 2026-04-15 |  | 2026-04-28 | sprint-Hanna | 1.5 | 6 | FILTER | unplanned-sprint |  | YES
Task | FILTER-13554 | Automation API script enhancements |  |  | Amol Mithari | In Progress |  | P2 | 2026-04-15 |  | 2026-04-28 | sprint-Hanna | 46 | 45 | FILTER | unplanned-sprint |  | YES
Task | FDSE-155 | Implementation for timepicker component | FDSE-136 | Epic | Swaroop Chavhan | Open |  | P3 | 2026-01-29 |  | 2026-04-28 | sprint-Hanna | 0 | 32 | FDSE | product-filter |  | YES
Task | FDSE-164 | Search with auto-complete component enhancement | FDSE-174 | Epic | Swaroop Chavhan | Open |  | P3 | 2026-02-26 |  | 2026-04-28 | sprint-Hanna | 0 | 20 | FDSE | Capitalized-Feature, product-filter |  | YES
QA | FILTER-12621 | QA- Policy Map Import not showing policy names ¦ San Ramon | FILTER-12619 | Escape Defect | Altamash Heroli | Open |  | P1 | 2026-03-23 |  | 2026-04-26 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-12906 | QA- Support Tool >> Custom list UI. Create custom list Resource and Edit custom list Resource, drawers donot check for duplicate Custom list resource. | FILTER-12904 | Defect | Altamash Heroli | Open |  | P2 | 2026-03-27 |  | 2026-04-24 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13644 | QA - Chrome Extension is causing specific form not to load | FILTER-10053 | Escape Defect | Altamash Heroli | Open |  | P1 | 2026-04-20 |  | 2026-04-20 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13663 | Regression testing for Filter product | FILTER-13657 | Story | Altamash Heroli | Backlog |  | P2 | 2026-04-21 |  | 2026-04-27 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13665 | Regression testing for Support-ool product | FILTER-13657 | Story | Altamash Heroli | Backlog |  | P2 | 2026-04-21 |  | 2026-04-27 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13713 | QA- Support Tool >> Custom list UI. Need Validation for Resource and Type Mismatch | FILTER-13711 | Defect | Altamash Heroli | Open |  | P3 | 2026-04-22 |  | 2026-04-27 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13717 | QA- Support Tool >> Custom list UI. Audit logs issues | FILTER-13715 | Escape Defect | Altamash Heroli | Open |  | P3 | 2026-04-22 |  | 2026-04-27 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13784 | QA- Use common sso package - www-support-tool | FILTER-13782 | Story | Altamash Heroli | Ready for QA |  | P3 | 2026-03-29 |  | 2026-04-27 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13787 | QA- Use common sso package - www-filter | FILTER-13785 | Story | Altamash Heroli | Ready for QA |  | P3 | 2026-03-29 |  | 2026-04-27 | sprint-Hanna | 0 | 0 | FILTER
QA | PTGM-701 | Validate fix for FATAL and Panic issues in www-support-tool repo | PTGM-698 | Story | Altamash Heroli | Open |  | P2 | 2026-04-13 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | PTGM
QA | FILTER-11844 | Verify fix for SafetyConsole CustomList API - Token invalidation on re-authentication | FILTER-11687 | Defect | Amit Shete | Open |  | P2 | 2026-01-29 |  | 2026-04-27 | sprint-Hanna | 0 | 2 | FILTER
QA | FILTER-11873 | Verify CustomList API returns 401 when Filter Product is disabled | FILTER-11688 | Escape Defect | Amit Shete | Ready for QA |  | P3 | 2026-01-29 |  | 2026-04-27 | sprint-Hanna | 0 | 2 | FILTER
Automation | FILTER-12179 | Scripting for about:blank loophole fix – policy and redirect behavior | FILTER-12119 | Escape Defect | Amit Shete | Open |  | P1 | 2026-02-25 |  | 2026-04-14 | sprint-Hanna | 0 | 4 | FILTER
Automation | FILTER-12515 | QA- [Extension API Fortification]Tasks for Verified access api | FILTER-12512 | Task | Amit Shete | Open |  | P1 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12622 | QA- Policy Map Import not showing policy names ¦ San Ramon | FILTER-12619 | Escape Defect | Amit Shete | Scripting in progress |  | P1 | 2026-03-23 |  | 2026-04-26 | sprint-Hanna | 0 | 3 | FILTER
Automation | FILTER-12823 | QA- Windows Extn : TS - Safe search is not getting applied immediately on google search engine(Ensure that api response shows SS enabled) | FILTER-12820 | Defect | Amit Shete | Open |  | P2 | 2026-03-27 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13098 | QA- On Support tool, if we turn on On-Call / Case manager setting along with Case Handled by as Both changes do not get saved | FILTER-13095 | Escape Defect | Amit Shete | Open |  | P3 | 2026-04-02 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13120 | QA- Students bypassing Filter using scrlybrkr | FILTER-13117 | Escape Defect | Amit Shete | Open |  | P1 | 2026-04-02 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13338 | QA- Image Blur Feature: Google Drive - Download and Copy options available for blurred images | FILTER-13335 | Defect | Amit Shete | Open |  | P1 | 2026-04-08 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13481 | QA- SPROX: yahoo.com loading and search issue | FILTER-13478 | Defect | Amit Shete | Open |  | P1 | 2026-04-11 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13714 | QA- Support Tool >> Custom list UI. Need Validation for Resource and Type Mismatch | FILTER-13711 | Defect | Amit Shete | Open |  | P3 | 2026-04-22 |  | 2026-04-27 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-13718 | QA- Support Tool >> Custom list UI. Audit logs issues | FILTER-13715 | Escape Defect | Amit Shete | Open |  | P3 | 2026-04-22 |  | 2026-04-27 | sprint-Hanna | 0 | 0 | FILTER
Automation | FILTER-12542 | Automation -Extension Bypass - Opening new tab | FILTER-12476 | Escape Defect | Amol Mithari | Open |  | P1 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 2 | FILTER
Dev | FILTER-11483 | Fix Canva.com NSFW Video Classification Timeout and Safe Image Click Blockers | FILTER-11418 | Defect | Arun Thakur | In Progress |  | P2 | 2025-12-19 |  | 2026-04-27 | sprint-Hanna | 6 | 6 | FILTER
Dev | FILTER-12282 | DE- JS (ALL Extensions) Image Blur model behaves differently on GSheet, Drive, Gslide, Email, PDF, GDoc | FILTER-12281 | Defect | Arun Thakur | In Progress |  | P2 | 2026-02-26 |  | 2026-04-27 | sprint-Hanna | 12 | 12 | FILTER
Dev | FILTER-12620 | DEV - Policy Map Import not showing policy names ¦ San Ramon | FILTER-12619 | Escape Defect | Arun Thakur | Open |  | P1 | 2026-03-23 |  | 2026-04-26 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-13826 | Dev Task for Beta flag | FILTER-12119 | Escape Defect | Arun Thakur | Open |  | P1 | 2026-04-28 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-12516 | Integrate the Google Verified Access API using a Google Service Account for secure server-to-server communication. | FILTER-12512 | Task | Ashish Modak | In Progress |  | P3 | 2026-03-17 |  | 2026-04-16 | sprint-Hanna | 0 | 16 | FILTER
Dev | FILTER-12517 | Create a Google Service Account and request an increase in the Requests Per Minute (RPM) quota from Google. | FILTER-12512 | Task | Ashish Modak | Open |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-12518 | Add logic to classify devices into High, Medium, and Low confidence levels based on the Verified Access response and validation checks. | FILTER-12512 | Task | Ashish Modak | Open |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-12519 | Implement a centralized rate-limiting mechanism for Verified Access API calls to prevent abuse and excessive requests. | FILTER-12512 | Task | Ashish Modak | Open |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-12520 | Ensure the implementation is backward compatible with existing authentication and device validation flows. | FILTER-12512 | Task | Ashish Modak | Open |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-12521 | Document step-by-step instructions to enable Verified Access in the Google Admin Console and configure the extension. | FILTER-12512 | Task | Ashish Modak | Open |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-12522 | Implement JWT-based authentication for Chrome and Edge browser extensions. | FILTER-12512 | Task | Ashish Modak | Open |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-12523 | Add a JWT token refresh mechanism for Chrome and Edge browser extensions to maintain valid sessions. | FILTER-12512 | Task | Ashish Modak | Open |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-12524 | Include the JWT token in request headers for all relevant APIs. | FILTER-12512 | Task | Ashish Modak | Open |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-12525 | Validate that existing SRE Broker APIs continue to function correctly after the Verified Access integration.\ | FILTER-12512 | Task | Ashish Modak | Open |  | P3 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-11485 | Fix Canva.com NSFW Video Classification Timeout and Safe Image Click Blockers | FILTER-11418 | Defect | Ayesha Kamde | Open |  | P2 | 2025-12-19 |  | 2026-04-16 | sprint-Hanna | 2 | 2 | FILTER
QA | FILTER-12178 | Verify about:blank loophole fix – block/redirect unless opened from allowed site | FILTER-12119 | Escape Defect | Ayesha Kamde | Open |  | P1 | 2026-02-25 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-12283 | QA- JS (ALL Extensions) Image Blur model behaves differently on GSheet, Drive, Gslide, Email, PDF, GDoc | FILTER-12281 | Defect | Ayesha Kamde | Open |  | P2 | 2026-02-26 |  | 2026-04-16 | sprint-Hanna | 3 | 2 | FILTER
QA | FILTER-12395 | QA- DA Filter >> Activities. DA is able to see activities of kids from other OU as well | FILTER-12393 | Defect | Ayesha Kamde | Open |  | P1 | 2026-03-09 |  | 2026-04-14 | sprint-Hanna | 0 | 2 | FILTER
QA | FILTER-12429 | [TS Extension] QA task to reverify issue - crextn - initial broker skips iframes | FILTER-12427 | Task | Ayesha Kamde | Open |  | P2 | 2026-03-12 |  | 2026-04-21 | sprint-Hanna | 1 | 2 | FILTER
QA | FILTER-12449 | QA- Site not loading correctly with extension | FILTER-12447 | Escape Defect | Ayesha Kamde | Open |  | P3 | 2026-03-12 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-12514 | QA- [Extension API Fortification]Tasks for Verified access api | FILTER-12512 | Task | Ayesha Kamde | Open |  | P1 | 2026-03-17 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-12541 | QA -Extension Bypass - Opening new tab - Fix Test | FILTER-12476 | Escape Defect | Ayesha Kamde | Ready for QA |  | P1 | 2026-03-17 |  | 2026-04-28 | sprint-Hanna | 0 | 5 | FILTER
QA | FILTER-13119 | QA- Students bypassing Filter using scrlybrkr | FILTER-13117 | Escape Defect | Ayesha Kamde | Open |  | P1 | 2026-04-02 |  | 2026-04-17 | sprint-Hanna | 0 | 0 | FILTER
QA | FILTER-13337 | QA- Image Blur Feature: Google Drive - Download and Copy options available for blurred images | FILTER-13335 | Defect | Ayesha Kamde | Open |  | P1 | 2026-04-08 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-13658 | Dependabot fixes for Filter product | FILTER-13657 | Story | Harshada Kude | In Progress |  | P2 | 2026-04-21 |  | 2026-04-23 | sprint-Hanna | 0 | 14 | FILTER
Dev | FILTER-11843 | SafetyConsole CustomList API - Old access tokens remain valid after new token generation | FILTER-11687 | Defect | Prateek Fotedar | Reopened |  | P2 | 2026-01-29 |  | 2026-04-28 | sprint-Hanna | 12 | 12 | FILTER
Dev | FILTER-11872 | SafetyConsole CustomList API - Token should be invalidated when Filter Product is disabled | FILTER-11688 | Escape Defect | Prateek Fotedar | Reopened |  | P3 | 2026-01-29 |  | 2026-04-28 | sprint-Hanna | 1 | 8 | FILTER
Dev | PTGM-700 | Dev task to Scan and fix FATAL and Panic issues in www-support-tool repo | PTGM-698 | Story | Prateek Fotedar | Open |  | P2 | 2026-04-13 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | PTGM
Dev | FILTER-12428 | [TS Extension]DEV - CLONE - crextn - initial broker skips iframes | FILTER-12427 | Task | Pratik Tiwari | Reopened |  | P2 | 2026-03-12 |  | 2026-04-21 | sprint-Hanna | 3 | 4 | FILTER
Dev | FILTER-13118 | DEV - Students bypassing Filter using scrlybrkr | FILTER-13117 | Escape Defect | Pratik Tiwari | Open |  | P1 | 2026-04-02 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-13643 | DEV - Chrome Extension is causing specific form not to load | FILTER-10053 | Escape Defect | Pratik Tiwari | Open |  | P1 | 2026-04-20 |  | 2026-04-20 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-13479 | DEV - SPROX: yahoo.com loading and search issue | FILTER-13478 | Defect | Ravi Raj | Open |  | P1 | 2026-04-11 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Dev | FILTER-13660 | Dependabot fixes for Support-tool product | FILTER-13657 | Story | Shailendra Singh | In Progress |  | P2 | 2026-04-21 |  | 2026-04-22 | sprint-Hanna | 0 | 10 | FILTER
QA | FILTER-13480 | QA- SPROX: yahoo.com loading and search issue | FILTER-13478 | Defect | Surabhi Choudhary | Open |  | P1 | 2026-04-11 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FILTER
Sub-task | FDSE-163 | Dev Task - Implementation for timepicker component | FDSE-155 | Task | Swaroop Chavhan | Open |  | P3 | 2026-02-22 |  | 2026-04-14 | sprint-Hanna | 0 | 0 | FDSE

## Removed
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Added Mid-Sprint
Debug | FILTER-13610 | Convert NSFW Image Blur JavaScript Code to TypeScript in securly-extension Repo Using Cursor Skills |  |  | Arun Thakur | Open |  | P2 | 2026-04-16 |  | 2026-04-22 | sprint-Hanna | 0 | 0 | FILTER | unplanned-sprint |  | YES
Task | FILTER-10604 | Placeholder task to track the efforts used for Vanta tool task completion |  |  | Harsh Verma | In Progress |  | P3 | 2025-11-03 |  | 2026-04-27 | sprint-Hanna | 0 | 8 | FILTER | unplanned-sprint |  | YES
Task | FILTER-11697 | Extension of FILTER-11605 |  |  | Harsh Verma | In Progress |  | P3 | 2026-01-19 |  | 2026-04-27 | sprint-Hanna | 0 | 24 | FILTER | unplanned-sprint |  | YES
Debug | FILTER-13047 | Need to work on Secrets identified on Filter/Aware repo |  |  | Harsh Verma | Open |  | P3 | 2026-03-31 |  | 2026-04-27 | sprint-Hanna | 0 | 16 | FILTER | unplanned-sprint |  | YES
Escape Defect | FILTER-12010 | P1 Escalation-Extension Bypass - Bookmark + stop page |  |  | Pratik Tiwari | Confirmation | Fixed | P1 | 2026-02-10 | 2026-04-06 | 2026-04-28 | sprint-Hanna | 20 | 0 | FILTER | jira_added, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_p1, jira_qa_verified, zendesk_enterprise, zendesk_org_at_risk |  | YES
Defect | FILTER-7955 | [TS Extension]Google search results appear while typing in the bar |  |  | Pratik Tiwari | Open |  | P2 | 2025-04-18 |  | 2026-04-27 | sprint-Hanna | 0 | 0 | FILTER | EXTN, MV3 |  | YES
Story | FILTER-12473 | Filter + Aware Accessibility - Mat tree |  |  | Swaroop Chavhan | Backlog |  | P3 | 2026-03-13 |  | 2026-04-21 | sprint-Hanna | 0 | 0 | FILTER |  |  | YES
Task | FILTER-13080 | Generate context for filter | FILTER-12341 | Epic | Vaibhav Kumbhar | Code Review | Fixed | P3 | 2026-04-01 | 2026-04-27 | 2026-04-27 | sprint-Hanna | 2 | 0 | FILTER | unplanned-sprint |  | YES
Story | FILTER-12400 | P1 Escalation - Extension API Fortification |  |  | Ashish Modak | Open |  | P1 | 2026-03-10 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER | p1escalation, unplanned-sprint
Escape Defect | FILTER-10780 | SmartPAC on iOS can be broken by changing time on the iPad ¦ St. Vrain |  |  | Ashish Temurnikar | Open |  | P2 | 2025-11-13 |  | 2026-04-27 | sprint-Hanna | 5 | 0 | FILTER | jira_added, jira_backlog, jira_escalated, jira_open, jira_p2, zendesk_enterprise
Task | FILTER-13290 | Update Filter code to route subdomains to PS whose parent domain categorization is enabled for Crextn |  |  | Sagar Satpute | Code Review | Fixed | P2 | 2026-04-07 | 2026-04-27 | 2026-04-28 | sprint-Hanna | 1 | 0 | FILTER

## P1 Escalation
P1 Escalation — FILTER · sprint-Hanna (2026-04-14 → 2026-04-27)
sprint-Hanna tickets where Issue Type = Escape Defect AND Priority = P1 AND summary contains 'P1 Escalation' (regardless of bucket). Total = 9.
Issue Type | Issue key | Summary | Parent key | Parent type | Assignee | Status | Resolution | Priority | Created | Resolved | Updated | Sprint | Time Spent | Original Est | Project | Labels | Blockers | Bucket
Escape Defect | FILTER-13117 | P1 Escalation-Students bypassing Filter using scrlybrkr |  |  | Dmitri Zhylienkov | Waiting on support |  | P1 | 2026-04-02 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER | jira_added, jira_escalated, jira_open, jira_p1, p1escalation, zendesk_enterprise, zendesk_org_at_risk |  | Removed
Escape Defect | FILTER-10053 | P1 Escalation-Chrome Extension is causing specific form not to load |  |  | Shashank Tiwari | Open |  | P1 | 2025-09-15 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER | Reverified-2025, jira_added, jira_backlog, jira_escalated, jira_open, jira_p1, jira_p2, jira_p3, p1escalation, unplanned-sprint, zendesk_enterprise |  | Not Completed
Escape Defect | FILTER-12119 | P1 Escalation-Investigate and address the use of about:blank pages as a filter loophole |  |  | Shashank Tiwari | In Progress |  | P1 | 2026-02-20 |  | 2026-04-28 | sprint-Hanna | 20 | 0 | FILTER | jira_added, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_p2, p1escalation, zendesk_enterprise, zendesk_org_at_risk |  | Not Completed
Escape Defect | FILTER-12476 | P1 Escalation-Extension Bypass - Opening new tab |  |  | Shashank Tiwari | QA READY | Fixed | P1 | 2026-03-13 | 2026-04-28 | 2026-04-28 | sprint-Hanna | 1 | 0 | FILTER | jira_added, jira_escalated, jira_in_progress, jira_open, jira_p1, zendesk_enterprise |  | Removed
Escape Defect | FILTER-12619 | P1 Escalation-Policy Map Import not showing policy names ¦ San Ramon |  |  | Shashank Tiwari | Waiting on support |  | P1 | 2026-03-23 |  | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_p2, jira_p3, p1escalation, zendesk_enterprise |  | Removed
Escape Defect | FILTER-12010 | P1 Escalation-Extension Bypass - Bookmark + stop page |  |  | Pratik Tiwari | Confirmation | Fixed | P1 | 2026-02-10 | 2026-04-06 | 2026-04-28 | sprint-Hanna | 20 | 0 | FILTER | jira_added, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_p1, jira_qa_verified, zendesk_enterprise, zendesk_org_at_risk |  | Removed
Escape Defect | FILTER-11654 | P1 Escalation-Crextn blocking issue with Google Workspace apps | FILTER-4326 | Epic | Shashank Tiwari | QA Verified | Done | P1 | 2026-01-15 | 2026-04-06 | 2026-04-28 | sprint-Hanna | 0 | 0 | FILTER | jira_added, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_qa_verified, jira_resolved |  | Completed
Escape Defect | FILTER-13105 | P1 Escalation-Looking for solution for HTML Editor vulnerabilities |  |  | Shashank Tiwari | QA Verified | Configuration Issue | P1 | 2026-04-02 | 2026-04-17 | 2026-04-27 | sprint-Hanna | 21 | 0 | FILTER | Reverified-2026, jira_added, jira_closed_notify, jira_done, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_qa_verified, p1escalation, unplanned-sprint, zendesk_enterprise |  | Completed
Escape Defect | FILTER-7666 | P1 Escalation-File downloading in Image Google Search |  |  | Shashank Tiwari | Confirmation | Cannot Reproduce | P1 | 2025-03-26 | 2025-09-04 | 2026-04-28 | sprint-Hanna | 2 | 12 | FILTER | Reverified-2026, jira_added, jira_backlog, jira_closed_notify, jira_confirmation, jira_done_notified, jira_escalated, jira_in_progress, jira_open, jira_p1, jira_reopened, jira_resolved, zendesk_org_at_risk |  | Removed